## Slide 1
September 2026
Pet Build Portfolio
Delivery Review
Nationwide Pet | Monthly Delivery Review
Reporting month: September 2026 Snapshot date: 9/30/2026

## Slide 2
September remains executable, but four Red projects concentrate the immediate risk.
RAG MIX — SOURCE-SET COMPARISON
Chart: 
| Green | Yellow | Red | Compl. | Not Assd.
August deck (43) | 25 | 9 | 3 | 5 | 1
September Planview (48) | 18 | 3 | 4 | 5 | 18
Portfolio scope and source coverage changed; mix is directional, not like-for-like.
TOP FIVE DELIVERY RISKS
PPT Program — Bundle 4 testing delays hit Bundle 5 and overall schedule; 2027 funding noted.
PPT Payroll Billing — UAT behind plan; no confirmed PDX dev/test and UAT timeline supplied.
Underwriting Question Optimization — Red; MVP3 depends on DDIT, sequencing, +$150K 2027.
FirstVet Consultation File API — Red; +$16.5K pending BDE and vendor integration activity.
PEC / TaiLWIND — environment data reset threatens PEC E2E; TaiLWIND dependency / DDIT risk.
TOP FIVE ACHIEVEMENTS
Add-A-Pet Improvements — production implementation completed 9/16 with monitoring/warranty.
MPPC UW Questions MVP3 — MVP3 production release 9/16; warranty release 9/23.
PPT REN2GIN Migration — SOW finalized; discovery and migration progress across lines.
MM-to-MM Non-CA Migration — SOW finalized; kickoff, requirements, discovery underway.
GIN API v5 Upgrades — Claims DDIT in progress; added-API analysis complete.
UPCOMING GO-LIVES / MILESTONES
FirstVet release milestones open — 10/12/2026 target dates in Planview.
PPT Program Employer Portal go-live — 11/11/2026.
PPT Payroll Billing Go Live — 11/11/2026.
Underwriting Opt. MVP3 production 2/10/2027; schedule finish 4/30/2027.
Where no committed date is supplied: Not supplied.
October 12 weekly update used only for supplemental context; September Planview remains authoritative.

## Slide 3
Four Red and three Yellow projects require active mitigation entering October.
Red
Yellow
Green
Completed
Not Assessed
Project | Work ID | Prev. RAG | Current RAG | Key Driver | Target Delivery
NW Pet – PPT Program | 1014117 | Yellow | Red | Employer Portal Bundle 4 testing delays; Bundle 5/6 and program schedule impact; 2027 funding request noted | Employer Portal go-live 11/11/2026
NW Pet: FirstVet Consultation File API | 1031012 | Yellow | Red | Additional $16.5K budget request pending BDE; vendor integration and release readiness | Schedule finish 10/30/2026; open release milestones 10/12/2026
NW Pet: PPT Payroll Billing Employer Experience | 1029802 | Yellow | Red | UAT start behind plan; PDX development/testing and UAT dates not confirmed | Go Live 11/11/2026
NW Pet: Underwriting Question Optimization for MPI | 1030240 | Green | Red | September status Red; remaining DDIT and cross-team sequencing; $150K 2027 funding approval item | Schedule finish 4/30/2027; MVP3 production 2/10/2027
NW Pet: NJ MPPC New Product and Rate Capping | 1029148 | Yellow | Yellow | Outstanding reporting work; rate-capping scope requires auditability and customer-service visibility | Schedule finish 10/12/2026
NW Pet: PEC Product and Underwriting Enhancements | 1029313 | Green | Yellow | QA validation on hold until 9/30 environment reset; E2E timing at risk | Schedule finish 1/29/2027
NW Pet: TaiLWIND Phase 1 (Claims AI) | 1029859 | Yellow | Yellow | Cross-team dependency timing, DDIT completion risk, and phased testing | Schedule finish 9/30/2027
NR = Not Reported (no matching August source value).

## Slide 4
Green delivery remains concentrated in active modernization and migration work.
Green — 1 of 2
Red
Yellow
Green
Completed
Not Assessed
Project | Work ID | Prev. RAG | Current RAG | Key Driver | Target Delivery
NW Pet - PPT - REN2GIN Policy migration-B2C | 1014865 | Green | Green | SOW finalized; migration discovery and policy conversion progress | Overall finish 4/10/2035; manual migration milestones in source
NW Pet – PPT – Major Medical – New Business on GIN | 1014368 | Green | Green | MiM capacity commitment; refinement and DDIT progressing | 2/10/2027
NW Pet: 2026 GIN Upgrades | 1029587 | Green | Green | Requirements/scope and line schedule being finalized | 2/26/2027
NW Pet: 2026 Product Rate Refresh | 1029254 | Green | Green | DDIT/UAT/production activity reported as complete in source | Overall finish 1/26/2027
NW Pet: Add-A-Pet Improvements | 1029314 | Red | Green | Production implementation completed 9/16; warranty monitoring | Overall finish 6/21/2028
NW Pet: Enhance Multi Denial Code Claims Z160/Z151 | 1029586 | Green | Green | Requirements on hold / Nov release alignment; target 11/11 | 12/31/2026
NW Pet: GIN API v5 Upgrades | 1029979 | Yellow | Green | Claims DDIT in progress; additional API analysis complete | 2/2/2027
NW Pet: Move Informatica Powercenter, SQL & Windows | 1029588 | Green | Green | Migration planning and line engagement | 12/30/2026
NW Pet: MPPC to MPI Conversion at Notice of Cancel | 1031134 | Green | Green | Design simplification and release planning | Overall finish 1/14/2027; release milestones in source
NR = Not Reported (no matching August source value).

## Slide 5
Green projects also include completed releases and platform stability work moving through milestones.
Green — 2 of 2
Red
Yellow
Green
Completed
Not Assessed
Project | Work ID | Prev. RAG | Current RAG | Key Driver | Target Delivery
NW Pet: Non-Insurance Pet Protection Bundle | 1024485 | Completed | Green | Production release complete; reporting follow-up remains | 10/30/2026
NW Pet: Paperless E-Delivery | 1026960 | Completed | Green | One-time data load and MMP2 warranty complete | 10/29/2026
NW Pet: PET Enhancement - MPPC UW Questions MVP3 | 1030950 | Green | Green | MVP3 release 9/16 and warranty release 9/23 | Overall finish 3/10/2027; MVP3.5 production 2/10/2027
NW Pet: Portal and GIN Stability | 1031470 | Yellow | Green | Stability work and platform hardening in progress | 3/31/2027
NW Pet: Portal Stability Work | 1029256 | Yellow | Green | September scope delivered; source supports continued platform work | 12/31/2026
NW Pet: Pricing Segmentation Sophistication | 1024050 | Green | Green | Release wave execution and state scope management | 1/13/2027
NW Pet: QEC A/B Testing & Tool Enhancements | 1028060 | Green | Green | Funnel and experience optimization work | 12/31/2026
NW Pet: Refresh the Windows 2016 Server | 1029977 | Green | Green | Server OS upgrade delivery in progress | 12/31/2026
Pet Data Center Transition | 1022011 | Completed | Green | Successful cutover / transition work reflected in source | 10/12/2026
NR = Not Reported (no matching August source value).

## Slide 6
Five projects are classified Completed by the September Planview lifecycle field.
Red
Yellow
Green
Completed
Not Assessed
Project | Work ID | Prev. RAG | Current RAG | Key Driver | Target Delivery
NW Pet: Callback Widget for PET Tool | 1032259 | NR | Completed | Lifecycle Stage = Completed; no current RAG supplied | Not supplied
NW Pet: Enhancement for Commission Reporting | 1029608 | Green | Completed | Lifecycle Stage = Completed | Not supplied
NW Pet: MM to MM Non CA Migration Capability | 1030589 | Green | Completed | Lifecycle Stage = Completed | Schedule finish 4/30/2027 in source
NW Pet: Unapproved States Product Build | 1030587 | Green | Completed | Lifecycle Stage = Completed | Schedule finish 12/31/2027 in source
Pet Small Projects allocation for MM | 1015021 | NR | Completed | Lifecycle Stage = Completed | Schedule finish 12/31/2026 in source
Completed classification is based on the September Planview lifecycle field; no additional completion claims are added. NR = Not Reported.

## Slide 7
Eighteen projects have no September overall RAG; visibility should not be confused with delivery health.
Not Assessed — 1 of 2
Red
Yellow
Green
Completed
Not Assessed
Project | Work ID | Prev. RAG | Current RAG | Key Driver | Target Delivery
NW Pet: AR Report vs. GL inconsistencies | 1031458 | NR | Not Assessed | Planning / P2B work shown; no overall RAG supplied | 12/31/2026
NW Pet: Claims History Report for GIN | 1032289 | NR | Not Assessed | Work description supplied; no overall RAG supplied | Not supplied
NW Pet: Data Quality Submission Chatbot | 1032487 | NR | Not Assessed | Data quality intake / agent concept supplied; no overall RAG supplied | 10/16/2026
NW Pet: DNS & Regi Updates Moniker to CSCglobal | 1031784 | NR | Not Assessed | Intake limited to registration movement; no overall RAG supplied | 11/30/2026
NW Pet: Enable PED Override for MPPC Payroll | 1030826 | NR | Not Assessed | Work description supplied; no overall RAG supplied | Not supplied
NW Pet: Enable Policy Search in EID in GIN | 1032258 | NR | Not Assessed | Policy-search scope supplied; no overall RAG supplied | 11/30/2026
NW Pet: GIN BPG8 Task Update | 1031455 | NR | Not Assessed | Task-date change supplied; no overall RAG supplied | 11/30/2026
NW Pet: GIN Cap/Scalability to 1.5-2M policies | 1032177 | NR | Not Assessed | Additional funding / scalability scope noted; no overall RAG supplied | 1/7/2027
NW Pet: IT Operational Risk Reserve | 1032179 | NR | Not Assessed | Reserve / OTL support item; no overall RAG supplied | 12/31/2026
Not Assessed = September Planview supplied no overall RAG. NR = Not Reported.

## Slide 8
The remaining Not Assessed items are retained as source gaps, not inferred health ratings.
Not Assessed — 2 of 2
Red
Yellow
Green
Completed
Not Assessed
Project | Work ID | Prev. RAG | Current RAG | Key Driver | Target Delivery
NW Pet: MA Junk Fee Regulation | 1029723 | NR | Not Assessed | Compliance scope supplied; no overall RAG supplied | 12/31/2026
NW Pet: MA MPPC Dec Page Update | 1032274 | NR | Not Assessed | Form-mapping scope supplied; no overall RAG supplied | 12/14/2026
NW Pet: Perks Page + uplift in Portal | 1031021 | NR | Not Assessed | Portal page scope supplied; no overall RAG supplied | 11/30/2026
NW Pet: Pet Analytics Model Outputs S3 Bucket | 1030239 | NR | Not Assessed | Governed analytics-output storage scope supplied; no overall RAG supplied | 12/8/2026
NW Pet: Phone Quote Email (BPG2) Enhancements | 1031457 | NR | Not Assessed | Quote-email scope supplied; no overall RAG supplied | Not supplied
NW Pet: Portfolio Readiness OTL Reserve | 1032181 | NR | Not Assessed | Reserve item for 2026/2027 readiness; no overall RAG supplied | 12/31/2026
NW Pet: Remove MPPC Utilization Level Capping PA | 1032273 | NR | Not Assessed | PA-specific cap removal scope supplied; no overall RAG supplied | 12/8/2026
NW Pet: Sales Conversion by Channel Reporting Data | 1030930 | NR | Not Assessed | REN/GIN conversion data alignment scope supplied; no overall RAG supplied | 3/31/2027
NW Pet: Unum Cobranding Capabilities for PET | 1032297 | NR | Not Assessed | Embedded/authenticated PET cobranding scope supplied; no overall RAG supplied | Not supplied
Not Assessed = September Planview supplied no overall RAG. NR = Not Reported.

## Slide 9
Health is mixed: Red concentration rose while the source set expanded and many remain unassessed.
48
Total
18
Green
3
Yellow
4
Red
5
Completed
18
Not Assessed
RAG DISTRIBUTION
Chart: 
| Green | Yellow | Red | Completed | Not Assessed
RAG | 18 | 3 | 4 | 5 | 18
MONTH-OVER-MONTH MOVEMENT
Improved: 4 Declined: 5 Unchanged: 13
New / not previously reportable: 26
Comparable RAG movements vs. the August reference; New includes projects newly present in September Planview, lifecycle-only Completed, and Not Assessed rows without an August RAG.
EMERGING RISKS
PEC — Green→Yellow (QA environment reset / E2E).
Underwriting Question Optimization — Green→Red.
Yellow→Red: PPT Program, FirstVet, PPT Payroll.
RED ITEMS
PPT Program
FirstVet Consultation File API
PPT Payroll Billing Employer Experience
Underwriting Question Optimization for MPI
TOP YELLOW DELIVERY RISKS
PEC QA environment reset / E2E.
TaiLWIND dependent-team timing and DDIT completion.
NJ MPPC reporting work outstanding.
RECENT SUCCESSES
Add-A-Pet implementation.
PET Enhancement MVP3 and warranty.
REN2GIN SOW / discovery.
MM-to-MM SOW / discovery.
LEADERSHIP WATCHLIST
PPT Program funding / recovery.
PPT Payroll UAT and resource coverage.
FirstVet budget / vendor integration.
Underwriting $150K funding and sequencing.
PEC environment reset; TaiLWIND cross-team commitments.
FINANCIALS IN FOCUS
Not supplied in September Planview detail records; no financial calculations were modified or recalculated.

## Slide 10
NW Pet – PPT Program
Work ID 1014117
OVERALL RAG · MONTH OVER MONTH
PREVIOUS
SEPTEMBER
Yellow
Red
DESCRIPTION
Modernize Pet backend systems by replacing REN and other legacy systems with the GIN platform.
RAG ASSESSMENT
Critical risk impacting delivery. Immediate mitigation and leadership support required. Employer Portal Bundle 4 testing delays are impacting Bundle 5 and the overall delivery schedule. Source notes an Employer Portal go-live milestone of 11/11/2026 and an additional $4M 2027 funding request.
CHANGES / RISKS / ISSUES
Bundle 4 testing delays.
Bundle 5/6 schedule and Finance integration timing remain exposed.
2027 funding / extended REN cost risk noted in source.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Date
Planning | Completed | 
DDIT | In Progress | 
E2E | In Progress | 
Business UAT | Upcoming | 
Implementation Plan Review | Upcoming | 
Go/No-Go | Upcoming | 
Stage | Upcoming | 
Implementation | Upcoming | 11/11/2026
FINANCIALS (AS SUPPLIED BY SOURCE)
Approved Budget | Not supplied
Actuals | Not supplied
Forecast | Not supplied
Variance | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated.
BUSINESS VALUE / BENEFIT
Modernized policy administration platform and reduced legacy dependency.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Employer Portal MVP moved to 11/11/2026.
Payroll Billing Defects Wave 1 (8 defects) deployed to production.
MM-to-MM capability initiated and vendor SOW process underway.
LEADERSHIP CONTACTS
Delivery Leader Dadgar, Ali Business Lead Not provided in source
TARGET / DELIVERY & % COMPLETE
Target delivery 4/10/2035
85%

## Slide 11
NW Pet: FirstVet Consultation File API
Work ID 1031012
OVERALL RAG · MONTH OVER MONTH
PREVIOUS
SEPTEMBER
Yellow
Red
DESCRIPTION
Configure a secure API integration to retrieve FirstVet consultation data and load it into downstream systems.
RAG ASSESSMENT
Critical risk impacting delivery. Immediate mitigation and leadership support required. Requirements are reviewed and finalized; build approach and core team are defined. Source notes an additional $16.5K budget request pending BDE approval and vendor integration / transfer-file milestones.
CHANGES / RISKS / ISSUES
Additional $16.5K budget pending BDE approval.
Vendor integration testing / access readiness.
Compressed release readiness around 10/12/2026 milestone dates.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Date
Planning | Completed | 
DDIT | In Progress | 
E2E | Upcoming | 
Business UAT | Upcoming | 
Implementation Plan Review | Upcoming | 
Go/No-Go | Upcoming | 
Stage | Upcoming | 
Implementation | Upcoming | 10/12/2026
FINANCIALS (AS SUPPLIED BY SOURCE)
Approved Budget | Not supplied
Actuals | Not supplied
Forecast | Not supplied
Variance | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated.
BUSINESS VALUE / BENEFIT
Automated consultation-data ingestion with less manual handling and improved downstream availability.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Requirements and epics reviewed.
Build approach defined and core team staffed.
Vendor data mapping and access planning progressed.
LEADERSHIP CONTACTS
Delivery Leader Kothandaraman, Rekha Business Lead Not provided in source
TARGET / DELIVERY & % COMPLETE
Target delivery 10/30/2026
49%

## Slide 12
NW Pet: PPT Payroll Billing Employer Experience
Work ID 1029802
OVERALL RAG · MONTH OVER MONTH
PREVIOUS
SEPTEMBER
Yellow
Red
DESCRIPTION
Deliver employer onboarding and payroll-billing financial-operations integration, including AR posting, GL posting, and reconciliation reporting.
RAG ASSESSMENT
Critical risk impacting delivery. Immediate mitigation and leadership support required. Source states the program is 1.5 weeks behind planned UAT start, remaining PDX development/testing and UAT dates are not confirmed, and the October 9 target is under review.
CHANGES / RISKS / ISSUES
IAM registration/authentication issue affected validation.
Finance testing had open blockers around test data and invoice/payment creation.
QE/resource capacity and UAT recovery dates require leadership attention.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Date
Planning | Completed | 
DDIT | In Progress | 
E2E | In Progress | 
Business UAT | Upcoming | 
Implementation Plan Review | Upcoming | 
Go/No-Go | Upcoming | 
Stage | Upcoming | 10/14/2026
Implementation | Upcoming | 11/11/2026
FINANCIALS (AS SUPPLIED BY SOURCE)
Approved Budget | Not supplied
Actuals | Not supplied
Forecast | Not supplied
Variance | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated.
BUSINESS VALUE / BENEFIT
Improved employer onboarding and financial-operational accuracy.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Bundles 1–4 marked Completed in the source milestone list.
IAM issue mitigation complete and testing resumed.
Core Finance scenarios prioritized for Cycle 2.
LEADERSHIP CONTACTS
Delivery Leader Dadgar, Ali Business Lead Not provided in source
TARGET / DELIVERY & % COMPLETE
Target delivery 6/30/2027
49%

## Slide 13
NW Pet: Underwriting Question Optimization for MPI
Work ID 1030240
OVERALL RAG · MONTH OVER MONTH
PREVIOUS
SEPTEMBER
Green
Red
DESCRIPTION
Reduce the number of MPI application questions while preserving response data, metadata, and traceability across binding channels.
RAG ASSESSMENT
Critical risk impacting delivery. Immediate mitigation and leadership support required. September Planview history shows Red. Source describes MVP1/MVP2/MVP3 execution, remaining DDIT and cross-team sequencing, and a $150K 2027 funding approval item.
CHANGES / RISKS / ISSUES
MVP1 change request to remove one question.
MVP2/MVP3 DDIT and sequencing across impacted lines.
Additional $150K 2027 funding approval item.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Date
Planning | Completed | 
DDIT | In Progress | 
E2E | Upcoming | 
Business UAT | Upcoming | 
Implementation Plan Review | Upcoming | 
Go/No-Go | Upcoming | 
Stage | Upcoming | 
Implementation | Upcoming | 2/10/2027
FINANCIALS (AS SUPPLIED BY SOURCE)
Approved Budget | Not supplied
Actuals | Not supplied
Forecast | Not supplied
Variance | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated.
BUSINESS VALUE / BENEFIT
Lower customer question burden with preserved auditability and cross-channel consistency.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Steering Committee approved the change request to remove one business question.
Mockups received for E2E/business validation.
MVP2 go-live risk assessment and target-date review completed.
LEADERSHIP CONTACTS
Delivery Leader Lawson, Lalitha Business Lead Not provided in source
TARGET / DELIVERY & % COMPLETE
Target delivery 4/30/2027
57%

## Slide 14
NW Pet: NJ MPPC New Product and Rate Capping
Work ID 1029148
OVERALL RAG · MONTH OVER MONTH
PREVIOUS
SEPTEMBER
Yellow
Yellow
DESCRIPTION
Turn on New Jersey new business and cap migrated-policy renewal increases for up to four renewals.
RAG ASSESSMENT
At risk. Key dependency, schedule, funding, or resource concerns require monitoring. Source assessment is “Outstanding Reporting work”; the work description specifies a 19.9% cap, extensibility, auditability, reporting, and customer-service visibility.
CHANGES / RISKS / ISSUES
Reporting work remains outstanding.
Target/release milestone dates are open in source.
No additional CRID detail supplied.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Date
Planning | Completed | 
DDIT | In Progress | 
E2E | Upcoming | 
Business UAT | Upcoming | 
Implementation Plan Review | Upcoming | 
Go/No-Go | Upcoming | 
Stage | Upcoming | 
Implementation | Upcoming | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Approved Budget | Not supplied
Actuals | Not supplied
Forecast | Not supplied
Variance | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated.
BUSINESS VALUE / BENEFIT
State-compliant rate capping with auditability and customer-service visibility.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Not supplied in source.
LEADERSHIP CONTACTS
Delivery Leader Kulkarni, Shilpa Sachin Business Lead Not provided in source
TARGET / DELIVERY & % COMPLETE
Target delivery 10/12/2026
69%

## Slide 15
NW Pet: PEC Product and Underwriting Enhancements
Work ID 1029313
OVERALL RAG · MONTH OVER MONTH
PREVIOUS
SEPTEMBER
Green
Yellow
DESCRIPTION
Prevent invalid PEC/coverage combinations and enable compliant mid-term correction of impacted coverage.
RAG ASSESSMENT
At risk. Key dependency, schedule, funding, or resource concerns require monitoring. PEC-to-Coverage QA Validation is on hold until 9/30 because of an environment data reset; E2E scheduled for 10/1 is at risk.
CHANGES / RISKS / ISSUES
Environment reset blocks QA validation.
E2E date may need to move.
UAT and downstream release timing need recovery assessment.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Date
Planning | Completed | 
DDIT | In Progress | 
E2E | Upcoming | 
Business UAT | Upcoming | 
Implementation Plan Review | Upcoming | 
Go/No-Go | Upcoming | 
Stage | Upcoming | 
Implementation | Upcoming | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Approved Budget | Not supplied
Actuals | Not supplied
Forecast | Not supplied
Variance | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated.
BUSINESS VALUE / BENEFIT
Reduces customer harm, complaints, and regulatory risk from invalid coverage combinations.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
DDIT (SS) completed.
Funding approved milestone completed.
Path-to-green actions documented in the source.
LEADERSHIP CONTACTS
Delivery Leader Barbour, Kinney L. Business Lead Not provided in source
TARGET / DELIVERY & % COMPLETE
Target delivery 1/29/2027
45%

## Slide 16
NW Pet: TaiLWIND Phase 1 (Claims AI)
Work ID 1029859
OVERALL RAG · MONTH OVER MONTH
PREVIOUS
SEPTEMBER
Yellow
Yellow
DESCRIPTION
Pilot AI-enabled claims intake and document transformation across Pet claims workflows.
RAG ASSESSMENT
At risk. Key dependency, schedule, funding, or resource concerns require monitoring. September source cites timing risk across REN, GIN, MIM, DMX, Portal, GOP, and Doodle Poodle dependencies; DDIT was not complete for all aspects by 10/1 and phased testing is being used.
CHANGES / RISKS / ISSUES
Cross-team dependency timing.
DDIT completion / phased testing.
Doodle Poodle processing service timing and access/token-management friction.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Date
Planning | In Progress | 
DDIT | In Progress | 
E2E | In Progress | 
Business UAT | Upcoming | 
Implementation Plan Review | Upcoming | 
Go/No-Go | Upcoming | 
Stage | Upcoming | 
Implementation | Upcoming | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Approved Budget | Not supplied
Actuals | Not supplied
Forecast | Not supplied
Variance | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated.
BUSINESS VALUE / BENEFIT
Reduces manual claims intake and establishes a path toward scalable claims automation.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Document Transformation Service production dark launch.
E2E test strategy finalized and planning underway.
9/18 extraction and metrics demonstration completed with stakeholder questions captured.
LEADERSHIP CONTACTS
Delivery Leader Kulkarni, Shilpa Sachin Business Lead Not provided in source
TARGET / DELIVERY & % COMPLETE
Target delivery 9/30/2027
51%

## Slide 17
Source hierarchy and reporting conventions keep the September view factual and auditable.
SOURCE REFERENCES
September Planview source (authoritative current values)
https://nationwide-be.glean.com/api/v1/downloadchatfile/4a6d42aa59af4cfb915a23d20ee9a127
August monthly deck (prior-month RAG and structure)
https://nationwide-be.glean.com/api/v1/downloadchatfile/7de8e6a82b7645d991dd40b812ae04bd
October 12 weekly update (supplemental context only)
https://nationwide-be.glean.com/api/v1/downloadchatfile/bd397ec5813a4a798ef2bf594df7ff54
Nationwide branding template
https://nationwide-be.glean.com/api/v1/downloadchatfile/6e51c3eb3505444c8de9c5104855bfdc
Pet Build rocket logo
https://nationwide-be.glean.com/api/v1/downloadchatfile/85e0dcfcf8c34d26855c580f0365b378
REPORTING ASSUMPTIONS
September 2026 reporting month; snapshot date 9/30/2026.
Prior month = August 2026 current RAG from the August monthly deck.
NR = Not Reported where no August source value exists.
Not Assessed = September Planview supplied no overall RAG.
RAG DEFINITIONS
Green — On track. Major milestones progressing as planned.
Yellow — At risk. Key dependency, schedule, funding, or resource concerns require monitoring.
Red — Critical risk impacting delivery. Immediate mitigation and leadership support required.
Completed — Delivery completed successfully.
Not Assessed — Status unavailable, planning-only, or data insufficient (supported source reasons only).
MILESTONE LEGEND & DATA QUALITY
Milestone statuses: Completed, In Progress, Upcoming. Dates appear only when supplied; none invented.
48 projects represented; all appear in the RAG snapshot; seven Red/Yellow projects have detail slides.
Blank values remain blank; TBD remains TBD; financial values are not recalculated.
September detail records for the seven Red/Yellow projects report no financial data → Not supplied.
October 12 weekly context does not override September Planview values.
This report reflects portfolio status as of 9/30/2026. Source fields are reported as supplied. Blank values remain blank. TBD values remain TBD. Financial calculations are not modified or recalculated. · Nationwide internal use only.