## Slide 1
NATIONWIDE PET
Monthly Build
Portfolio Report
August 2026
Latest source snapshot: 8/31/2026
This August monthly report reflects the 8/31/2026 business status. Source fields are reported as supplied — blanks remain blank, TBD remains TBD, and financials are not recalculated.

## Slide 2
Portfolio RAG Snapshot — Red, Yellow & Green (1 of 3)
August 2026 report · status as of 8/31/2026
Red
Yellow
Green
Completed
Not assessed
Project | Current RAG | Key driver | Target delivery
Add-A-Pet Improvements | Red | Two showstopper defects; remediation, testing & business approval | 9/9/2026
MPPC UW Questions Reduction MVP3 / Find a Vet | Red | Stage & Implementation dependent on Add-A-Pet | 9/9/2026
EDO: Talend Run | Red | Aurora write-access restriction (last: 7/31/2026) | Per 7/31/2026 source
Employer Portal / Payroll Billing | Yellow | Bundle 5/6 scope, defects, E2E readiness, no schedule contingency | 11/11/2026
FirstVet Consultation File API | Yellow | ImageRight/MIM CR & funding/prioritization dependency | 9/14/2026
Portal Stabilization | Yellow | Additional Q4 funding; CR scope/estimate by 9/4 | 10/31/2026
GIN / Batch Stabilization | Yellow | ECIF Data Integrity & GIN stability funding/CR | Oct 2026
GIN Long-Term Stability — Scalability to 1.5–2M Policies | Yellow | QE lead gap | TBD
GIN API V2 to V5 Upgrade | Yellow | Phased delivery & resource onboarding; risk date 9/4 | Risk date 9/4/2026
TaiLWIND Flagship AI / Claims AI Phase 1 | Yellow | Capacity, KPIs, integrations, production ownership alignment | 11/11/2026
PPT Program | Yellow | Employer Portal / 2027 funding (last: 7/31/2026) | Per 7/31/2026 source
NJ MPPC New Product and Rate Capping | Yellow | Talend→Python dependency (last: 7/31/2026) | 7/27/2026 (per source)
PPT – REN2GIN Policy Migration | Green | SOW finalized 8/28; schedule/cost alignment 9/30 | 9/30/2026 alignment
PPT – Major Medical – New Business on GIN | Green | MiM capacity commitment (second developer) | 2/10/2027
Major Medical-to-Major-Medical Migration (Non-CA) | Green | ITS SOW finalized; schedule aligned to March 2027 | March 2027

## Slide 3
Portfolio RAG Snapshot — Green (2 of 3)
August 2026 report · status as of 8/31/2026
Red
Yellow
Green
Completed
Not assessed
Project | Current RAG | Key driver | Target delivery
NY and Unapproved States Product Build | Green | Cognizant draft SOW expected 9/11 | SOW 9/11/2026
MPI Underwriting Optimization MVP1 | Green | CR to remove one business question approved | 10/14/2026
MPI Underwriting Optimization MVP2 | Green | SteerCo approved 11/11 go-live (8/27) | 11/11/2026
MPI Underwriting Optimization MVP3 | Green | $150K 2027 funding remains an approval item | February 2027
MPPC to MPI Conversion at Notice of Cancel | Green | Dec 9 achievable; options being evaluated | 12/9/2026
PEC Product & Underwriting Enhancements | Green | DDIT continuing | 11/11/2026
Enhance Multi Denial Code Claims Z160/Z151 | Green | MPPC/MPI and ETL DDIT in progress | 11/11/2026
MPI Pricing Segmentation Sophistication | Green | R9 on schedule; R10 scope frozen | 9/16/2026 (R9)
Pet Model Law Reboot | Green | Wave 3 implemented 8/12; Wave 4 in November | 9/16/2026 (REN CR forms)
Payroll Billing Defect Fixes / Talend-to-Python Waves | Green | Wave 2 sign-off 8/17; production deployment 8/19 | 11/12/2026 (Wave 5)
Refresh the Windows 2022 Server | Green | Phased server upgrade; remaining teams in September | 9/30/2026
Enhancement for Commission Reporting — Internal Batch | Green | Kickoff 8/26; BO→Power BI, Oracle→Snowflake | 9/30/2026
2026 GIN Updates | Green | Requirements/scope/line schedule finalizing | 9/30/2026
CPP Right to Delete & Right to Access (Externally Funded) | Green | Technical design & line estimates pending | 9/30/2026
Vulnerabilities Remediation | Green | Cloud-run stabilization dependency | 8/31/2026 (past-due closure)

## Slide 4
Portfolio RAG Snapshot — Green, Completed & Not-Assessed (3 of 3)
August 2026 report · status as of 8/31/2026
Red
Yellow
Green
Completed
Not assessed
Project | Current RAG | Key driver | Target delivery
Legacy Talend to Python Migration | Green | Latest available source: 7/20/2026 | Per 7/20/2026 source
2026 Product Rate Refresh | Green | On track (last: 7/31/2026) | Per 7/31/2026 source
Hawaii Territory Factor Change | Green | Table update pending (last: 7/31/2026) | 8/31/2026 (per source)
Maryland MPPC Approval | Green | State readiness (last: 7/31/2026) | 8/31/2026 (per source)
P.E.T. Exchange Encryption Upgrade | Green | Security posture (last: 7/31/2026) | 7/27/2026 (per source)
PA WP to MPI Rate Capping and Letter | Green | PA cap logic & letter (last: 7/31/2026) | 9/11/2026 (per source)
QEC A/B Testing & Tool Enhancements | Green | Funnel optimization (last: 7/31/2026) | 11/30/2026 (per source)
Pet Paperless eDelivery | Completed | Core release + MMP2 warranty complete | Dashboard 8/28/2026
Data Center Production Migration | Completed | Cutover 7/24; Dallas & Irvine retired | Complete
Non-Insurance Bundle v1 | Completed | Production release complete | Complete
Update Legacy Portal Interface to UAv3 | Completed | 8/5 deployment validated; sign-offs received | Warranty through 9/5/2026
GW Cloud Platform Migration | Completed | Migration complete (retained baseline) | Complete
WA MPI 5% Affinity Discount Removal | Not assessed | Not assessed (last: 7/31/2026) | 9/30/2026 (per source)

## Slide 5
Portfolio Health at a Glance
August 2026 report · status as of 8/31/2026
43 projects tracked · 1 not assessed
25
Green — on track
9
Yellow — at risk
3
Red — escalated
5
Completed
Chart: RAG Distribution (8/31/2026)
| Green | Yellow | Red | Completed | Not assessed
RAG mix | 25 | 9 | 3 | 5 | 1
CURRENT RAG HIGHLIGHTS
Red Add-A-Pet Improvements and MPPC UW MVP3 / Find a Vet — both targeting 9/9 At risk Employer Portal / Payroll Billing — Bundle 5/6 scope, E2E Red, no schedule contingency Not assessed WA MPI 5% Affinity Discount Removal — early planning underway
AUGUST DELIVERY SPOTLIGHT
Payroll Billing Wave 2 signed off (8/17) and deployed to production (8/19)
Data Center Production Migration complete — cutover 7/24; Dallas & Irvine retired
Non-Insurance Bundle v1 live; Legacy Portal UAv3 deployed & validated (8/5)
REN2GIN SOW finalized (8/28); MPPC UW MVP3 UAT signed off
LEADERSHIP WATCHPOINTS
Q4 funding / CR decisions pending on Portal Stabilization and GIN/Batch Stabilization
GIN API V2→V5 needs phased delivery and resource onboarding; risk date 9/4
TaiLWIND needs cross-team capacity, KPI, and production-ownership alignment

## Slide 6
Leadership Focus — Decisions & Escalations
August 2026 report · status as of 8/31/2026
Employer Portal — Yellow, at risk
Bundle 5/6 scope, open defects, E2E readiness, and schedule contingency remain unresolved. Dark launch 10/21 and go-live 11/11 have no remaining schedule buffer.
Portal Stability & GIN / Batch Stabilization
Both require Q4 funding and CR decisions — Portal CR scope/estimate requested by 9/4; GIN/Batch needs funding for ECIF Data Integrity and GIN stability.
GIN API V2→V5 Upgrade
Needs a phased-delivery plan and resource onboarding (QE/developers). Integrated E2E planning is required; project-plan risk date is 9/4.
TaiLWIND Flagship AI / Claims AI Phase 1
Needs cross-team capacity, operational KPI definition, and production-ownership alignment to commit future delivery timing.

## Slide 7
NW Pet: Add-A-Pet Improvements
Work ID 1029314
OVERALL RAG · 8/31/2026
Red
DESCRIPTION
Improve the member experience by showing relevant products and eligibility information during Add-A-Pet.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Red — 86% execution complete. Two showstopper defects plus an additional logical change remain; E2E runs through 9/1 and UAT through 9/2. Next potential deployment is 9/9, contingent on remediation, testing, and business approval.
CHANGES / RISKS / ISSUES (CRID)
Two showstopper defects plus an additional logical change under active remediation; deployment gated on completed testing and business sign-off.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ✓ Done |  | 
E2E | ◐ In-progress |  | 9/1
Business UAT / Sign-off | ◐ In-progress |  | 9/2
Implementation Plan Review | ◯ Upcoming |  | 
Go / No-Go | ◯ Upcoming |  | 
Stage | ◯ Upcoming |  | 
Implementation | ◯ Upcoming | 9/9 | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | $356,440
YTD Actuals | $233,740.40
Remaining Forecast | $122,700
Year-End Forecast | $356,440
Variance / Delta | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Personalized member experience and stronger eligibility-driven conversion.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Prior E2E blockers and environment issues resolved
Testing restored to full execution
Business-flow validation advanced
DELIVERY LEADER (DL)
Rekha Kothandaraman
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Nidia Gudino
TARGET / DELIVERY DATES & % COMPLETE
Target delivery 9/9/2026
86%

## Slide 8
NW Pet: MPPC UW Questions Reduction MVP3 / Find a Vet
Work ID 1030950
OVERALL RAG · 8/31/2026
Red
DESCRIPTION
Reduce MPPC underwriting questions and deliver Find a Vet provider-information enhancements.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Red — target 9/9. E2E and UAT are complete and UAT is signed off. Governance approval to move the question-removal CR toward February 2027 completed 8/31. Stage and Implementation remain dependent on Add-A-Pet.
CHANGES / RISKS / ISSUES (CRID)
Question-removal CR governance-approved 8/31 to move toward February 2027. Stage/Implementation dependency on Add-A-Pet remains open.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ✓ Done |  | 
E2E | ✓ Done |  | 
Business UAT / Sign-off | ✓ Done |  | 
Implementation Plan Review | ◐ In-progress |  | 
Go / No-Go | ◯ Upcoming |  | 
Stage | ◯ Upcoming |  | 
Implementation | ◯ Upcoming | 9/9 | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | $341,000
YTD Actuals | $197,033
Remaining Forecast | $146,296
Year-End Forecast | $343,330
Variance / Delta | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
A lighter partner/customer experience with complete provider information and reduced friction.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
DDIT complete for warranty fix TAB-1027
E2E and UAT complete; UAT signed off
Question-removal CR governance-approved 8/31
DELIVERY LEADER (DL)
Kinney Barbour
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Sara Andrews
TARGET / DELIVERY DATES & % COMPLETE
Target delivery 9/9/2026
80%

## Slide 9
NW Pet: Employer Portal / Payroll Billing
Work ID 1029802
OVERALL RAG · 8/31/2026
Yellow
DESCRIPTION
Deliver employer onboarding and payroll-billing financial-operations integration, including AR, GL, and reconciliation.
Cost
Schedule
Scope
RAG ASSESSMENT
Yellow, at risk of turning Red — Bundle 4 and the first dark launch are complete, but Bundle 5/6 scope and priorities are not finalized and E2E is Red. Dark launch is set for 10/21 and go-live for 11/11 with no remaining schedule contingency. Forecast delta is approximately -$196K versus the revised budget.
CHANGES / RISKS / ISSUES (CRID)
Bundle 5/6 scope not finalized; E2E Red; no remaining schedule contingency; forecast delta ~ -$196K vs revised budget.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ✓ Done |  | 
E2E | ◐ In-progress |  | 
Business UAT / Sign-off | ◯ Upcoming |  | 
Implementation Plan Review | ◯ Upcoming |  | 
Go / No-Go | ◯ Upcoming |  | 
Stage | ◯ Upcoming |  | 10/21
Implementation | ◯ Upcoming | 11/11 | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | $4,050,000 (revised)
YTD Actuals | $1,809,495
Remaining Forecast | $2,044,359.81
Year-End Forecast | $3,853,855
Variance / Delta | approx. -$196K vs revised budget
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Improved employer onboarding and financial-operational accuracy.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Bundle 4 complete
First dark launch complete
DELIVERY LEADER (DL)
Ali Dadgar
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Victor Nas
TARGET / DELIVERY DATES & % COMPLETE
Dark launch 10/21/2026 · go-live 11/11/2026
60%

## Slide 10
NW Pet: FirstVet Consultation File API
Work ID 1031012
OVERALL RAG · 8/31/2026
Yellow
DESCRIPTION
Configure a secure API integration to retrieve FirstVet consultation data and load it into downstream systems.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Yellow — the API release is deployed and functional testing is complete with no application defects. The ImageRight/MIM CR and its funding/prioritization remain dependencies. Transfer-file target is 9/14.
CHANGES / RISKS / ISSUES (CRID)
ImageRight/MIM CR and funding/prioritization remain open dependencies.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ✓ Done |  | 
E2E | ✓ Done |  | 
Business UAT / Sign-off | ✓ Done |  | 
Implementation Plan Review | ◯ Upcoming |  | 
Go / No-Go | ◯ Upcoming |  | 
Stage | ◐ In-progress |  | 
Implementation | ◯ Upcoming |  | 9/14
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | $69,100
YTD Actuals | $32,330
Remaining Forecast | $53,268
Year-End Forecast | $74,000
Variance / Delta | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Automated consultation-data ingestion with less manual handling and improved data availability.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
MIM ImageRight import development
Authentication fix and deployment
Functional testing complete (no defects)
Cross-functional alignment
DELIVERY LEADER (DL)
Rekha Kothandaraman
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Kelly Heitmann
TARGET / DELIVERY DATES & % COMPLETE
Transfer-file target 9/14/2026
70%

## Slide 11
NW Pet: Portal Stabilization
Work ID 1029256
OVERALL RAG · 8/31/2026
Yellow
DESCRIPTION
Resolve portal reliability, login/access, payments, enrollment, and billing issues for migrated policies.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Yellow — additional Q4 funding is required and a CR scope/estimate was requested by 9/4. The Angular upgrade moved to 9/9; login/access reliability is delivered; Apigee/API and redundant-call releases are planned 9/16; payments/enrollment/billing target 10/31.
CHANGES / RISKS / ISSUES (CRID)
Additional Q4 funding required; CR scope/estimate requested by 9/4.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ◐ In-progress |  | 
E2E | ◯ Upcoming |  | 
Business UAT / Sign-off | ◯ Upcoming |  | 
Implementation Plan Review | ◯ Upcoming |  | 
Go / No-Go | ◯ Upcoming |  | 
Stage | ◯ Upcoming |  | 
Implementation | ◯ Upcoming |  | 10/31
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | $75,000
YTD Actuals | $32,221
Remaining Forecast | $78,142
Year-End Forecast | $112,056
Variance / Delta | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Improves member experience and reduces migrated-policy support incidents.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Login/access reliability delivered
Angular upgrade rescheduled to 9/9
Apigee/API & redundant-call releases planned 9/16
DELIVERY LEADER (DL)
Dinesh
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Nidia Gudino
TARGET / DELIVERY DATES & % COMPLETE
Payments/enrollment/billing target 10/31/2026
45%

## Slide 12
NW Pet: GIN / Batch Stabilization
Work ID 1031470
OVERALL RAG · 8/31/2026
Yellow
DESCRIPTION
Stabilize GIN/ECIF data integrity and critical batch jobs to reduce member-visible errors and support growth.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Yellow — additional funding/CR is needed for ECIF Data Integrity and GIN stability. ECIF/ECN fixes deployed 8/12 and estimates were received 8/21. Task-error remediation is planned 9/15, a phased-delivery proposal is under review, and the CEM-to-Java Golden Path is targeted for October.
CHANGES / RISKS / ISSUES (CRID)
Additional funding/CR needed for ECIF Data Integrity and GIN stability; phased-delivery proposal under review.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ◐ In-progress |  | 9/15
E2E | ◯ Upcoming |  | 
Business UAT / Sign-off | ◯ Upcoming |  | 
Implementation Plan Review | ◯ Upcoming |  | 
Go / No-Go | ◯ Upcoming |  | 
Stage | ◯ Upcoming |  | 
Implementation | ◯ Upcoming |  | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | $425,000
YTD Actuals | $243,318
Remaining Forecast | $386,168
Year-End Forecast | $663,871
Variance / Delta | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Fewer member-visible errors, more reliable documents/remittances, and scalable operations.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
ECIF/ECN fixes deployed 8/12
Estimates received 8/21
Task-error remediation planned 9/15
DELIVERY LEADER (DL)
Dinesh
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Gary Wilson
TARGET / DELIVERY DATES & % COMPLETE
CEM-to-Java Golden Path targeted October 2026
35%

## Slide 13
NW Pet: GIN Long-Term Stability — Scalability to 1.5–2M Policies
Work ID — (not in source)
OVERALL RAG · 8/31/2026
Yellow
DESCRIPTION
Scale GIN to support 1.5–2M policies through Snowflake and phased GIN platform work.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Yellow — discovery is complete and the solution-approach/project-plan review is complete with feedback. Snowflake and GIN phase work is underway. A QE lead gap is noted.
CHANGES / RISKS / ISSUES (CRID)
QE lead resource gap noted.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ◐ In-progress |  | 
E2E | ◯ Upcoming |  | 
Business UAT / Sign-off | ◯ Upcoming |  | 
Implementation Plan Review | ◯ Upcoming |  | 
Go / No-Go | ◯ Upcoming |  | 
Stage | ◯ Upcoming |  | 
Implementation | ◯ Upcoming |  | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | $463,000 (approved funding)
YTD Actuals | Not supplied
Remaining Forecast | Not supplied
Year-End Forecast | Not supplied
Variance / Delta | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Platform scalability to support long-term policy growth.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Discovery complete
Solution-approach / project-plan review complete with feedback
Snowflake and GIN phase work underway
DELIVERY LEADER (DL)
Dinesh
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Gary Wilson
TARGET / DELIVERY DATES & % COMPLETE
Target not supplied in source
20%

## Slide 14
NW Pet: GIN API V2 to V5 Upgrade
Work ID — (not in source)
OVERALL RAG · 8/31/2026
Yellow
DESCRIPTION
Migrate customer-facing Accounts, Claims, and Members APIs from V2 SOAP/RPC to V5 REST.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Yellow — the project plan is in progress and core resources are identified. QE/developer onboarding is underway. Phased delivery and integrated E2E planning are required; the risk date is 9/4.
CHANGES / RISKS / ISSUES (CRID)
Phased delivery and integrated E2E planning required; project-plan risk date 9/4.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ◐ In-progress |  | 
DDIT | ◯ Upcoming |  | 
E2E | ◯ Upcoming |  | 
Business UAT / Sign-off | ◯ Upcoming |  | 
Implementation Plan Review | ◯ Upcoming |  | 
Go / No-Go | ◯ Upcoming |  | 
Stage | ◯ Upcoming |  | 
Implementation | ◯ Upcoming |  | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | $350,000
YTD Actuals | Not supplied
Remaining Forecast | Not supplied
Year-End Forecast | $349,839.29 (forecast)
Variance / Delta | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Modernized customer-facing APIs on V5 REST with reduced legacy dependency.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Project plan in progress
Core resources identified
QE/developer onboarding underway
DELIVERY LEADER (DL)
Dinesh
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Gary Wilson
TARGET / DELIVERY DATES & % COMPLETE
Project-plan risk date 9/4/2026
15%

## Slide 15
NW Pet: TaiLWIND Flagship AI / Claims AI Phase 1
Work ID 1029859
OVERALL RAG · 8/31/2026
Yellow
DESCRIPTION
Pilot AI-enabled claims intake (email, document submission) and downstream mapping for claims processing.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Yellow — Email Ingestion is 70% complete and Document Submission release 1 is underway. PDFBox replaced a licensing risk and benchmark/ground-truth work advanced. Drivers are capacity, operational KPIs, integrations, and production-ownership alignment. Next show-and-tell is 9/18.
CHANGES / RISKS / ISSUES (CRID)
Open drivers: cross-team capacity, operational KPIs, integrations, and production-ownership alignment.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ◐ In-progress |  | 
E2E | ◯ Upcoming |  | 
Business UAT / Sign-off | ◯ Upcoming |  | 
Implementation Plan Review | ◯ Upcoming |  | 
Go / No-Go | ◯ Upcoming |  | 
Stage | ◯ Upcoming |  | 
Implementation | ◯ Upcoming | 11/11 | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | $1,500,000
YTD Actuals | $666,489
Remaining Forecast | $859,818
Year-End Forecast | $1,526,307
Variance / Delta | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Reduces manual claims intake and creates a flexible path to agentic automation.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Email Ingestion 70% complete
Document Submission release 1 underway
PDFBox replaced licensing risk
Benchmark/ground-truth advanced
DELIVERY LEADER (DL)
Shilpa K
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Dan Clausing
TARGET / DELIVERY DATES & % COMPLETE
Target 11/11/2026 · next show-and-tell 9/18
55%

## Slide 16
NW Pet – PPT – REN2GIN Policy Migration
Work ID 1014865
OVERALL RAG · 8/31/2026
Green
DESCRIPTION
Migrate policies from REN to GIN across planned migration waves.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Green — SOW finalized 8/28. Latest migration: MM→MPI 99.7%, MPP→MPPC 87.2%, WP→MPI 72.4%, total 87.3%. Schedule/cost alignment is targeted for 9/30.
CHANGES / RISKS / ISSUES (CRID)
No escalated CRIDs reported; schedule/cost alignment pending 9/30.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ✓ Done |  | 
E2E | ✓ Done |  | 
Business UAT / Sign-off | ✓ Done |  | 
Implementation Plan Review | ◐ In-progress |  | 9/30
Go / No-Go | ◯ Upcoming |  | 
Stage | ◯ Upcoming |  | 
Implementation | ◐ In-progress |  | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | $800,000
YTD Actuals | $436,842
Remaining Forecast | $407,037
Year-End Forecast | $843,880
Variance / Delta | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Moves policy administration to the modern GIN platform and reduces legacy dependency.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
SOW finalized 8/28
Migration advanced: total 87.3% (MM→MPI 99.7%, MPP→MPPC 87.2%, WP→MPI 72.4%)
DELIVERY LEADER (DL)
Shilpa K
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Gary Wilson
TARGET / DELIVERY DATES & % COMPLETE
Schedule/cost alignment 9/30/2026
87%

## Slide 17
NW Pet – PPT – Major Medical – New Business on GIN
Work ID 1014368
OVERALL RAG · 8/31/2026
Green
DESCRIPTION
Configure Major Medical product functionality for new business on GIN.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Green — confirmed following a MiM commitment based on second-developer availability. Refinement and DDIT are underway; target is 2/10/2027.
CHANGES / RISKS / ISSUES (CRID)
No escalated CRIDs reported; delivery contingent on committed MiM capacity.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ◐ In-progress |  | 
E2E | ◯ Upcoming |  | 
Business UAT / Sign-off | ◯ Upcoming |  | 
Implementation Plan Review | ◯ Upcoming |  | 
Go / No-Go | ◯ Upcoming |  | 
Stage | ◯ Upcoming |  | 
Implementation | ◯ Upcoming | 2/10/27 | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | $840,000
YTD Actuals | $117,650
Remaining Forecast | $761,646
Year-End Forecast | $879,296
Variance / Delta | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Enables Major Medical new-business capability on GIN.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
MiM capacity commitment secured (second developer)
Refinement and DDIT underway
DELIVERY LEADER (DL)
Shilpa K
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Gary W.
TARGET / DELIVERY DATES & % COMPLETE
Target 2/10/2027
30%

## Slide 18
NW Pet: Major Medical-to-Major-Medical Migration (Non-CA)
Work ID — (not in source)
OVERALL RAG · 8/31/2026
Green
DESCRIPTION
Build Major Medical-to-Major-Medical migration capability for non-California states.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Green — the ITS SOW is finalized and the schedule is aligned to March 2027. Discovery kickoff is next.
CHANGES / RISKS / ISSUES (CRID)
No escalated CRIDs reported.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ◐ In-progress |  | 
DDIT | ◯ Upcoming |  | 
E2E | ◯ Upcoming |  | 
Business UAT / Sign-off | ◯ Upcoming |  | 
Implementation Plan Review | ◯ Upcoming |  | 
Go / No-Go | ◯ Upcoming |  | 
Stage | ◯ Upcoming |  | 
Implementation | ◯ Upcoming |  | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | $250,000 (working)
YTD Actuals | Not supplied
Remaining Forecast | Not supplied
Year-End Forecast | Not supplied
Variance / Delta | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Enables Major Medical policy migration capability outside California.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
ITS SOW finalized
Schedule aligned to March 2027
Discovery kickoff next
DELIVERY LEADER (DL)
Shilpa
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Gary
TARGET / DELIVERY DATES & % COMPLETE
Schedule aligned to March 2027
5%

## Slide 19
NW Pet: NY and Unapproved States Product Build
Work ID — (not in source)
OVERALL RAG · 8/31/2026
Green
DESCRIPTION
Build product capability for New York and other unapproved states.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Green — an additional $167K in funding was received and intake is submitted. A Cognizant draft SOW is expected 9/11; final SOW and staffing remain open.
CHANGES / RISKS / ISSUES (CRID)
Final SOW and staffing remain open.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ◐ In-progress |  | 
DDIT | ◯ Upcoming |  | 
E2E | ◯ Upcoming |  | 
Business UAT / Sign-off | ◯ Upcoming |  | 
Implementation Plan Review | ◯ Upcoming |  | 
Go / No-Go | ◯ Upcoming |  | 
Stage | ◯ Upcoming |  | 
Implementation | ◯ Upcoming |  | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | $267,000
YTD Actuals | Not supplied
Remaining Forecast | $267,000
Year-End Forecast | $267,000
Variance / Delta | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Expands product availability into New York and additional states.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Additional $167K funding received
Intake submitted
Cognizant draft SOW expected 9/11
DELIVERY LEADER (DL)
Ali (Interim)
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Gary W.
TARGET / DELIVERY DATES & % COMPLETE
Cognizant draft SOW expected 9/11/2026
10%

## Slide 20
NW Pet: MPI Underwriting Optimization MVP1
Work ID 1030240
OVERALL RAG · 8/31/2026
Green
DESCRIPTION
Reduce MPI application questions while preserving response data and traceability (MVP1).
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Green — target 10/14. DDIT ends 9/2; E2E 9/3–9/15; UAT 9/16–10/2; implementation-plan review, Go/No-Go, and Stage 10/3; Implementation 10/14. The CR to remove one business question is approved; $7K was funded through contingency with no budget impact; mockups and risk assessment are complete.
CHANGES / RISKS / ISSUES (CRID)
CR to remove one business question approved; $7K funded through contingency with no budget impact.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ◐ In-progress |  | 9/2
E2E | ◯ Upcoming | 9/3 | 9/15
Business UAT / Sign-off | ◯ Upcoming | 9/16 | 10/2
Implementation Plan Review | ◯ Upcoming | 10/3 | 
Go / No-Go | ◯ Upcoming | 10/3 | 
Stage | ◯ Upcoming | 10/3 | 
Implementation | ◯ Upcoming | 10/14 | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | $1,120,000
YTD Actuals | $191,445
Remaining Forecast | $925,157
Year-End Forecast | $1,116,603
Variance / Delta | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Lighter customer experience and lower question burden with maintained auditability.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
CR to remove one business question approved
Mockups and risk assessment complete
$7K funded via contingency (no budget impact)
DELIVERY LEADER (DL)
Lalitha Kumar
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Sarah Andrews
TARGET / DELIVERY DATES & % COMPLETE
Target 10/14/2026
40%

## Slide 21
NW Pet: MPI Underwriting Optimization MVP2
Work ID — (not in source)
OVERALL RAG · 8/31/2026
Green
DESCRIPTION
Second increment of MPI underwriting-question optimization (MVP2).
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Green — the Steering Committee approved the 11/11 go-live on 8/27. DDIT runs through 9/30; E2E 10/1–10/14; UAT 10/15–10/30; Go/No-Go 11/2; Implementation 11/11. Risk and Open Enrollment assessments are complete.
CHANGES / RISKS / ISSUES (CRID)
No escalated CRIDs reported; Open Enrollment alignment assessed.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ◐ In-progress |  | 9/30
E2E | ◯ Upcoming | 10/1 | 10/14
Business UAT / Sign-off | ◯ Upcoming | 10/15 | 10/30
Implementation Plan Review | ◯ Upcoming |  | 
Go / No-Go | ◯ Upcoming | 11/2 | 
Stage | ◯ Upcoming |  | 
Implementation | ◯ Upcoming | 11/11 | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | $1,120,000 (shared program)
YTD Actuals | $191,445
Remaining Forecast | $925,157
Year-End Forecast | $1,116,603
Variance / Delta | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Continued reduction in application question burden across channels.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Steering Committee approved 11/11 go-live (8/27)
Risk and Open Enrollment assessments complete
DELIVERY LEADER (DL)
Lalitha Kumar
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Sarah Andrews
TARGET / DELIVERY DATES & % COMPLETE
Go-live 11/11/2026 (SteerCo approved 8/27)
30%

## Slide 22
NW Pet: MPI Underwriting Optimization MVP3
Work ID — (not in source)
OVERALL RAG · 8/31/2026
Green
DESCRIPTION
Third increment of MPI underwriting-question optimization (MVP3).
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Green — February 2027 target. DDIT 8/13–12/24; E2E 12/28–1/10/27; UAT 1/11–1/30/27; Go/No-Go 2/2/27; Implementation 2/17/27. $150K of 2027 funding remains an approval item.
CHANGES / RISKS / ISSUES (CRID)
$150K 2027 funding remains an approval item.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ◐ In-progress | 8/13 | 12/24
E2E | ◯ Upcoming | 12/28 | 1/10/27
Business UAT / Sign-off | ◯ Upcoming | 1/11 | 1/30/27
Implementation Plan Review | ◯ Upcoming |  | 
Go / No-Go | ◯ Upcoming | 2/2/27 | 
Stage | ◯ Upcoming |  | 
Implementation | ◯ Upcoming | 2/17/27 | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | Not supplied
YTD Actuals | Not supplied
Remaining Forecast | Not supplied
Year-End Forecast | Not supplied
Variance / Delta | $150K 2027 funding pending approval
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Completes the multi-phase reduction in application question burden.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Milestone plan established through February 2027
DELIVERY LEADER (DL)
Lalitha Kumar
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Sarah Andrews
TARGET / DELIVERY DATES & % COMPLETE
Target February 2027
12%

## Slide 23
NW Pet: MPPC to MPI Conversion at Notice of Cancel
Work ID 1031134
OVERALL RAG · 8/31/2026
Green
DESCRIPTION
Create an automated MPPC→MPI conversion path for payroll-billed customers at Notice of Cancel.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Green — December 9 is technically achievable while January, February, and phased options are evaluated. The simplified design uses existing cancellation reason codes, with no new eligibility flag or RRD indicator; the printed-insert timeline is established.
CHANGES / RISKS / ISSUES (CRID)
No escalated CRIDs reported; delivery timing options (Dec/Jan/Feb/phased) under evaluation.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ◐ In-progress |  | 
E2E | ◯ Upcoming |  | 
Business UAT / Sign-off | ◯ Upcoming |  | 
Implementation Plan Review | ◯ Upcoming |  | 
Go / No-Go | ◯ Upcoming |  | 
Stage | ◯ Upcoming |  | 
Implementation | ◯ Upcoming | 12/9 | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | $880,000
YTD Actuals | $169,884
Remaining Forecast | $707,038
Year-End Forecast | $876,922
Variance / Delta | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Keeps members insured with less friction and reduces manual conversion effort.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Simplified design finalized (existing cancellation reason codes; no new flag/RRD)
Printed-insert timeline established
DELIVERY LEADER (DL)
Lalitha Kumar
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Gary Wilson
TARGET / DELIVERY DATES & % COMPLETE
12/9/2026 technically achievable (options under evaluation)
25%

## Slide 24
NW Pet: PEC Product & Underwriting Enhancements
Work ID 1029313
OVERALL RAG · 8/31/2026
Green
DESCRIPTION
Prevent invalid PEC/coverage combinations and enable compliant mid-term correction.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Green — 50% complete with DDIT continuing; target 11/11.
CHANGES / RISKS / ISSUES (CRID)
No escalated CRIDs reported.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ◐ In-progress |  | 
E2E | ◯ Upcoming |  | 
Business UAT / Sign-off | ◯ Upcoming |  | 
Implementation Plan Review | ◯ Upcoming |  | 
Go / No-Go | ◯ Upcoming |  | 
Stage | ◯ Upcoming |  | 
Implementation | ◯ Upcoming | 11/11 | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | $100,000
YTD Actuals | Not supplied
Remaining Forecast | $96,874
Year-End Forecast | $96,874
Variance / Delta | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Reduces customer harm, complaints, and regulatory risk from invalid coverage combinations.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
DDIT Sprint 1 completed
DELIVERY LEADER (DL)
Kinney Barbour
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Gary Wilson
TARGET / DELIVERY DATES & % COMPLETE
Target 11/11/2026
50%

## Slide 25
NW Pet: Enhance Multi Denial Code Claims Z160/Z151
Work ID 1029586
OVERALL RAG · 8/31/2026
Green
DESCRIPTION
Enhance claims denial handling to preserve multiple applicable denial reasons, including Z160 and Z151.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Green — MPPC/MPI and ETL DDIT are in progress; target 11/11.
CHANGES / RISKS / ISSUES (CRID)
No escalated CRIDs reported.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ◐ In-progress |  | 
E2E | ◯ Upcoming |  | 
Business UAT / Sign-off | ◯ Upcoming |  | 
Implementation Plan Review | ◯ Upcoming |  | 
Go / No-Go | ◯ Upcoming |  | 
Stage | ◯ Upcoming |  | 
Implementation | ◯ Upcoming | 11/11 | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | $114,000
YTD Actuals | $14,527
Remaining Forecast | $96,834
Year-End Forecast | $111,360
Variance / Delta | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Improves denial accuracy and defensibility while reducing legal/compliance exposure.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
MPPC/MPI DDIT in progress
ETL DDIT in progress
DELIVERY LEADER (DL)
Kinney Barbour
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Alex Suarez
TARGET / DELIVERY DATES & % COMPLETE
Target 11/11/2026
30%

## Slide 26
NW Pet: MPI Pricing Segmentation Sophistication
Work ID 1024050
OVERALL RAG · 8/31/2026
Green
DESCRIPTION
Implement MPI rating-segmentation and utilization changes across release waves.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Green — R9 is on schedule for 9/16 and R10 scope is frozen for RI/DC/CT. R9 DDIT/E2E are complete and R9 UAT is due 9/4.
CHANGES / RISKS / ISSUES (CRID)
No escalated CRIDs reported.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ✓ Done |  | 
E2E | ✓ Done |  | 
Business UAT / Sign-off | ◐ In-progress |  | 9/4
Implementation Plan Review | ◯ Upcoming |  | 
Go / No-Go | ◯ Upcoming |  | 
Stage | ◯ Upcoming |  | 
Implementation | ◐ In-progress | 9/16 | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | $200,000
YTD Actuals | $144,918
Remaining Forecast | $47,489
Year-End Forecast | $192,403
Variance / Delta | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Estimated net benefit of $30M–$50M annually, subject to assumptions and data availability.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
R9 DDIT/E2E complete
R10 scope frozen for RI/DC/CT
R9 UAT due 9/4
DELIVERY LEADER (DL)
Kinney L. Barbour
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Not provided in source
TARGET / DELIVERY DATES & % COMPLETE
R9 target 9/16/2026
90%

## Slide 27
NW Pet: Pet Model Law Reboot
Work ID 1029817
OVERALL RAG · 8/31/2026
Green
DESCRIPTION
Move MPI/MPPC medical and congenital coverage from a 14-day waiting period to delayed coverage.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Green — Wave 3 was implemented 8/12. The REN CR forms update targets 9/16 and Wave 4 is planned for November; requirements are due 9/1.
CHANGES / RISKS / ISSUES (CRID)
No escalated CRIDs reported.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ✓ Done |  | 
E2E | ✓ Done |  | 
Business UAT / Sign-off | ◐ In-progress |  | 
Implementation Plan Review | ◐ In-progress |  | 
Go / No-Go | ◐ In-progress |  | 
Stage | ◐ In-progress |  | 
Implementation | ◐ In-progress | 8/12 | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | $750,000
YTD Actuals | $554,981.75
Remaining Forecast | $194,172.70
Year-End Forecast | $194,994.70
Variance / Delta | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Regulatory readiness and consistent coverage treatment across products.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Wave 3 implemented 8/12
REN CR forms update targeted 9/16
Wave 4 planned for November; requirements due 9/1
DELIVERY LEADER (DL)
Venkata Dinesh Konatalapalli
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Gary T. Wilson (WILSG3)
TARGET / DELIVERY DATES & % COMPLETE
REN CR forms 9/16/2026 · Wave 4 November 2026
80%

## Slide 28
NW Pet: Payroll Billing Defect Fixes / Talend-to-Python Waves
Work ID — (not in source)
OVERALL RAG · 8/31/2026
Green
DESCRIPTION
Deliver payroll-billing defect fixes and Talend-to-Python migration in sequential waves.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Green — Wave 2 sign-off completed 8/17 with production deployment 8/19. Wave 3 targets 9/17, Wave 4 10/15, and Wave 5 11/12. A CDC/non-prod issue is mitigated by a workaround.
CHANGES / RISKS / ISSUES (CRID)
CDC/non-prod issue mitigated by workaround.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ✓ Done |  | 
E2E | ✓ Done |  | 
Business UAT / Sign-off | ✓ Done |  | 
Implementation Plan Review | ✓ Done |  | 
Go / No-Go | ✓ Done |  | 
Stage | ✓ Done |  | 
Implementation | ◐ In-progress | 8/19 | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | Not supplied
YTD Actuals | Not supplied
Remaining Forecast | Not supplied
Year-End Forecast | Not supplied
Variance / Delta | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Stabilizes payroll billing and completes modernization off Talend.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Wave 2 sign-off 8/17
Wave 2 production deployment 8/19
CDC/non-prod issue mitigated by workaround
DELIVERY LEADER (DL)
Rekha Kothandaraman
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Victor Nas
TARGET / DELIVERY DATES & % COMPLETE
Wave 3 9/17 · Wave 4 10/15 · Wave 5 11/12/2026
50%

## Slide 29
NW Pet: Refresh the Windows 2022 Server
Work ID 1029977
OVERALL RAG · 8/31/2026
Green
DESCRIPTION
Upgrade the Windows Server OS to 2022 across 71 servers.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Green — 41 non-prod and 11 MIM production servers are complete; 2 are scheduled 8/24 and 3 on 8/26, with remaining teams in September. Target is 9/30 across 71 servers total.
CHANGES / RISKS / ISSUES (CRID)
No escalated CRIDs reported.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ✓ Done |  | 
E2E | ✓ Done |  | 
Business UAT / Sign-off | ✓ Done |  | 
Implementation Plan Review | ✓ Done |  | 
Go / No-Go | ◐ In-progress |  | 
Stage | ◐ In-progress |  | 
Implementation | ◐ In-progress |  | 9/30
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | $50,000
YTD Actuals | Not supplied
Remaining Forecast | Not supplied
Year-End Forecast | Not supplied
Variance / Delta | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Maintains platform supportability and reduces infrastructure risk.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
41 non-prod servers complete
11 MIM production servers complete
2 scheduled 8/24; 3 scheduled 8/26; remaining in September
DELIVERY LEADER (DL)
Chalam Buddha
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Not provided in source
TARGET / DELIVERY DATES & % COMPLETE
Target 9/30/2026
75%

## Slide 30
NW Pet: Enhancement for Commission Reporting — Internal Batch
Work ID 1029608
OVERALL RAG · 8/31/2026
Green
DESCRIPTION
Enhance internal batch processing for sales commission reporting.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Green — kickoff 8/26. Three reports are identified for BO→Power BI conversion and Oracle→Snowflake data movement; target 9/30.
CHANGES / RISKS / ISSUES (CRID)
No escalated CRIDs reported.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ◐ In-progress |  | 
DDIT | ◯ Upcoming |  | 
E2E | ◯ Upcoming |  | 
Business UAT / Sign-off | ◯ Upcoming |  | 
Implementation Plan Review | ◯ Upcoming |  | 
Go / No-Go | ◯ Upcoming |  | 
Stage | ◯ Upcoming |  | 
Implementation | ◯ Upcoming |  | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | $60,000
YTD Actuals | $31,344
Remaining Forecast | $91,344
Year-End Forecast | Not supplied
Variance / Delta | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
More accurate and timely sales commission reporting.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Kickoff 8/26
Three reports identified for BO→Power BI and Oracle→Snowflake
DELIVERY LEADER (DL)
Chalam Buddha
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Not provided in source
TARGET / DELIVERY DATES & % COMPLETE
Target 9/30/2026
10%

## Slide 31
NW Pet: 2026 GIN Updates
Work ID 1029587
OVERALL RAG · 8/31/2026
Green
DESCRIPTION
Deliver the 2026 GIN platform updates.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Green — target 9/30. Requirements, scope, and line schedule are still being finalized.
CHANGES / RISKS / ISSUES (CRID)
No escalated CRIDs reported.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ◐ In-progress |  | 
DDIT | ◯ Upcoming |  | 
E2E | ◯ Upcoming |  | 
Business UAT / Sign-off | ◯ Upcoming |  | 
Implementation Plan Review | ◯ Upcoming |  | 
Go / No-Go | ◯ Upcoming |  | 
Stage | ◯ Upcoming |  | 
Implementation | ◯ Upcoming |  | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | $60,000
YTD Actuals | Not supplied
Remaining Forecast | Not supplied
Year-End Forecast | Not supplied
Variance / Delta | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Maintains platform currency and release readiness.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Requirements, scope, and line schedule being finalized
DELIVERY LEADER (DL)
Chalam Buddha
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Gary Wilson
TARGET / DELIVERY DATES & % COMPLETE
Target 9/30/2026
15%

## Slide 32
NW Pet: CPP Right to Delete & Right to Access (Externally Funded)
Work ID — (not in source)
OVERALL RAG · 8/31/2026
Green
DESCRIPTION
Implement CPP consumer Right to Delete and Right to Access capabilities (externally funded).
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Green — requirements are approved; technical design and line estimates are pending; target 9/30.
CHANGES / RISKS / ISSUES (CRID)
No escalated CRIDs reported.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ◐ In-progress |  | 
E2E | ◯ Upcoming |  | 
Business UAT / Sign-off | ◯ Upcoming |  | 
Implementation Plan Review | ◯ Upcoming |  | 
Go / No-Go | ◯ Upcoming |  | 
Stage | ◯ Upcoming |  | 
Implementation | ◯ Upcoming |  | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | $60,000
YTD Actuals | Not supplied
Remaining Forecast | Not supplied
Year-End Forecast | Not supplied
Variance / Delta | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Regulatory compliance for consumer privacy rights.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Requirements approved
Technical design and line estimates pending
DELIVERY LEADER (DL)
Chalam Buddha
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Not provided in source
TARGET / DELIVERY DATES & % COMPLETE
Target 9/30/2026
15%

## Slide 33
NW Pet: Vulnerabilities Remediation
Work ID — (not in source)
OVERALL RAG · 8/31/2026
Green
DESCRIPTION
Remediate open platform vulnerabilities, including AI-agent-assisted remediation.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Green / active remediation — scope is defined with a cloud-run stabilization dependency. Approximately 1,200 vulnerabilities are in scope; AI-agent remediation has started with a past-due closure target of 8/31.
CHANGES / RISKS / ISSUES (CRID)
Cloud-run stabilization dependency for full remediation.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ◐ In-progress |  | 
E2E | ◯ Upcoming |  | 
Business UAT / Sign-off | ◯ Upcoming |  | 
Implementation Plan Review | ◯ Upcoming |  | 
Go / No-Go | ◯ Upcoming |  | 
Stage | ◯ Upcoming |  | 
Implementation | ◯ Upcoming |  | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | Not supplied
YTD Actuals | Not supplied
Remaining Forecast | Not supplied
Year-End Forecast | Not supplied
Variance / Delta | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Reduced security exposure across the platform.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Scope defined (~1,200 vulnerabilities)
AI-agent remediation started
DELIVERY LEADER (DL)
Chalam Buddha
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Not provided in source
TARGET / DELIVERY DATES & % COMPLETE
Past-due closure target 8/31/2026
40%

## Slide 34
NW Pet: Legacy Talend to Python Migration
Work ID 1029588
OVERALL RAG · 8/31/2026
Green
DESCRIPTION
Migrate Pet ETL workflows off Talend to Python/modernized services.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Green (latest available source 7/20/2026) — no newer status update was supplied. Retained from the last sourced report; kickoff and team engagement being scheduled.
CHANGES / RISKS / ISSUES (CRID)
No escalated CRIDs in the latest available source.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ◐ In-progress |  | 
E2E | ◯ Upcoming |  | 
Business UAT / Sign-off | ◯ Upcoming |  | 
Implementation Plan Review | ◯ Upcoming |  | 
Go / No-Go | ◯ Upcoming |  | 
Stage | ◯ Upcoming |  | 
Implementation | ◯ Upcoming |  | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | Not supplied
YTD Actuals | Not supplied
Remaining Forecast | Not supplied
Year-End Forecast | Not supplied
Variance / Delta | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Reduces legacy platform dependency and supports a modern ETL architecture.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Latest status update not provided — retained from 7/20/2026 source
DELIVERY LEADER (DL)
Chalam Babu Buddha
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Not provided in source
TARGET / DELIVERY DATES & % COMPLETE
Latest available source 7/20/2026
22%

## Slide 35
NW Pet: Pet Paperless eDelivery
Work ID 1026960
OVERALL RAG · 8/31/2026
Completed
DESCRIPTION
Unified business-rules and preference-management capability for Pet digital communications.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Completed core release — the one-time data load and MMP2 warranty are complete. Dashboard refinements were targeted for 8/28.
CHANGES / RISKS / ISSUES (CRID)
No escalated CRIDs reported; dashboard refinements in warranty.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ✓ Done |  | 
E2E | ✓ Done |  | 
Business UAT / Sign-off | ✓ Done |  | 
Implementation Plan Review | ✓ Done |  | 
Go / No-Go | ✓ Done |  | 
Stage | ✓ Done |  | 
Implementation | ✓ Done |  | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | $990,000
YTD Actuals | $933,321
Remaining Forecast | $52,920
Year-End Forecast | $986,242
Variance / Delta | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
More consistent member communications and less fragmented preference management.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Core release complete
One-time data load complete
MMP2 warranty complete
DELIVERY LEADER (DL)
Shilpa K
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Kelly Heitmann
TARGET / DELIVERY DATES & % COMPLETE
Dashboard refinements targeted 8/28/2026
99%

## Slide 36
NW Pet: Data Center Production Migration
Work ID 1022011
OVERALL RAG · 8/31/2026
Completed
DESCRIPTION
Migrate Pet infrastructure from Irvine/Dallas co-location facilities to Nationwide data centers.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Completed — cutover 7/24; Dallas retirement 8/13; Irvine retirement 8/17; retrospective 8/21. Warranty defects are being tracked.
CHANGES / RISKS / ISSUES (CRID)
Warranty defects tracked post-migration.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ✓ Done |  | 
E2E | ✓ Done |  | 
Business UAT / Sign-off | ✓ Done |  | 
Implementation Plan Review | ✓ Done |  | 
Go / No-Go | ✓ Done |  | 
Stage | ✓ Done |  | 
Implementation | ✓ Done |  | 7/24
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | N/A
YTD Actuals | N/A
Remaining Forecast | N/A
Year-End Forecast | N/A
Variance / Delta | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Modernized infrastructure and reduced co-location dependency.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Production cutover 7/24
Dallas retirement 8/13
Irvine retirement 8/17
Retrospective 8/21
DELIVERY LEADER (DL)
Kinney Barbour
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Melissa Morris
TARGET / DELIVERY DATES & % COMPLETE
Cutover 7/24 · retrospective 8/21/2026
100%

## Slide 37
NW Pet: Non-Insurance Bundle v1
Work ID 1024485
OVERALL RAG · 8/31/2026
Completed
DESCRIPTION
Deliver an affordable, comprehensive pet-protection option for employees and employer groups.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Completed — the production release is complete. Reporting follow-up does not affect product delivery.
CHANGES / RISKS / ISSUES (CRID)
No escalated CRIDs reported.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ✓ Done |  | 
E2E | ✓ Done |  | 
Business UAT / Sign-off | ✓ Done |  | 
Implementation Plan Review | ✓ Done |  | 
Go / No-Go | ✓ Done |  | 
Stage | ✓ Done |  | 
Implementation | ✓ Done |  | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | $273,000
YTD Actuals | $164,899
Remaining Forecast | $108,000
Year-End Forecast | $273,000
Variance / Delta | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
New employee/broker offering with convenience and broader adoption potential.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Production release complete
Reporting follow-up does not affect product delivery
DELIVERY LEADER (DL)
Rekha Kothandaraman
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Nidia Gudino
TARGET / DELIVERY DATES & % COMPLETE
Production release complete
100%

## Slide 38
NW Pet: Update Legacy Portal Interface to UAv3
Work ID 1029592
OVERALL RAG · 8/31/2026
Completed
DESCRIPTION
Update the legacy portal interface to UAv3, including authentication integration.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Completed / deployed — the 8/5 deployment is validated and sign-offs are received. Warranty runs through 9/5.
CHANGES / RISKS / ISSUES (CRID)
No escalated CRIDs reported; warranty through 9/5.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ✓ Done |  | 
E2E | ✓ Done |  | 
Business UAT / Sign-off | ✓ Done |  | 
Implementation Plan Review | ✓ Done |  | 
Go / No-Go | ✓ Done |  | 
Stage | ✓ Done |  | 
Implementation | ✓ Done |  | 8/5
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | $67,200
YTD Actuals | $34,673
Remaining Forecast | $20,000
Year-End Forecast | $20,000
Variance / Delta | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
A supported authentication path and reduced operational risk for the legacy portal.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
8/5 deployment validated
Sign-offs received
Warranty through 9/5
DELIVERY LEADER (DL)
Chalam Buddha
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Not provided in source
TARGET / DELIVERY DATES & % COMPLETE
Deployed 8/5/2026 · warranty through 9/5/2026
100%

## Slide 39
NW Pet – GW Cloud Platform Migration
Work ID 1021174
OVERALL RAG · 8/31/2026
Completed
DESCRIPTION
Migrate the GW platform to the target cloud environment.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Completed — retained from the monthly-deck baseline. The cloud-platform migration is complete with no reported cost, scope, or schedule exception.
CHANGES / RISKS / ISSUES (CRID)
No escalated CRIDs reported.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ✓ Done |  | 
E2E | ✓ Done |  | 
Business UAT / Sign-off | ✓ Done |  | 
Implementation Plan Review | ✓ Done |  | 
Go / No-Go | ✓ Done |  | 
Stage | ✓ Done |  | 
Implementation | ✓ Done |  | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | $350,000 (allocated)
YTD Actuals | Not supplied
Remaining Forecast | Not supplied
Year-End Forecast | Not supplied
Variance / Delta | Not supplied
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Modernized infrastructure and reduced platform dependency risk.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Cloud platform migration complete (retained from baseline)
DELIVERY LEADER (DL)
Chalam Babu Buddha
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Not provided in source
TARGET / DELIVERY DATES & % COMPLETE
Migration complete (retained baseline)
100%

## Slide 40
EDO: Talend Run
Work ID 1020895
OVERALL RAG · 8/31/2026
Red
DESCRIPTION
Run and sustain the Talend platform while resolving the Aurora write-access constraint affecting the GIN T2P design.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Latest status update not provided — retained from the 7/31/2026 source. Sustained Red: the Aurora write-access restriction impacts the T2P implementation for the GIN component.
CHANGES / RISKS / ISSUES (CRID)
Risk R-2251656 — Write Access Restriction (Aurora). Priority High · Type Schedule · Status Open.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ✓ Done |  | 
E2E | ✓ Done |  | 
Business UAT / Sign-off | ✓ Done |  | 
Implementation Plan Review | ✓ Done |  | 
Go / No-Go | ✓ Done |  | 
Stage | ◐ In-progress |  | 
Implementation | ◐ In-progress |  | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | Not in source
YTD Actuals | Not in source
Remaining Forecast | Not separately reported
Year-End Forecast | $901,138 (WM Fcst)
Variance / Delta | $626,136 (Δ vs Jan)
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Operational continuity and a viable path to modernize ETL delivery.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Latest status update not provided — retained from 7/31/2026 source
DELIVERY LEADER (DL)
Gregory T. Davis
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Not provided in source
TARGET / DELIVERY DATES & % COMPLETE
Latest available source 7/31/2026
99%

## Slide 41
NW Pet – PPT Program
Work ID 1014117
OVERALL RAG · 8/31/2026
Yellow
DESCRIPTION
Modernize Pet backend systems through the PPT program and coordinate migrations, employer portal, and payroll billing.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Latest status update not provided — retained from the 7/31/2026 source. Yellow: Finance requirements and Employer Portal integration create schedule risk, with longer-term funding pressure.
CHANGES / RISKS / ISSUES (CRID)
Risk R-2245180 (Open): Employer Portal Bundles 4–5 schedule risk. Risk R-2245181 (Open): 2027 funding risk.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ✓ Done |  | 
E2E | ✓ Done |  | 
Business UAT / Sign-off | ✓ Done |  | 
Implementation Plan Review | ✓ Done |  | 
Go / No-Go | ◐ In-progress |  | 
Stage | ◯ Upcoming |  | 
Implementation | ◯ Upcoming |  | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | Not in source
YTD Actuals | Not in source
Remaining Forecast | Not separately reported
Year-End Forecast | $399,447 (WM Fcst)
Variance / Delta | ($331,210) (Δ vs Jan)
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Modernized core platform and reduced long-term REN cost exposure.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Latest status update not provided — retained from 7/31/2026 source
DELIVERY LEADER (DL)
Ali Dadgar
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Not provided in source
TARGET / DELIVERY DATES & % COMPLETE
Latest available source 7/31/2026
92%

## Slide 42
NW Pet: 2026 Product Rate Refresh
Work ID 1029254
OVERALL RAG · 8/31/2026
Green
DESCRIPTION
Implement annual product rate-refresh changes.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Latest status update not provided — retained from the 7/31/2026 source. Green: DDIT completed 6/05; UAT sign-off recorded; production implementation completed 6/17.
CHANGES / RISKS / ISSUES (CRID)
Change C-2215383 (Open): excess rate-refresh funding to move to product profitability.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ✓ Done |  | 
E2E | ✓ Done |  | 
Business UAT / Sign-off | ◐ In-progress |  | 
Implementation Plan Review | ◯ Upcoming |  | 
Go / No-Go | ◯ Upcoming |  | 
Stage | ◯ Upcoming |  | 
Implementation | ◯ Upcoming |  | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | Not in source
YTD Actuals | Not in source
Remaining Forecast | Not separately reported
Year-End Forecast | $56,517 (WM Fcst)
Variance / Delta | ($193,482) (Δ vs Jan)
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Supports approved rates and state/product filing readiness.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Latest status update not provided — retained from 7/31/2026 source
DELIVERY LEADER (DL)
Venkata Dinesh Konatalapalli
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Not provided in source
TARGET / DELIVERY DATES & % COMPLETE
Latest available source 7/31/2026
61%

## Slide 43
NW Pet: Hawaii Territory Factor Change
Work ID 1031022
OVERALL RAG · 8/31/2026
Green
DESCRIPTION
Update Hawaii ZIP-code factors to the required statewide factor.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Latest status update not provided — retained from the 7/31/2026 source. Green: scope is a straightforward table update once the final table is provided.
CHANGES / RISKS / ISSUES (CRID)
No escalated CRIDs reported.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ✓ Done |  | 
E2E | ✓ Done |  | 
Business UAT / Sign-off | ◐ In-progress |  | 
Implementation Plan Review | ◯ Upcoming |  | 
Go / No-Go | ◯ Upcoming |  | 
Stage | ◯ Upcoming |  | 
Implementation | ◯ Upcoming |  | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | Not in source
YTD Actuals | Not in source
Remaining Forecast | Not separately reported
Year-End Forecast | $37,345 (WM Fcst)
Variance / Delta | $37,345 (Δ vs Jan)
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Regulatory compliance with Hawaii DOI rating-factor requirements.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Latest status update not provided — retained from 7/31/2026 source
DELIVERY LEADER (DL)
Rekha Kothandaraman
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Not provided in source
TARGET / DELIVERY DATES & % COMPLETE
Latest available source 7/31/2026
53%

## Slide 44
NW Pet: Maryland MPPC Approval
Work ID 1031033
OVERALL RAG · 8/31/2026
Green
DESCRIPTION
Turn on MPPC state functionality for Maryland.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Latest status update not provided — retained from the 7/31/2026 source. Green: no current exception was reported.
CHANGES / RISKS / ISSUES (CRID)
No escalated CRIDs reported.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ✓ Done |  | 
E2E | ✓ Done |  | 
Business UAT / Sign-off | ◐ In-progress |  | 
Implementation Plan Review | ◯ Upcoming |  | 
Go / No-Go | ◯ Upcoming |  | 
Stage | ◯ Upcoming |  | 
Implementation | ◯ Upcoming |  | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | Not in source
YTD Actuals | Not in source
Remaining Forecast | Not separately reported
Year-End Forecast | $55,500 (WM Fcst)
Variance / Delta | $55,500 (Δ vs Jan)
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Enables Maryland product availability and state readiness.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Latest status update not provided — retained from 7/31/2026 source
DELIVERY LEADER (DL)
Rekha Kothandaraman
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Not provided in source
TARGET / DELIVERY DATES & % COMPLETE
Latest available source 7/31/2026
54%

## Slide 45
NW Pet: NJ MPPC New Product and Rate Capping
Work ID 1029148
OVERALL RAG · 8/31/2026
Yellow
DESCRIPTION
Turn on NJ new business and cap migrated-policy renewal increases for up to four renewals.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Latest status update not provided — retained from the 7/31/2026 source. Yellow: reporting scope delivery is delayed by the Talend-to-Python dependency.
CHANGES / RISKS / ISSUES (CRID)
Issue I-2251662 (Open): reporting scope delivery delay dependent on Talend→Python migration.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ✓ Done |  | 
E2E | ✓ Done |  | 
Business UAT / Sign-off | ✓ Done |  | 
Implementation Plan Review | ◐ In-progress |  | 
Go / No-Go | ◯ Upcoming |  | 
Stage | ◯ Upcoming |  | 
Implementation | ◯ Upcoming |  | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | Not in source
YTD Actuals | Not in source
Remaining Forecast | Not separately reported
Year-End Forecast | $23,100 (WM Fcst)
Variance / Delta | ($1,249) (Δ vs Jan)
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
State-compliant rate capping with auditability.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Latest status update not provided — retained from 7/31/2026 source
DELIVERY LEADER (DL)
Shilpa Sachin Kulkarni
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Not provided in source
TARGET / DELIVERY DATES & % COMPLETE
Latest available source 7/31/2026
72%

## Slide 46
NW Pet: P.E.T. Exchange Encryption Upgrade
Work ID 1029705
OVERALL RAG · 8/31/2026
Green
DESCRIPTION
Replace or supplement AES-CBC with AES-GCM in PET exchange encryption.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Latest status update not provided — retained from the 7/31/2026 source. Green: no current exception was reported.
CHANGES / RISKS / ISSUES (CRID)
No escalated CRIDs reported.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ◐ In-progress |  | 
DDIT | ◯ Upcoming |  | 
E2E | ◯ Upcoming |  | 
Business UAT / Sign-off | ◯ Upcoming |  | 
Implementation Plan Review | ◯ Upcoming |  | 
Go / No-Go | ◯ Upcoming |  | 
Stage | ◯ Upcoming |  | 
Implementation | ◯ Upcoming |  | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | Not in source
YTD Actuals | Not in source
Remaining Forecast | Not separately reported
Year-End Forecast | $31,370 (WM Fcst)
Variance / Delta | $31,370 (Δ vs Jan)
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Stronger encryption posture and reduced security exposure.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Latest status update not provided — retained from 7/31/2026 source
DELIVERY LEADER (DL)
Rekha Kothandaraman
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Not provided in source
TARGET / DELIVERY DATES & % COMPLETE
Latest available source 7/31/2026
0%

## Slide 47
NW Pet: PA WP to MPI Rate Capping and Letter
Work ID 1030929
OVERALL RAG · 8/31/2026
Green
DESCRIPTION
Apply Pennsylvania rate-cap logic and the state-specific non-renewal letter for WP-to-MPI conversion.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Latest status update not provided — retained from the 7/31/2026 source. Green: scope is limited to PA cap logic and the state-specific non-renewal letter.
CHANGES / RISKS / ISSUES (CRID)
No escalated CRIDs reported.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ✓ Done |  | 
E2E | ✓ Done |  | 
Business UAT / Sign-off | ◐ In-progress |  | 
Implementation Plan Review | ◯ Upcoming |  | 
Go / No-Go | ◯ Upcoming |  | 
Stage | ◯ Upcoming |  | 
Implementation | ◯ Upcoming |  | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | Not in source
YTD Actuals | Not in source
Remaining Forecast | Not separately reported
Year-End Forecast | $75,722 (WM Fcst)
Variance / Delta | $75,722 (Δ vs Jan)
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
State-specific compliance and controlled conversion experience.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Latest status update not provided — retained from 7/31/2026 source
DELIVERY LEADER (DL)
Rekha Kothandaraman
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Not provided in source
TARGET / DELIVERY DATES & % COMPLETE
Latest available source 7/31/2026
60%

## Slide 48
NW Pet: QEC A/B Testing & Tool Enhancements
Work ID 1028060
OVERALL RAG · 8/31/2026
Green
DESCRIPTION
Optimize enrollment and digital purchase experiences through A/B testing and QEC/PET tool enhancements.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Latest status update not provided — retained from the 7/31/2026 source. Green: no current exception was reported.
CHANGES / RISKS / ISSUES (CRID)
No escalated CRIDs reported.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ✓ Done |  | 
DDIT | ✓ Done |  | 
E2E | ✓ Done |  | 
Business UAT / Sign-off | ✓ Done |  | 
Implementation Plan Review | ◐ In-progress |  | 
Go / No-Go | ◯ Upcoming |  | 
Stage | ◯ Upcoming |  | 
Implementation | ◯ Upcoming |  | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | Not in source
YTD Actuals | Not in source
Remaining Forecast | Not separately reported
Year-End Forecast | $267,565 (WM Fcst)
Variance / Delta | $221,675 (Δ vs Jan)
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Improves funnel throughput, user experience, and conversion rates.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Latest status update not provided — retained from 7/31/2026 source
DELIVERY LEADER (DL)
Rekha Kothandaraman
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Not provided in source
TARGET / DELIVERY DATES & % COMPLETE
Latest available source 7/31/2026
86%

## Slide 49
NW Pet: WA MPI 5% Affinity Discount Removal
Work ID 1031212
OVERALL RAG · 8/31/2026
Not assessed
DESCRIPTION
Remove the 5% Affinity Discount from WA MPI.
Sub-RAG (Cost · Schedule · Scope): not separately reported in source
RAG ASSESSMENT
Latest status update not provided — retained from the 7/31/2026 source. Not assessed: early planning underway with no overall RAG provided.
CHANGES / RISKS / ISSUES (CRID)
No escalated CRIDs reported.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Start | End
Planning / Discovery | ◐ In-progress |  | 
DDIT | ◯ Upcoming |  | 
E2E | ◯ Upcoming |  | 
Business UAT / Sign-off | ◯ Upcoming |  | 
Implementation Plan Review | ◯ Upcoming |  | 
Go / No-Go | ◯ Upcoming |  | 
Stage | ◯ Upcoming |  | 
Implementation | ◯ Upcoming |  | 
FINANCIALS (AS SUPPLIED BY SOURCE)
Current / Approved Budget | Not in source
YTD Actuals | Not in source
Remaining Forecast | Not separately reported
Year-End Forecast | $34,562 (WM Fcst)
Variance / Delta | $34,562 (Δ vs Jan)
Reported as supplied — blanks remain blank; financials are not recalculated when source fields are missing or inconsistent.
BUSINESS VALUE / BENEFIT
Implements the approved Washington pricing change.
ACCOMPLISHMENTS (LATEST AVAILABLE SOURCE)
Latest status update not provided — retained from 7/31/2026 source
DELIVERY LEADER (DL)
Kinney L. Barbour
BUSINESS LEAD (OPEX / ASSET-ALIGNED PM)
Not provided in source
TARGET / DELIVERY DATES & % COMPLETE
Latest available source 7/31/2026
1%

## Slide 50
Appendix — Sources & Reporting Conventions
August 2026 report · status as of 8/31/2026
SOURCE REPORTS (SHAREPOINT, BY DATE)
August 2026 business status report — SharePoint (status as of 8/31/2026; current status authority)
Prior monthly Build Portfolio deck — structural baseline & legacy project coverage
RAG LEGEND
● Red ● Yellow ● Green ● Completed ● Not assessed
ROLE DEFINITIONS
DL = Delivery Leader
BL = Business Lead — source OpEx Business Lead / Asset-Aligned Program Manager; where absent, the slide flags “Not provided in source.”
DATA-QUALITY CONVENTIONS
The 8/31/2026 business status report is the current status authority for this August monthly report.
Source fields are reported as supplied — blanks remain blank and TBD remains TBD.
Financials are not recalculated when source fields are missing or internally inconsistent.
Where no August update exists, the last available source date is retained and labelled; no August status is fabricated.
Every detail slide keeps Description at top, Accomplishments, and the standard 8-stage milestone table.
Reporting Basis
Reporting month August 2026 · latest source snapshot 8/31/2026