## Slide 1: 2026 Weekly Portfolio Status
Cindy Trudeau & Delivery Leads
Aug 31, 2026
Pet Tech Delivery

## Slide 2: Red Projects

## Slide 3: Add-a-Pet Improvements Streamline the add‑a‑pet quote flow to boost conversion by showing the right products and eliminating redundant data entry
Status Key | C | Completed |  | On-Schedule |  | Major Issues |  | Some Issues | NS | Not Started
Milestone | Status | Due Date | Notes
Validate and Lock business requirements | C | 1/20 | 
Obtain approval from BDE | C | 2/10 | Incorporated BDE feedback
Detail Requirements and Epic Creations | C | 1/26/-2/9 | Scott (TA) to deliver; Nidia met with Scott on 1/30 to support Epic creations.
Deliver end‑to‑end architectural design for the new solution. | C | 2/2-2/13 2/20 | Josh shared with IT teams on 2/23
Provide L0 project estimates with high‑level scope and effort | C | 3/6/26 | Line estimates are being received
Build project plan based online approval of estimates | C | 3/17 | Rekha will build-transitioned to DL on 3/13 after reviewing estimates and planning budget.
Technical Design | C | 2/27 | Vu Pham will complete
DDIT | C | 7/8 7/20 | EW/Tail Blazers/MIM/Scrum Sharks have begun work. Duration is 40 days.
E2E |  | 8/5 9/1 | E2E in progress with 86% completed, 14% no run
UAT |  | 8/7 9/2 | UAT in progress
Go Live | NS | 8/12 8/19 8/26 TBD | 
Critical Risks/Issues | Status | Target Date | Resolution / Mitigation
Two showstopper defects remain open in Add a Pet (MPI enrollment and payment processing). Additional issues involving member prefill and employer selection are under review. These defects currently block production deployment and contribute to schedule risk. | C | 8/25 | Teams are prioritizing resolution of the showstopper defects and completing E2E retesting. Remaining issues are being assessed for disposition. Production readiness is dependent on successful validation, business approval, and closure of critical defects.
GoupID is showing up as “NULL” for policies created with Non Payroll Code |  | 8/31 | GOP team is working on this requirement
Status: Overall Status: RED
The Add a Pet project remains in Red status due to critical open defects and additional logical change required Based on current discussions, the next potential deployment target is 9/9, contingent upon successful remediation of critical defects, completion of testing, and business approval. Path To Yellow:
Complete E2E retesting and validate all previously resolved defects across critical business flows.
Demonstrate stable integrations and consistent test execution results.
Path To Green:
Receive business UAT sign-off.
Obtain final release approvals and confirm production readiness
Accomplishments:
Overall execution has reached 86% completion, with 12% Blocked and 2% no run.
Resolved previously reported E2E blockers and environment-related issues.
Restored testing environments and resumed end-to-end retesting activities.
Continued cross-team collaboration to validate critical business flows and integrations.
Advanced testing efforts toward overall release readiness.
Next Steps:
Complete remaining E2E retesting and validation activities.
Monitor and address any defects identified during retesting.
Continue business validation and UAT support activities.
Finalize release readiness assessments and deployment planning.
Review schedule risks and ensure readiness criteria are met before confirming the next release date.
Project Manager : Rekha Kothandaraman
OpEx Business Lead: Nidia Gudino
Status Date: | 8/28/2026
2026 Budget | YTD Actuals | Remaining 2026 Forecast | Current YE Forecast | Total Budget
$356,440 | $233,740 | $122,700 | $356,440 | $356,440
Overall | Scope | Schedule | Financials
Target Delivery: | Aug 12th – Aug 19th – Aug 26th TBD

## Slide 4: MPPC UW Questions Reduction MVP3
Status Key | C | Completed |  | On-Schedule |  | Major Issues |  | Some Issues | NS | Not Started
Status Date: | 08/28/2026
2026 Budget | YTD Actuals | Remaining 2026 Forecast | Current YE Forecast | Total Budget
$341,000 | $197,033 | $146,296 | $343,330 | $341,000
Overall | Scope | Schedule | Financials
Target Delivery: | 8/26/2026 9/9/26 (MVP3) 12/9/26 2/10/27 /(CR-RPQ)
Milestone | Status | Due Date | Notes
E2E Testing Completed (MVP3) | C | 7/16 - 8/11 | 
UAT Completed (MVP3) | C | 7/29 – 8/11 | 
Go-No Go Meeting Scheduled (MVP3) | C | 8/11 | 
Stage Validation Completed (MVP3) | NS | 8/19 9/4 | Need to find environment to validate
Prod Deployment (MVP3) | NS | 8/26 9/9 | Rescheduled from 8/12 to 8/19 offcycle
Warranty (MVP3) | NS | 9/16 | 2 missed requirement planned to deliver during warranty.
Project level Epics Created (CR – RPQ) | C | 8/19 | 
EPIC Prioritization by Product Owners (RPQ) | C | 8/19 | Prioritized in respect to Feb Release
Project Schedule/Timeline Draft (RPQ) | C | 8/19 | 
Stakeholder signoff for CQ data change (RPQ) | C | 8/26 8/31 | Send email request for stakeholder approval
Critical Risks/Issues | Status | Target Date | Resolution / Mitigation
Portal Project Dependency with Add A Pet project |  | 9/4 | Hard dependency. High level of confidence for 9/9 release
Status Update
Overall Status: Red
Justification
Due to dependencies and testing delays associated with the Add A Pet project, the release will no longer target the 8/26 off-cycle deployment date and is rescheduled to target 9/9. UAT is complete and signed off with no issues.
Additionally, the Change Request to remove the prior underwriting question is now expected to move from the planned December 2026 implementation to February 2027. This shift is driven by competing priorities, capacity constraints across the Scrum Sharks and Epic Winners teams, and the December code freeze.
We have sent the request to key stakeholders for approval of the move to the February release.
Path to yellow
Develop and provide the financial estimate required to support the Change Request extension into February 2027. (8/24) Complete
Obtain formal approval from project governance for the revised Change Request implementation date. (8/26) 8/31 Complete
Obtain a high level of confidence in UAT signoff for the Add A Pet project to support the planned 9/9 release. (9/4)
Accomplishments
DDIT complete for Warranty fix TAB-1027 for showing pop-up when no vet is available.
Next Steps
UAT for TAB-1027
DDIT complete and UAT for TAB-1038 ‘Display - Not one of these options’
Project Manager : Kinney Barbour
OpEx Business Lead: Sara Andrews

## Slide 5: Yellow Projects

## Slide 6
Status Key | C | Completed |  | On-Schedule |  | Major Issues |  | Some Issues | NS | Not Started
Status Date: | 08/28/2026
2026 Revised Budget | YTD Actuals | Remaining 2026 Forecast | Total Actuals +Fcst | Original Budget
$4,050,000 | $1,809,495 | $2,044,359.81 | $3,853,855 | $6,200,000
Overall | Scope | Schedule | Financials
Target Delivery: | Dark Launch: Oct 14 Go live: Nov 11
Milestone | Status | Due Date | Notes
Bundle 2 (Communication and Servicing)) | C | 5/6 | 
Bundle 3 (VBO admin) | C | 5/27 | 
Bundle 4 (Billing) | C | 8/18 | 
Finance Schedule | C | 7/17 | 
Dark Launch | C | 8/12 | 
Finance Development |  | 9/2 | 
Bundle 5 (Payments and IAM Integration) |  | 9/29 | E2E testing is Red as scope and priorities are not yet finalized
Bundle 6 (Stability, reporting Finance Integration) |  | 10/09 | Yellow as scope is not finalized
IAM Dark Launch |  | 10/08 | Testing is on hold pending on RBAC/SSO completion
End to End and UAT Validation |  | 10/09 | 
Portal dark launch |  | 10/21 | 
Finance Prod Deployment | NS | 10/23 | 
Go Live | NS | 11/11 | 
Warranty | NS | 12/9 | 
Onboarding, stability and user experience | NS | 4/30 | 
“Should Have” Features | NS | 5/31/27 | 
Critical Risks/Issues | Status | Target Date | Resolution / Mitigation
The October 14 dark launch remains achievable but is at risk because UAT now completes October 9, leaving no schedule contingency. Bundle 4 invoice defects and Bundle 6 scope compression could delay testing, defect resolution, and deployment readiness. |  | 8/28 9/4 | Conduct daily IT/business defect triage, prioritize and retest critical invoice and access-control defects, approve a skinny Bundle 6 MVP, validate Finance integration in parallel, defer nonessential scope to the November 11 release, and secure Release Management approval for the revised timeline by August 28.
Overall status is Yellow trending Red: Delivery and testing remain at risk because Bundle 5 and Bundle 6 scope and priorities are still being finalized, Critical and High functionality requires completion and code validation, and open defects and dependencies are preventing a reliable E2E schedule.
Bundle 5 and 6 Schedule Risk and Mitigation Plan:
Risk
  E2E status is Red: Bundle 5 and Bundle 6 scope and priorities are not yet finalized.
  Implementation readiness is uncertain: Critical and High-priority functionality still requires completion and code validation.
  Schedule is at risk: The Bundle 5 testing scope and timeline must be re-baselined.
  Defects remain open: Several defects require owner assignment, review, and disposition.
  Business impact: The team cannot yet confirm a reliable E2E testing schedule or release-readiness date.
  IAM Integration Testing (Phase 1) is Yellow: E2E testing is scheduled for August 31–September 11, but testing is on hold pending RBAC/SSO completion and internal CSR and Proxy Registration testing targeted for August 28.
  Finance Integration Testing is Yellow: Cycle 1 and Cycle 2 E2E testing is scheduled for September 4–October 2, but outstanding test-planning actions and dependency on Bundle 5 Critical and High Cash testing could affect the schedule.
Mitigation Plan or Go to Green Plan (9/4)
  Finalize priorities: VBO and Cash business teams to complete behavior prioritization by August 27.
  Close critical gaps: Development to complete and validate all remaining Critical and High-priority functionality.
  Re-plan testing: QE to continue backend file-processing validation for Finance integration testing and prepare a revised internal-screen E2E plan.
  Manage defects: Accountable owners to resolve or disposition open Bundle 5 defects with target dates.
  Resolve dependencies: Confirm Finance, payment, and IAM dependencies, owners, and readiness dates.
  Leadership action: Remove blockers, confirm staffing and ownership, and maintain Red status until scope, implementation readiness, defect disposition, and the revised testing
Financial
  July ME: YTD spend is $1.8M, a $43K decrease month over month, with a YE forecast of $3.8M, approximately $0.3M under the $4.2M budget. The reduction was primarily driven by lower-than-forecast labor spend in the Pawroll Pioneers and Rangers workstream and the release of all remaining contingency to the portfolio.
  An additional $250K has been allocated to accelerate “Should-Have” scope, bringing the total project budget to $4.05M. If resources are not assigned by mid-September, the funding may not be fully utilized.
Payroll Billing Employer Portal Seamless Self-Service Administration for Payroll Employer Groups
Delivery Leader: Ali Dadgar
OpEx Business Lead: Victor Nas

## Slide 7: FirstVet Consultation File - API
Status Key | C | Completed |  | On-Schedule |  | Major Issues |  | Some Issues | NS | Not Started
Status Date: | 8/28/2026
2026 Budget | YTD Actuals | Remaining 2026 Forecast | Current YE Forecast | Total Budget
69,100 | 32,330 | 53,268 | 74K | 74K
Overall | Scope | Schedule | Financials
Target Delivery: | Aug 12th - Aug 19th
Milestone | Status | Due Date | Notes
Validate and Lock business requirements | C | 4/2 | 
Obtain approval from BDE | C | 4/2 | Incorporated BDE feedback
DDIT – Epic Winner | C | 6/24 | Epic winners still in DDIT and requested additional hrs for DDIT effort
DDIT – Analysis This | C | 7/28 | 
Testing | C | 7/30 | 
E2E testing | C | 8/5 | 
Vendor Integration testing | C | 8/18 | Had session with vendor to discuss the integration testing Plan
Production | C | 8/19 | 
Transfer file to ImageRight Location |  | 9/14 | 
Critical Risks/Issues | Status | Target Date | Resolution / Mitigation
End to end testing and Integration should be planned ahead with the Firstvet vendor | C | 8/6 | Schedule meeting with vendor to communicate the plan for E2E testing and system integration steps
Vendor Connectivity Readiness: Vendor-side setup and connectivity validation remain in progress. | C | 8/18 | Vendor is working to ensure all required configurations are established before final testing. Completion of end-to-end vendor validation is required prior to production execution.
Code push to stagging environment is blocked due to access restriction | C | 8/17 | Working with secondary owner to resolve the access issue
The ImageRight integration Change Request required for consultation file processing is awaiting prioritization and a committed delivery date from MIM team. Also awaiting funding approval confirmation. Delays in prioritization or implementation may impact production readiness, end-to-end testing, claims support functionality, and the September 21, 2026 telemedicine launch timeline. |  | 9/14 | Actively engage MIM stakeholders to secure prioritization and delivery commitments, escalate through program governance as needed, and monitor progress daily while evaluating interim workaround options.
Status:
Overall Status YELLOW
The FirstVet Consultation API project has advanced to Yellow status following the successful deployment of the FirstVet Consultation API file release and resolution of the Stage deployment access issue. Functional testing has been completed successfully with no outstanding application defects, and core deployment objectives have been achieved. Vendor integration verification activities are underway as planned.
New Change Request: A change request was required to fund and implement a previously unidentified ImageRight integration dependency that is essential for end-to-end Vet Consultation processing, claims support, and readiness for the September 21, 2026 telemedicine launch.
Path To Green:
Complete MIM ImageRight import development, testing, and New Relic monitoring implementation.
Validate consultation record availability in ImageRight.
Complete production readiness activities and launch support preparations.
Accomplishments :
MIM ImageRight import development completed
Resolved the generic ID/password authentication issue that previously blocked deployment activities.
Successfully deployed the FirstVet Consultation API file release.
Completed functional testing and retesting with no outstanding functional defects.
Identified and documented the ImageRight import and monitoring dependency required for end-to-end processing.
Established cross-functional alignment among Engineering, Operations, Data Analytics, MIM, QE, and Vendor teams to support launch readiness.
Next Steps:
Complete postproduction deployment activities.
Monitor initial production execution and validate weekly ETL scheduling requirements.
complete the import work within ImageRight before testing can begin
Resolve QA environment issue to import the work
Project Manager : Rekha Kothandaraman
OpEx Business Lead: Kelly Heitmann

## Slide 8: Portal Stabilization
Status Key | C | Completed |  | On-Schedule |  | Major Issues |  | Some Issues | NS | Not Started
Status Date: | 8/28/2026
2026 Budget | YTD Actuals | Remaining 2026 Forecast | Total Budget
$75,000 | $32,221 | $78,142 | $112,056
Overall | Scope | Schedule | Financials
Target Delivery: | TBD
Milestone | Status | Due Date | Notes
Breakdown Portal Stability Scope into tasks, scope, sequencing, outcomes, metrics, target go live | C | 7/24 | Workbook has been created and 2026 scope identified. Need to rebaseline current state.
Widget / security / version upgrades |  | 08/19 08/26 09/09 | 08/14 - Angular Upgrade is moved to 08/26 due to the issues with the Add-A-Pet project changes. 08/21 - Angular Upgrade is moved to 09/09 due to the issues with the Add-A-Pet project changes.
Login/Access/Registration Reliability | C | 08/13 08/17 | Deployed in prod - Missing policy documents now load for members with migrated policies (passes multiple insured codes). Pivot document links now open on iPad (pop-up blocker fix). Deductible tracker now displays the applied / remaining deductible.
Payments / enrollment / billing reliability |  | 10/31 | Analysis and Development work is in progress for the Prod issues identified till 06/30 for this scope item. Backlog is being created for the issues identified later 06/30.
Remove chatty / redundant API calls |  | 09/16 | Development is completed. Release planned for 09/16.
Apigee / API alignment |  | 09/16 | Development is completed. Release planned for 09/16.
Critical Risks/Issues | Status | Target Date | Resolution / Mitigation
Project remains yellow due to the budget overage beyond September activities |  | 08/31 09/04 | Resources are allocated till Sep with the current budget of 75K for Portal Stability. Need more funding for the work planned for Q4. CR will be submitted once the additional scope is received for Q4 portal stability work
Status:
Overall Status: Yellow – Scope is identified and Resources are allocated till Sep for the approved budget of 75K for Portal Stability. Additional funding required for the work planned for Q4.
Path to Green – Requested teams to provide the scope clarity on Portal Stability and high-level effort estimates for Q4 work by 09/04 for CR submission.
Portal stability
Team worked on the scope and the work is in progress for Aug and Sep release activities.
The scope is locked based on the window selection of the deployment date. Any new incidents identified after that date will be added to backlog and team will prioritize them accordingly.
Prod release for Angular upgrade is rescheduled for 09/09 from 08/26 due to issues identified with the Add-A-PET project changes
All issues identified as of 07/31 for the scope item Login / Access / Registration Reliability have been resolved. Any new incidents reported after 07/31 for this scope item will be added to the backlog.
Project Manager : Dinesh
OpEx Business Lead: Nidia Gudino
Portal scope item | Release
Widget / security / version upgrades | Rel - 1 (Sep)
CI/CD Modernization | Rel-1 (Oct)
Login / access / registration reliability | Rel - 1 (Aug)
Code cleanup / memory leak / type safety | Rel - 1 (Sep)
Apigee / API alignment | Rel - 1 (Sep)
Remove chatty / redundant API calls | Rel - 1 (Sep)
Claim submission reliability | Rel - 2 (Oct)
Payments / enrollment / billing reliability | Rel - 2 (Oct)
Config and performance optimization | Rel - 1 (Aug)

## Slide 9: GIN / Batch Stabilization
Status Key | C | Completed |  | On-Schedule |  | Major Issues |  | Some Issues | NS | Not Started
Status Date: | 08/28/2026
2026 Budget | YTD Actuals | Remaining 2026 Forecast | Total Budget
$425,000 | $243,318 | $386,168 | $663,871
Overall | Scope | Schedule | Financials
Target Delivery: | Monthly releases
Milestone | Status | Due Date | Notes
Capacity / scalability to 1-2M policies – Discovery Phase | C | 07/31/26 | Completed the discovery. Started the new initiative for solutioning and implementation work and tracked as a separate project.
RRD Failures | C | 07/31/2026 | Completed. RRD Ananlysis completed and redesign will be taken after the Python Conversion
Concurrency Error – Customer Update – Permanent Fix | C | 07/15/2026 | Deployed to Production. 30+ incidents reported for last 12 months.
ECIF Call related Changes for Conversion Policies | C | 08/12/2026 | Planned for August Release. 50+ incidents reported for last 12 months related to ECIF for Converted Policies.
ECN Missing for NB Issuance for Payroll Policies | C | 08/12/2026 | Planned for August Release. This will fix 80+ incidents reported for last 12 months related to missing ECN for Payroll policies
Line Estimations on the Solution Approach for Data Integrity | C | 07/31/2026 08/21/2026 | Solution Approach reviewed and requested lines MIM & SS teams for Line estimations. MiM and SS teams provided the estimates and work has been kicked off.
Task System clean up/ Error reduction |  | 09/15/2026 | Team is working on Task errors identified till the date. 2 task errors 2038 and 2005 are planned for 09/15
ECIF Data Integrity – Convert CEM to Java Golden Path – Analysis & DDII |  | 10/14/2026 | Analysis is in progress
Critical Risks/Issues | Status | Target Date | Resolution / Mitigation
Project remains yellow on the budget overage |  | 09/04/2026 | Data Integrity effort – Estimates are received from MiM and SS lines. Originally 200K was put aside for this effort but GIN / batch hardening work consumed most of the budget till the date. CR will be submitted once the additional scope is received for GIN stability work. The CR will include the effort estimate for ECIF Data integrity work
Overall Status: Yellow – Additional funding is required for ECIF Data Integrity work as GIN / batch hardening consumed most of the budget for the remediation activities and discovery effort for Scalability to 1-2M policies effort.
08/18– Discussed on 08/18 and decision made that none of the GIN stability effort should stop.
Path to Green –
Requested teams to provide the scope clarity on GIN Stability and high-level effort estimates by 09/04 for CR submission. CR will include the already estimated effort for ECIF Data Integrity work as well.
GIN Stability
Task-system cleanup / error reduction –
Working on most frequently failing Task error – Analysis and development efforts are in progress for the 6 task errors identified as of 07/31 and planning to deploy for 09/16 release
Observability & Monitoring –
Team has identified 43 batch flows as of 07/31 for which monitoring and observability needs to be setup.
Completed long running monitoring enablement, Retry logic fix for19 workflows. Work is in progress for remaining workflows.
  RRD Redesign –
Development effort is in progress. Planning for Sep release
GIN / REN / ECIF data integrity –
Solution Approach completed by Ronda.
Solution Approach review completed and requested line level estimations for the effort
Submitted Intake for ECIF consultation
Line level estimates received from MiM and SS. Work has been kicked off for MiM.
Worked on phased delivery proposal approach rather than waiting to deploy the entire solution in December due to the implementation risks associated with a year-end deployment, including release freeze periods and limited resource availability during the holiday season. Lines are reviewing the below proposal.
  Convert CEM to Java Golden Path – MiM – October Release
  Migrate MQ to Kafka event streams for Agreement notifications - no new functionality – MiM – Novemeber release
  Migrate MQ to Kafka event streams for Party notifications – no new functionality – MiM - November/December release
  Add Party notification event stream – consume ECN changes & registration email (January) – MiM – January release
  Modify GIN Resource APIs to enable ECN update (January) (dependent on V2 to V5) – SS – January release
Analysis is in progress by MiM team
Project Manager : Dinesh
OpEx Business Lead: Gary Wilson

## Slide 10: GIN Long Term Stability – Scalability to 1.5-2M policies
Status Key | C | Completed |  | On-Schedule |  | Major Issues |  | Some Issues | NS | Not Started
Status Date: | 8/28/2026
2026 Budget | YTD Actuals | Remaining 2026 Forecast | Current YE Forecast | Total Budget
$463,000 | $0 | $463,000 | $463,000 | $463,000
Overall | Scope | Schedule | Financials
Target Delivery: | TBD
Milestone | Status | Due Date | Notes
Capacity / scalability to 1-2M policies – Discovery Phase | C | 07/31/26 | Exavalu team completed Discovery Phase.
Detailed Project plan and Solution Approach document | C | 08/31/26 | Internal team review is completed. Will review with Sastry and Ronda this week.
Review of Solution Approach and project Plan |  | 08/31/26 | Reviewed with Sastry and Ronda. Working on the feedback
Snowflake Infra Upgrade- KPI Queries | C | 08/24/26 | 
RS2SNF-Architecture and LLD |  | 09/02/26 | Work is in progress
GIN - Phase 1 solutions |  | 08/31/26 | Work is in progress
GIN - Phase 2 Long Term Solutions identification |  | 10/31/26 | Work is in progress
Implementation Planned for finalized use cases | NS | 11/30/26 | 
Critical Risks/Issues | Status | Target Date | Resolution / Mitigation
Lack of overall project QE lead |  |  | Requested Amy for QE lead who will work on to create the master test strategy which is very critical to success of this project
Status:
Overall Status: The Discovery work is completed and Now the 463K funding is approved, the team is working on scoping the solution approach and detailing tasks for development and testing
Work in progress activities -
GIN -
Deploy Phase 1 Quick Fix changes in train2 and perform dry run test.
Deploy changes with sunset jobs removal in train2 and validate data after daily cycle run.
Proceed with planned Phase 2 activity
  Policy Summary Stats Action - determine long running queries.
  Orange Job - ECIF Report VHL Cancellations and Failed Policies - Analyze on Multi-threading feasibility.
Snowflake DW
Complete the LLD and solutioning document for Redshift to Snowflake. Review with Amit/Visali.
Create python scripts to test for few sample tables to validate the incremental flows with test scenarios.
Project Manager : Dinesh
OpEx Business Lead: Gary Wilson

## Slide 11: GIN – API V2 to V5 upgrade
Status Key | C | Completed |  | On-Schedule |  | Major Issues |  | Some Issues | NS | Not Started
Status Date: | 8/28/2026
2026 Budget | YTD Actuals | Remaining 2026 Forecast | Current YE Forecast | Total Budget
$350,000 | $0 | $349,839.29 | $349,839.29 | $350,000
Overall | Scope | Schedule | Financials
Target Delivery: | TBD
Milestone | Status | Due Date | Notes
Detailed Project plan |  | 08/31/26 | Work is in progress. Team is evaluating the options for Phased delivery approach to enable monthly releases.
Review of Solution Approach and project plan |  | 08/31/26 09/04/26 | Not started.
Critical Risks/Issues | Status | Target Date | Resolution / Mitigation
Single December deployment carries high implementation risk |  | 09/04/26 | Evaluate and implement a phased delivery approach with monthly releases.
End-to-end testing coordination challenges |  | 09/04/26 | Develop an integrated E2E testing plan covering all impacted systems. Begin integration testing as components become available rather than waiting for complete development.
Resource constraints during critical delivery phases due to holiday season |  | 09/04/26 | Validate resource plans for development and testing phases. Identify backup resources and establish contingency coverage for critical roles.
This project GIN API V5 Upgrade is to migrate the last customer-facing GIN APIs – Accounts, Claims, Members from V2 (SOAP/RPC) to V5 (REST).
Overall Project Status: Yellow
The project remains in Yellow status because of timeline uncertainty. Immediate onboarding of API development resources to the SS workstream is required to initiate DDIT and mitigate schedule risks.
Requested team to evaluate the options for a phased delivery approach rather than waiting to deploy the entire solution in December due to the implementation risks associated with a year-end deployment, including release freeze periods and limited resource availability during the holiday season
Path to Green –
The project can be moved to Green when:
API resources are onboarded and DDIT is underway.
A phased delivery plan is approved and baselined.
Cross-system dependencies are committed and tracked.
End-to-end testing dates are confirmed across Portal, QEC, P.E.T, SF, and IR.
Delivery milestones have high confidence with no critical unresolved risks.
Work in progress activities -
Creation of the Project plan is in progress
Resources are being identified and will be allocated this week –
  Core resources are identified.
  2 NW offshore QE onboarding is in progress for SS line
  1 Exavalu Offshore dev onboarding is in progress
  Jagan is looking internally for 1 API Dev
SS Changes –
  Analysis on Claims resource APIs
    Get Claims Details By PolicyNumber - In progress
    Get Claim By Id - Not Started
    Get Claims By PolicyNumber – Not Started
    LossNotices – DDIT is in progress
MM Changes –
  Analysis in is progress on Claims Resource APIs
Project Manager : Dinesh
OpEx Business Lead: Gary Wilson

## Slide 12: TaiLWIND Flagship AI
Upcoming Milestone | Status | Due Date | Notes
Email Ingestion |  | 9/17 | Specs development complete. DDIT moving into Sept 9/10
Document Submission Service |  | 8/31 | Targeting Dark Launch 8/28
(Tailwind Agent)-Lookup Tool, Extraction | C | 8/31 | Completed
Testing (End to End) kick-off |  | 10/1 | Dependent on all teams' code availability (refined on 8/27)
Go-Live |  | 11/11 | 
Status Date: | 8/28/2026
Overall | Scope | Schedule | Financials
Target Delivery: | 11/11/2026
Risks, Issues, & Dependencies | Status | Target Date | Resolution / Mitigation Owner
R: SS, AT, eCIF, DMX, and MiM team capacity in achieving November release commitments. |  | 10/1 | Owner: Dan/Amy Mitigation Plan – Work with POs to prioritize.
Full staffing pending – Requisition made for new PO for AT line owned by AVP OpEx. Working to acquire 1 Software Engineers to enable future work. |  | NA | Resolution: Leslie (PO) Action - REQ has been opened for this.
iText solution approach needs licenses/contract this is being finalized. Timeline for resolution undefined at this point. | C | 8/31 | Owner: Natalie/Anurag Action – Replaced with PDF Box – Completed
Operational Metrics – Leadership, Model, Operational |  | 9/30 | Owner: Dan/Natalie/Melissa/Ying Action – Team to define needs
This Week – Accomplishments/Value Delivered:
The Document Submission CI pipeline release 1 underway (Multiple releases expected – build/test cycle)
Development on Email Ingestion 70% completed development
The Document Transformation Service design specification completed. Development underway.
TaiLWIND is validated as the top priority across dependencies.
EAO completed focused knowledge sharing on page-level extraction, JSON normalization, line-item treatment, confidence scoring, and manual-review considerations, including identification of a duplicate-page classification defect.​
EAO advanced alignment with NF Pet and Tailwind on the ground-truth workflow, cross-channel comparison, and production ownership, while reinforcing the value of EAO’s capability for future internal use cases.​
Overall Status: Yellow
Engagement with the REN, GIN, MiM, and Portal teams continued to advance integration planning. The status remains Yellow due to potential risks associated with securing timely alignment and support for Phase1 delivery. Integration scope has been handed off to Scrum Sharks, GOP, AT, and MIM all have provided initial estimates. Significant progress has been made on prioritization, finalized scope, revised estimates, and timelines is nearing completion.
EAO is building on the 8/7 benchmark and moving toward a more consistent, production-relevant evaluation by aligning partner outputs, validating ground truth and matching logic, and advancing fax/mail analysis​
2026 Budget | YTD Actuals | Remaining 2026 Forecast | Total Actuals +Fcst
$1,500,000 | $666,489 | $859,818 | $1,526,307
Next 1–2 Weeks Deliverables:
Continue progress on Email ingestion build, Document submission service, and infrastructure build for existing work.
Support of work transferred to GIN/REN/MIM/AT/ECIF – Beginning build, Validating need for Tailblazers support.
Finalize initial KPIs for Phase 1.
Apply the agreed normalization rules, correct the duplicate-page classification, and complete the remaining multi-page comparison work for the shared benchmark.​
Continue fax/mail analysis, align partner JSON and ground-truth inputs, and prepare the next channel comparison and leadership show-and-tell​
Status Key | C | Completed |  | On-Schedule |  | Major Issues |  | Some Issues | NS | Not Started
Key Learnings/Insights:
Need continued monitoring of DDIT token usage for Doodle Poodle line.
AWS (Claude) remains the fastest phase-1 path, while open-source options still matter for longer-term cost and flexibility.
Architecture Solution should be highly flexible to accommodate everchanging agentic solution.
Maturing understanding of metrics and KPIs for build and operations.
Success now depends less on extraction execution and more on aligning business scoring rules and field definitions to ensure meaningful benchmark outcomes.
Infrastructure challenges – Frequent progress depends on access and remediation owned by other teams impacting throughput.
Tailwind intentionally preserves page-level and low-confidence extracts; downstream agents reconcile duplicate or conflicting records later in the workflow.​
Apples-to-apples comparison requires explicit normalization across pages, line items, entities, fees, duplicates, and confidence levels, with conservative invoice-to-claim matching for ambiguous cases.​
Project Manager : Shilpa K
OpEx Business Lead: Dan Clausing

## Slide 13: Green Projects

## Slide 14: PPT: Pet REN2GIN Policy Migration
Status Key | C | Completed |  | On-Schedule |  | Major Issues |  | Some Issues | NS | Not Started
Status Date: | 8/28/2026
2026 Budget | YTD Actuals | Remaining 2026 Forecast | Total Actuals +Fcst | Total Budget
$800,000 | $436,842 | $407,037 | $843,880 | $800,000
Overall | Scope | Schedule | Financials
Target Delivery: | Manual Migration – TBD
Milestone | Status | Due Date | Notes
WP to MPI Migration Wave 14 (PA) | C | 8/12 | 8/12 – Production Deployment Completed successfully.
MPP to MPP Choice Wave 15 (MD) Migration | C | 8/12 | 8/12 – Production Deployment Completed successfully.
Manual Migration SOW execution |  | 8/28 9/4 | SOW is finalized
Manual Migration DDIT completion | NS | 11/30 | 
Manual Migration – Stabilization/E2E | NS | 12/30 | 
UAT | NS | 1/31 | 
Go-Live | NS | 2/10 | 
Warranty Support | NS | 3/10 | 
Critical Risks/Issues | Status | Target Date | Resolution / Mitigation
Overall Project Status: Green
Project status is upgraded to Green as the team has finalized SOW and timeline is finalized for Manual Migration.
Highlights:
  Manual Migration –
  The SOW is revised based on the inputs provided and is finalized
Next Steps:
SOW finalization 8/28 – Complete
Schedule/Cost alignment for Manual Migration 9/30
Policy Migration:
Project Manager : Shilpa K
OpEx Business Lead: Gary W
Product | States Deployed | Policies Migrated | Original Premium Migrated | % Complete
MM to MPI | CA | 66,564 | $58.65M | 99.7%
MPP to MPPC | 49 | 535,678 | $427,923 | 87.2%
WP to MPI | 26 | 38,119 | $81M | 72.4
Total |  | 640,361 | $568,164 | 87.3

## Slide 15: PPT: Pet Major Medical On GIN
Status Key | C | Completed |  | On-Schedule |  | Major Issues |  | Some Issues | NS | Not Started
Status Date: | 8/28/2026
2026 Budget | YTD Actuals | Remaining 2026 Forecast | Total Actuals +Fcst | Total Budget
$840,000 | $117,650 | $761,646 | $879,296 | $840,000
Overall | Scope | Schedule | Financials
Target Delivery: | 2/10/2027
Milestone | Status | Due Date | Notes
DDIT |  | 12/2/26 | 
E2E Testing | NS | 1/6/27 | 
UAT Sign-off / Code Freeze | NS | 1/29/27 | 
Final Regression | NS | 2/3/27 | 
Staging Validations | NS | 2/9/27 | 
Production Deployment | NS | 2/10/27 | 
Warranty Support | NS | 3/31/27 | 
Critical Risks/Issues | Status | Target Date | Resolution / Mitigation
AT line has raised capacity risk to support Feb-27 timeline |  | 11/30 | Mitigation - Sequencing the work from highest priority to lowest priority.
MiM Capacity issues and Commitment to Feb-27 release |  | 11/30 | Mitigation – Prioritization, Demand/Capacity Review and other options
Overall Project Status: Green
Project status is upgraded from Yellow to Green based on the commitment shared by MiM. The team will continue to monitor capacity/prioritization and other risks to ensure the alignment to Feb-2027 timeline
Highlights:
MiM commitment received based on the the availability of a second developer for the Partnership API workstream.
FinTech and Controllership estimates received.
Refinement/DDIT is in-progress by the lines
Pawroll Rangers Impact assessment working session was scheduled on 8/11.
Schedule impact in-progress for approved change request to include Z160/ changes for Major Medical.
Next Steps:
Refinement completion by the impacted lines.
DDIT Progress
Project Manager : Shilpa K​
OpEx Business Lead: Gary W

## Slide 16
Status Key | C | Completed |  | On-Schedule |  | Major Issues |  | Some Issues | NS | Not Started
Status Date: | 8/28/2026
2026 Budget | YTD Actuals | Remaining 2026 Forecast | Total Actuals +Fcst | Original Budget
$250,0000 | 0 | $250,000 | $520,000 | $520,000
Overall | Scope | Schedule | Financials
Target Delivery: | Q2 2017
Milestone | Status | Due Date | Notes
Business Requirement |  | 9/4 | 
ITS SOW | C | 8/28 | 
Discovery Completion | NS | 9/30 | 
Production Deployment | NS | 3/10 | 
Critical Risks/Issues | Status | Target Date | Resolution / Mitigation
PPT: Major Medical to Major Medical Migration Capability(Non-CA)
Project Manager : Shilpa
OpEx Business Lead: Gary
Overall Project Status: Green
Project status is upgraded to Green as the SOW is finalized and the schedule is aligned to March-2027.
The team will kick-off the discovery with ITS starting this week.
Highlights:
ITS SOW is finalized and scheduled aligned to March-2027
Project team finalized
Next Steps:
Discovery Kick-off with ITS
Finalize Project team structure.
Milestone Plan Finalization

## Slide 17: PPT: NY and Unapproved States Product Build
Status Key | C | Completed |  | On-Schedule |  | Major Issues |  | Some Issues | NS | Not Started
Status Date: | 8/26/2026
2026 Budget | YTD Actuals | Remaining 2026 Forecast | Total Actuals +Fcst | Total Budget
$267,000 | 0 | $267,000 | $267,000 | $267,000
Overall | Scope | Schedule | Financials
Target Delivery: | TBD
Milestone | Status | Due Date | Notes
Procurement Intake Request | C | 8/10/26 | 
SOW (Draft) |  | 9/11/2026 | 
Final SOW | NS | TBD | 
Staff Project team | NS | TBD | 
Critical Risks/Issues | Status | Target Date | Resolution / Mitigation
Potential underspend of the $267K budget this year due to resource constraints and delays in finalizing the SOW. |  | 9/30/26 | Procurement is engaging Cognizant to determine the next steps required to start the project.
Overall Project Status: The team received an additional $167K in funding to accelerate this initiative. A procurement intake request submitted to begin engaging Cognizant and initiate project planning. Meeting is scheduled with Cognizant this week. Update: Ali and Gary met with Cognizant. Expecting to receive the draft by 9/11.
Project Manager : Ali (Interim)
OpEx Business Lead: Gary W

## Slide 18: MPI Underwriting Optimization MVP1 Increase new business writings by simplifying point-of-sale underwriting and accelerating rule-based decisions
Status Key | C | Completed |  | On-Schedule |  | Major Issues |  | Some Issues | NS | Not Started
Status Date: | 8/28/2026
2026 Budget | YTD Actuals | Remaining 2026 Forecast | Current YE Forecast | Total Estimate
$1,120,000 | $191,445 | $925,157 | $1,116,603 | $1,116,603
Overall | Scope | Schedule | Financials
Target Delivery: | 10/14/2026
Milestone | Status | Due Date | Notes
MVP1 DDIT Start | C | 6/25 | 
MVP1 DDIT start - complete |  | 6/24- 9/2 | 
MVP1 E2E | NS | 9/3 -9/15 | 
MVP1 Business UAT/Sign off Complete | NS | 9/16 -10/2 | 
Implementation Plan Review | NS | 10/3 | 
MVP1 Go No/Go | NS | 10/3 | 
Stage | NS | 10/3 | 
Implementation | NS | 10/14 | 
Critical Risks/Issues | Status | Target Date | Resolution / Mitigation
Dependencies / Risks MiM and PR are dependent on SS to remove the UW question and add two new questions. EW is dependent on MiM to remove the spay/neuter backend logic. AT is dependent on SS to add the two new questions. Risk: There is a delivery risk for DDIT to complete implementation across all lines by 8/20 if SS does not complete the required question changes by 8/5. Any delay in SS delivery will impact downstream work for MiM, PR, and AT, potentially putting the 8/20 completion target at risk. | C | 8/5 | Resolution: SS to complete the UW question removal and addition of two new questions by 8/5, enabling MiM, PR, and AT to proceed without impacting the overall timeline. Mitigation: Track SS progress through weekly checkpoints and escalate any risk to the 8/5 milestone immediately to protect DDIT's 8/20 delivery target across all lines.
Status:
During the week, the project team finalized preparations for End-to-End (E2E) testing and received the required mockups to support testing and business validation activities. The Steering Committee approved the Change Request (CR) to remove one of the business questions, and the impacted lines are engaged to implement the change without affecting the project timeline. The approved CR has an estimated cost of $7,000, which will be funded through project contingency, resulting in no impact to the overall project budget.
Highlights:
Received Steering Committee approval for Change Request to remove one business question.
Confirmed implementation approach with impacted lines, with no impact to the project schedule.
Received required mockups to support E2E testing and stakeholder review activities.
Approved CR cost of $7,000 will be funded through project contingency with no impact to the overall project budget.
Next Steps
Begin and execute End-to-End (E2E) testing (Sep 3 – Sep 15).
Monitor implementation of approved Change Request and validate outcomes during testing.
Continue business stakeholder operational readiness and customer support preparation activities.
Prepare for User Acceptance Testing (UAT) scheduled for Sep 16 – Oct 2.
Project Manager : Lalitha Kumar
OpEx Business Lead: Sarah Andrews
Notes: Chuck, Tamil, Victor

## Slide 19: MPI Underwriting Optimization MVP 2 Increase new business writings by simplifying point-of-sale underwriting and accelerating rule-based decisions
Status Key | C | Completed |  | On-Schedule |  | Major Issues |  | Some Issues | NS | Not Started
Status Date: | 8/28/2026
2026 Budget | YTD Actuals | Remaining 2026 Forecast | Current YE Forecast | Total Estimate
$1,120,000 | $191,445 | $925,157 | $1,116,603 | $1,116,603
Overall | Scope | Schedule | Financials
Target Delivery: | 11/11/2026
Milestone | Status | Due Date | Notes
MVP2 DDIT start - complete |  | 7/9-9/30 | E2E dependency with all other lines is at risk for target Nov release
MVP2 E2E | NS | 10/1- 10/14 | 
MVP2 Business UAT/Sign off Complete | NS | 10/15-10/30 | 
MVP2 Go No/Go | NS | 11/2 | 
MVP2 Delivery to Production | NS | 11/11 | 
Critical Risks/Issues | Status | Target Date | Resolution / Mitigation
Open Enrollment Timing Risk: The proposed November 11 release occurs during peak Open Enrollment, creating elevated risks for production support, operational readiness, issue resolution, and potential customer impact should post-release issues arise. Cross-Team Dependency Risk: MVP2 delivery is dependent on Scrum Sharks completing the Rules Engine/API functionality required by Epic Winners. Delays in API delivery could impact integration, end-to-end testing, and overall release readiness. | C | 8/30 | Complete Open Enrollment impact assessment Obtain Steering Committee approval, execute enhanced readiness and hypercare plans Reassess the release window if risk levels exceed acceptable thresholds.
Project Manager : Lalitha Kumar
OpEx Business Lead: Sarah Andrews
Status MVP2 continues to progress according to plan, with development and integration activities tracking toward the November 11 implementation date. During the week, the project team reviewed the November 11 release risk assessment with leadership and received Steering Committee approval to proceed with the target go-live date. The lines are actively executing Development and Integration Testing (DDIT) activities and remain on track to begin End-to-End (E2E) testing on October 1.
Highlights
Reviewed November 11 implementation risk assessment with project stakeholders and Steering Committee.
Received Steering Committee approval to proceed with the November 11 MVP2 go-live date on August 27.
Lines are actively executing DDIT activities and progressing without significant blockers.
Cross-team coordination and dependency management continue to support readiness for E2E testing.
Next Steps
Continue DDIT execution and defect resolution activities through September.
Complete Master Test Strategy with stakeholders by September 11
Complete remaining MVP2 design, development, and integration work by September 30.
Kick off End-to-End (E2E) testing on October 1.
Conduct Show & Tell sessions prior to E2E testing.
Begin User Acceptance Testing (UAT) on October 15.
Continue release planning, deployment readiness, and operational readiness activities in preparation for the November 11 implementation.

## Slide 20: MPI Underwriting Optimization MVP 3 Increase new business writings by simplifying point-of-sale underwriting and accelerating rule-based decisions.
Status Key | C | Completed |  | On-Schedule |  | Major Issues |  | Some Issues | NS | Not Started
Status Date: | 8/28/2026
2026 Budget | YTD Actuals | Remaining 2026 Forecast | Current YE Forecast | Total Estimate
$1,120,000 | $191,445 | $925,157 | $1,116,603 | $1,116,603
Overall | Scope | Schedule | Financials
Target Delivery: | Feb 2027
Milestone | Status | Due Date | Notes
MVP3 DDIT start - complete |  | 8/13 – 12/24 | 
MVP3 E2E | NS | 12/28-1/10/27 | 
MVP3 Business UAT/Sign off Complete | NS | 1/11/27 – 1/30/27 | 
MVP3 Go No/Go | NS | 2/2/27 | 
MVP3 Delivery to Production | NS | 2/17/27 | 
Critical Risks/Issues | Status | Target Date | Resolution / Mitigation
Funding Risk: Current MVP3 budget does not include all test execution and implementation activities required to support enterprise release readiness. An additional $150K is needed to complete Integration Testing, E2E, UAT, Regression, Performance, Security Testing, and Implementation activities. Schedule Risk: MVP3 readiness is dependent upon securing both funding approval and leadership alignment on the February 2027 target date. Delays in either approval may impact planning, testing timelines, and release readiness. |  | 8/30 9/30 | Complete Open Enrollment impact assessment Obtain Steering Committee timeline and 2027 cost approval Execute enhanced readiness and hypercare plans Reassess the release window if risk levels exceed acceptable thresholds.
Project Manager : Lalitha Kumar
OpEx Business Lead: Sarah Andrews
Status MVP3 delivery activities continue to progress as planned. During the week, Epic Winners continued refining and finalizing Jira stories to ensure delivery scope is fully defined and ready for execution. In parallel, the lines are actively working through Development and Integration Testing (DDIT) activities, with teams focused on validating functionality, and preparing for downstream testing milestones. Planning, dependency management, and cross-team coordination remain on track in support of the February 2027 production target.
Highlights
Epic owners are finalizing backlog refinement and Jira story definition activities to support MVP3 delivery.
Lines are actively executing DDIT activities and progressing through.
Business and technology teams continue alignment on MVP3 scope, architecture, and delivery approach.
Cross-team dependency management and release planning activities remain on track for the February 2027 implementation target.
Next Steps
Obtain Steering Committee approval for the additional $150K in 2027 funding to support testing and implementation activities.
Complete remaining DDIT activities and address identified defects.
Finalize release sequencing and confirm cross-team dependency commitments.
Complete Master Test Strategy alignment and confirm testing responsibilities across all teams.
Continue architecture, design, development, and dependency management activities.
Finalize integrated testing and implementation plans to support MVP3 release readiness.
Prepare for upcoming integration and end-to-end testing activities in support of the February 2027 release.

## Slide 21: MPPC to MPI Conversion at Notice of Cancel Deliver the ability to offer cancelled MPPC policies conversion to MPI upon termination of working with the employer
Status Key | C | Completed |  | On-Schedule |  | Major Issues |  | Some Issues | NS | Not Started
Status Date: | 8/28/2026
2026 Budget | YTD Actuals | Remaining 2026 Forecast | Current YE Forecast | Total Estimate
880,000 | $169,884 | $707,038 | $876,922 | $876,922
Overall | Scope | Schedule | Financials
Target Delivery: | 12/09/2026
Milestone | Status | Due Date | Notes
DDIT start -end |  | 7/2 – 10/28 | 
MVP2 E2E sign off start -end | NS | 10/29-11/11 | 
MVP2 Business UAT/Sign off Complete start - end | NS | 11/12-11/27 | 
MVP2 Go No/Go | NS | 11/30 | 
MVP2 Delivery to Production | NS | 12/9 | 
Critical Risks/Issues | Status | Target Date | Resolution / Mitigation
Analyze This (AT) is dependent on Scrum Sharks (SS) to deliver the GIN table updates required for RRD processing. Pet Rocks (PR) and Epic Winners (EW) are dependent on Monkees in the Middle (MiM) to deliver filter, map, and update request functionality, including Origin Code and MPPC Policy ID handling. Monkees in the Middle (MiM) is dependent on Scrum Sharks (SS) to publish the final MPPC cancellation criteria required for design and development. Delays in any of the above dependencies may impact DDIT completion, integration testing, and December release readiness. | C | 7/16 7/31 8/27 | AT ← SS (GIN Table Updates) Mitigation: Prioritize GIN table delivery, conduct weekly dependency reviews, and provide table structures early for parallel development. Contingency: Use mock/stub data for development and initial testing until final updates are available. PR/EW ← MiM (Filter, Map, Update Request Functionality) Mitigation: Finalize interface specifications early and deliver functionality incrementally. Contingency: Use mock APIs and sample payloads to continue development and integration testing. MiM ← SS (MPPC Cancellation Criteria) Mitigation: Accelerate business decisions and align regularly on requirements. Contingency: Proceed with agreed interim assumptions and externalize rules to minimize rework. Program-Level Mitigation: Weekly critical-path reviews, dependency tracking, and early integration testing as components become available. Contingency: Reprioritize scope, add delivery capacity, and evaluate phased delivery if dependency delays threaten the December 9 release.
Project Manager : Lalitha Kumar
OpEx Business Lead: Gary Wilson
Status​
The MPPC to MPI project continues to make steady progress, with teams aligned on a revised technical solution following completion of the MPPC to MPI impact assessment. During the week, business and technology teams confirmed the go-forward design approach, significantly reducing solution complexity by leveraging existing cancellation reason codes and eliminating the need for new eligibility flags and RRD integration changes. Development activities continue across workstreams while teams assess release timing options, focused on reducing implementation risk and improving testing and stabilization opportunities.​
​
Highlights​
Completed cross-team impact assessment and confirmed the new technical solution design for MPPC to MPI.​
Confirmed Previous Policy Number will be passed through the integration flow and used to identify continuance policies.​
Eliminated the need for a new MPI Offer Eligibility flag by leveraging existing cancellation reason codes and current XML fields.​
Removed RRD file modification requirements, reducing overall scope, complexity, and downstream impacts.​
Validated that the December 9 release remains technically achievable if no additional changes are introduced.​
Leadership initiated evaluation of alternative deployment windows, with February currently emerging as the preferred release option due to year-end operational and support risks.​
​
Next Steps​
Collect final effort estimates, timeline impacts, and cost assessments from all impacted teams.​
Validate the final implementation approach for Previous Policy Number handling across PPAPI, MIM, Epic Winners, and GIN.​
Evaluate January, February, and phased deployment alternatives and prepare leadership recommendations.​
Determine feasibility of dark launch and feature-shelving options where applicable.​
Continue DDIT execution and dependency management activities across all workstreams.​
Prepare Steering Committee materials summarizing design decisions, release options, timeline impacts, and recommended deployment strategy.​
Finalize implementation timeline and release strategy following leadership review.​
Notes: Karthik S

## Slide 22: PEC Product & Underwriting Enhancements
Status Key | C | Completed |  | On-Schedule |  | Major Issues |  | Some Issues | NS | Not Started
Status Date: | 08/28/2026
2026 Budget | YTD Actuals | Remaining 2026 Forecast | Current YE Forecast | Total Budget
$100,000 | 0 | $96,874 | $96,874 | $100,000
Overall | Scope | Schedule | Financials
Target Delivery: | 11/11/26
Milestone | Status | Due Date | Notes
Role Level Resource Commitment Received | C | 8/13 | 
EPIC Prioritization by Product Owners | C | 8/13 | 
Project Schedule/Timeline Draft | C | 8/13 | 
Story creation and Grooming completed | C | 8/19 | 
DDIT Complete | NS | 9/30 | 
E2E Complete | NS | 10/14 | 
UAT Complete | NS | 10/30 | 
Production Release | NS | 11/11 | 
Critical Risks/Issues | Status | Target Date | Resolution / Mitigation
Status Update
Overall Status: Green
Work is aligned, committed, and on schedule for November release. DDIT continuing into the current sprint. Project is at 50% complete.
Accomplishments:
DDIT (SS) Sprint 1 completed
Next Steps:
Continued DDIT (ScrumSharks)
Project Manager : Kinney Barbour
OpEx Business : Gary Wilson

## Slide 23: Enhance Multi Denial Code Claims Z160/Z151
Status Key | C | Completed |  | On-Schedule |  | Major Issues |  | Some Issues | NS | Not Started
Status Date: | 08/28/2026
2026 Budget | YTD Actuals | Remaining 2026 Forecast | Current YE Forecast | Total Budget
$114,000 | 14,527 | $96,834 | $111,360 | $114,000
Overall | Scope | Schedule | Financials
Target Delivery: | 11/11/26
Milestone | Status | Due Date | Notes
Story creation & grooming completed | C | 8/5 | 
DDIT Complete (SS) |  | 9/30 | MPPC, MPI, WP in process
DDIT Complete (AT) | NS | 9/30 | 
E2E Testing | NS | 10/14 | 
UAT Complete | NS | 10/30 | 
Production Release | NS | 11/11 | 
Warranty Completed | NS | 12/11 | 
Critical Risks/Issues | Status | Target Date | Resolution / Mitigation
None |  |  | 
Status Update
Overall Status: Green
Development for the MPPC product began progressing as planned. ETL DEV work starting in the current sprint. Project on Schedule.
Accomplishments:
MPPC, MPI DDIT (Scrum Sharks)
MPPC ETL DDIT (AT)
Next Steps:
MPPC, MPI DDIT (Scrum Sharks)
ETL DDIT MPPC (AT)
Project Manager : Kinney Barbour
OpEx Business : Alex Suarez

## Slide 24: MPI Pricing Segmentation Sophistication
Status Key | C | Completed |  | On-Schedule |  | Major Issues |  | Some Issues | NS | Not Started
Status Date: | 08/28/2026
2026 Budget | YTD Actuals | Remaining 2026 Forecast | Current YE Forecast | Total Budget
$200,000 | 144,918 | 47,489 | 192,403 | 200,000
Overall | Scope | Schedule | Financials
Target Delivery: | 9/16/26 10/14/26
Milestone | Status | Due Date | Notes
Dev Completion (R9) | C | 8/5 | 
Stage Validation (R8) | C | 8/11 | 
Production Release (R8) | C | 8/12 | LA, VT, FL, MT, MD, GA, NH, TN states
DDIT Completion (R9) | C | 8/12 | 
E2E Completion (R9) | C | 8/19 | 
UAT Completion (R9) |  | 9/4 | 
Production Release (R9) | NS | 9/16 | NV, AK, ND States
Scope Cutoff (R10) | C | 8/26 | Approved States - RI, DC, CT
DDIT Complete (R10) | NS | 9/16 | 
Critical Risks/Issues | Status | Target Date | Resolution / Mitigation
Status Update
Overall Status: Green
R9 states (NV, AK, ND) on schedule for September 16h.
Accomplishments:
R9 E2E Completion
R10 Scope Frozen for next wave of states (RI, DC, CT)
Next Steps:
R9 States UAT Completion
R10 DDIT
Project Manager : Kinney Barbour
OpEx Business : Alex Suarez

## Slide 25: Pet Model Law Reboot Weekly Status Update
Status Key | C | Completed |  | On-Schedule |  | Major Issues |  | Some Issues | NS | Not Started
Status Date: | 08/28/2026
2026 Budget | YTD Actuals | Remaining 2026 Forecast | Current YE Forecast | Total Budget
$750,000 | $554,981.75 | $194,172.70 | $194,994.70 | $749,153.45
Overall | Scope | Schedule | Financials
Target Delivery: | 09/16/2026
Milestone | Status | Due Date | Notes
Validate and Lock business requirements | C | 1/23 | 
Obtain approval from leadership team (BDE & ITDE) | C | 1/26 | 
Provide effort estimates for all changes without new architectural solution based on Line Dev/TA designs. | C | 1/30 | 
Business requirements on open questions; Pi.com | C | 1/16 | 
Deliver end‑to‑end architectural design for the new solution. Technical design walkthrough | C | 1/30 | 
Provide L1 project estimates with high‑level scope and effort | C | 2/6 | 
Perform a line walkthrough to review processes and ensure cross‑team alignment. For line estimation | C | 1/30-2/13 | 
Complete line‑level effort estimation for all impacted changes. (L2) | C | 2/9 – 2/20 | 
Wave – 3 : DDIT activities. | C | 07/20 | 
Wave – 3 : E2E Testing | C | 07/20 | 
Wave – 3 : UAT | C | 07/31 | 
Wave – 3 : Implementation Planning | C | 08/03 - 08/05 | 
GO / No Go | C | 08/10 | 
Go Live | C | 08/12 | 
REN CR - PML Form Updates |  | 09/16 | UAT completed. Ready for prod release for 09/16
Critical Risks/Issues | Status | Target Date | Resolution / Mitigation
Status Update
Overall Status: Green
PML Reboot Wave 3 got implemented Successfully on 08/12
Highlights
Received leadership approval for Salesforce CR on 4/15
Discovery for Salesforce scope clarified and locked on 4/17
Refined PR estimate entered in Planview and line commitment logged
CR approvals in progress for PML Reboot - Add REN Form Updates
PML Reboot Wave 1 got implemented Successfully on 06/19
PML Reboot Wave 2 got implemented Successfully on 07/15
Next Steps
REN CR - PML Form Updates
DDIT – complete
UAT – Complete
Prod release – 09/16
Wave 4
Gary is working with Business teams to finalize the Wave 4 requirements
Wave 4 is planned for Nov release. Based on Gary’s discussion on requirements this week the release timelines will be confirmed.
Business requirements need to be finalized by 09/01 for teams to plan the work
Project Manager : Venkata Dinesh
OpEx Business Lead: Gary Wilson

## Slide 26
Status Key | C | Completed |  | On-Schedule |  | Major Issues |  | Some Issues | NS | Not Started
Status Date: | 08/28/2026
2026 Revised Budget | YTD Actuals | Remaining 2026 Forecast | Total Actuals +Fcst | Original Budget
2026 Revised Budget | YTD Actuals | Remaining 2026 Forecast | Total Actuals +Fcst | Original Budget
Overall | Scope | Schedule | Financials
Target Delivery: | Every Month starting July, Aug, Sep, Oct, Nov
Milestone | Status | Due Date | Notes
Critical defects PP 2 & 166 Prod deployment | C | 2/20 | 
Defects Prioritization | C | 3/6 | 
Defect AI Generated analysis | C | 3/10 | 
Revised Release Plan | C | 4/24 | 
Talend to Python Phase 1 UAT | C | 4/30 | Re-baseline due to UAT testing
Talend to Python Phase 1 Prod | C | 5/26 | 5 defects have been identified - Completed
Critical Defects | c | 6/29 | 3 defects have been planned
Wave 1 - Prod | C | 7/9 7/14 | 8 defects have been planned
Wave 2 - Prod | C | 8/20 | 25 defects have been planned
Wave 3 - Prod |  | 9/17 | 31 defects have been planned
Wave 4 - Prod |  | 10/15 | 34 defects have been planned
Wave 5 - Prod | NS | 11/12 | 26 defects have been planned
Critical Risks/Issues | Status | Target Date | Resolution / Mitigation
Overall Testing delays caused by CDC and infrastructure dependencies. CDC enablement is not built in Non-Prod and resulting in ODS data inconsistency which is affecting testing. |  | TBD | Team is having a workaround to perform the testing and not to impact the targeted release date
Status: Green
The overall project status is Green. Wave 2 has been successfully completed, with all planned objectives delivered and business signoff obtained. Throughout the release cycle, the project team effectively managed several unexpected challenges, including intermittent environment issues and temporary GitHub outages, while maintaining focus on critical delivery milestones. The team proactively resolved blockers, implemented necessary workarounds, and ensured successful execution of testing and deployment activities. As a result, Wave 2 has been deployed successfully, all key deliverables have been completed, and the project has achieved its planned outcomes. No critical issues remain that impact project objectives, and the solution is now operating as expected in production. The successful completion of Wave 2 demonstrates strong cross-functional collaboration, effective risk management, and overall delivery excellence.
Issue:
The project encountered several environmental and infrastructure-related challenges during testing and release preparation. These included intermittent issues with the Test environment, CDC refresh delays, and occasional availability issues with GIN2SNF processing agents.
Despite these challenges, the team established effective workarounds and maintained testing and deployment activities without impacting the release schedule.
Highlights:
Critical Hotfix Defects migrated to Production on 06/29
Wave 1 completed and deployed to Production on 07/14
Business signoff received for Wave 2 on 8/17
Wave 2 completed and deployed to Production on 08/19
Wave 3 defect analysis and development in progress
Wave 4 defect analysis initiated
Team successfully overcame numerous release blockers, including environment challenges and temporary GitHub service disruptions
Strong collaboration across business and technology teams enabled achievement of August release goals
Payroll Billing Defect Fixes
Delivery Leader: Rekha Kothandaraman
OpEx Business Lead: Victor Nas

## Slide 27: Refresh the Windows 2022 Server
Status Key | C | Completed |  | On-Schedule |  | Major Issues |  | Some Issues | NS | Not Started
Status Date: | 08/28/26
2026 Budget | YTD Actuals | Remaining 2026 Forecast | Current YE Forecast | Total Budget
$50,000 | $ | $ | $ | $
Overall | Scope | Schedule | Financials
Target Delivery: | 9/30/2026
Milestone | Status | Due Date | Notes
Validate and Lock business requirements | C |  | 
Obtain approval from BDE | C |  | 
Non Prod servers | C |  | All 41 non prod servers completed
MIM Production servers | C |  | 16 Production completed
Analyze this – 4 | TBD |  | 
EW | Sep 10 |  | 8 servers were planned
Technical Design | NA |  | 
1 S&I and 1 Help Desk | TBD |  | 
Non prod servers | C |  | 
Dev Ops server | C |  | 
Critical Risks/Issues | Status | Target Date | Resolution / Mitigation
Status:
Overall Status Green
Business requirements: Approved
Next Steps:
All lower environments were upgraded, and Production servers to start after Python and DCM migration as few servers were being decommissioned and getting upgraded.
Schedule provided for the Prod servers and ETA to complete all the servers is Sep 30th before open enrollment
  Target is to complete all the upgrades by end of Sep before the open enrollment starts.
  Total 26 servers to be upgraded.
  Production servers upgrade schedule to finalize.
  Meeting with teams to finalize the schedule on upgrade
  MIM team has provided schedule to upgrade target to complete by end of Aug
Project Manager : Chalam Buddha
Total servers to be upgraded | Total 71 Server need upgrade
Non Prod servers | All 41 non prod servers completed
MIM Production servers | 16 completed
Analyze this – 4 | Target to complete in Sep
EW- 8 | Target to complete in Sep
1 S&I and 1 Help Desk | TBD

## Slide 28: NW Pet: Enhancement for Commission Reporting - Internal Batch
Status Key | C | Completed |  | On-Schedule |  | Major Issues |  | Some Issues | NS | Not Started
Status Date: | 08/28/26
2026 Budget | YTD Actuals | Remaining 2026 Forecast | Current YE Forecast | Total Budget
$60,000 | $ 31,344 | $91,344 | $ | $
Overall | Scope | Schedule | Financials
Target Delivery: | 9/30/2026
Milestone | Status | Due Date | 
Validate and Lock business requirements | C |  | 
Obtain approval from BDE | C |  | 
Detail Requirements and Epic Creations | C |  | 
Deliver end‑to‑end architectural design for the new solution. | C |  | 
Provide L0 project estimates with high‑level scope and effort | C |  | 
Project kick off | 8/26 C |  | 
Technical Design | C |  | 
DDIT | NS |  | 
E2E | NS |  | 
UAT | NS |  | 
Stage Validation | NS |  | 
Critical Risks/Issues | Status | Target Date | Resolution / Mitigation
Status:
Overall Status Green
Business requirements: Approved
Next Steps:
Requirements and scope to be finalized; estimated delivery is Nov
Had discussion the Scope, need to summarize the scope with Sastry and Ronda
Had technical discussion with Tech arch on the solution and Scope. Have follow up call on 7/20 to finalize the technical design.
Scope discussion was complete and high level solution yet to come scheduled on 7/29.
Scope finalization in process.
Technical design in process Schedule from the line pending
Kick off call scheduled on Aug 26th
  Scope Finalized
Project Manager : Chalam Buddha
Scope
There were 3 reports identified which will be converted from BO to Power BI.
The underlying data from oracle also need to be moved to Snowflake
Reports to be converted are SA4070, SA4072, and SA4073

## Slide 29: 2026 GIN Updates
Status Key | C | Completed |  | On-Schedule |  | Major Issues |  | Some Issues | NS | Not Started
Status Date: | 08/28/26
2026 Budget | YTD Actuals | Remaining 2026 Forecast | Current YE Forecast | Total Budget
$60,000 | $ | $ | $ | $
Overall | Scope | Schedule | Financials
Target Delivery: | 9/30/2026
Milestone | Status | Due Date | 
Validate and Lock business requirements | C |  | 
Obtain approval from BDE | C |  | 
Detail Requirements and Epic Creations | NS |  | 
Deliver end‑to‑end architectural design for the new solution. | NS |  | 
Provide L0 project estimates with high‑level scope and effort | NS |  | 
Build project plan based online approval of estimates | NS |  | 
Technical Design | NS |  | 
DDIT | NS |  | 
E2E | NS |  | 
UAT | NS |  | 
Stage Validation | NS |  | 
Critical Risks/Issues | Status | Target Date | Resolution / Mitigation
This project is to have the upgrades from GIN to implement in Nation wide
Status:
Overall Status Green
Business requirements: Approved
Next Steps:
Requirements and scope to be finalized; estimated delivery is Nov
Follow up call scheduled on 7/30
Scope to be finalized
Schedule from the line to be finalized
Project Manager : Chalam Buddha
PO: Gary Wilson

## Slide 30: NW Pet: CPP Right to Delete and Right to access (Externally funded)
Status Key | C | Completed |  | On-Schedule |  | Major Issues |  | Some Issues | NS | Not Started
Status Date: | 08/28/26
2026 Budget | YTD Actuals | Remaining 2026 Forecast | Current YE Forecast | Total Budget
$60,000 | $ | $ | $ | $
Overall | Scope | Schedule | Financials
Target Delivery: | 9/30/2026
Milestone | Status | Due Date | 
Validate and Lock business requirements | C |  | 
Obtain approval from BDE | C |  | 
Detail Requirements and Epic Creations | C |  | 
Deliver end‑to‑end architectural design for the new solution. | NS |  | 
Provide L0 project estimates with high‑level scope and effort | NS |  | 
Build project plan based online approval of estimates | NS |  | 
Technical Design | NS |  | 
DDIT | NS |  | 
E2E | NS |  | 
UAT | NS |  | 
Stage Validation | NS |  | 
Critical Risks/Issues | Status | Target Date | Resolution / Mitigation
Status:
Overall Status Green
Business requirements: Approved
Next Steps:
Requirements and scope to be finalized; estimated delivery is Nov
Kick off call scheduled and scope and estimations pending from Line.
Technical design in process and expected to finalize by 08/21
Project Manager : Chalam Buddha

## Slide 31: NW Pet: Vulnerabilities Remediation
Status Key | C | Completed |  | On-Schedule |  | Major Issues |  | Some Issues | NS | Not Started
Status Date: | 08/28/26
2026 Budget | YTD Actuals | Remaining 2026 Forecast | Current YE Forecast | Total Budget
$ | $ | $ | $ | $
Overall | Scope | Schedule | Financials
Target Delivery: | Ongoing
Milestone | Status | Due Date | Notes
Validate and Lock business requirements | NS |  | 
Obtain approval from BDE | NS |  | 
Detail Requirements and Epic Creations | NS |  | 
Deliver end‑to‑end architectural design for the new solution. | NS |  | 
Provide L0 project estimates with high‑level scope and effort | NS |  | 
Build project plan based online approval of estimates | NS |  | 
Technical Design | NS |  | 
DDIT | NS |  | 
E2E | NS |  | 
UAT | NS |  | 
Stage Validation | NS |  | 
Critical Risks/Issues | Status | Target Date | Resolution / Mitigation
Status:
GIN Data updates to be carried to Ren in batches
Highlights:
Yet to start, scope is defined and will start till Cloud based runs are stabilized
Next Steps:
Scope technical definition and process of updating yet to start
Starting with automation and self remediation.
Vulnerabilities are at all time low with 1200 count.
Use AI agents for remediation work started
Up coming targets to have all the Past due closed by Aug 31st
Project Manager : Chalam Buddha

## Slide 32: Projects on Hold

## Slide 33: NW Pet – Convert: Move Informatica Power Center to Python
Status Key | C | Completed |  | On-Schedule |  | Major Issues |  | Some Issues | NS | Not Started
Status Date: | 08/28/26
2026 Budget | YTD Actuals | Remaining 2026 Forecast | Current YE Forecast | Total Budget
$230,000 | $214K | $142K | $356K | $356K
Overall | Scope | Schedule | Financials
Target Delivery: | Dec 15, 2026
Milestone | Status | Due Date | Notes
figma for Informatica to Python | C | 05/28 | 
fight specific for RRD-Redesign. | C | 05/28 | 
Informatica to Python GitHub link | C | 05/28 | 
Solution Approach PPT | C | 05/28 | 
PET Informatica jobs inventory | C | 05/28 | 
Official kick off | C | 07/10 | 
Build project plan based online approval of estimates |  |  | 
Technical Design | C |  | 
DDIT |  |  | 
E2E | NS |  | 
UAT | NS |  | 
Stage Validation | NS |  | 
Critical Risks/Issues | Status | Target Date | Resolution / Mitigation
The estimations from the team is not finalized yet, there could be some slippage in scope or budget after the final estimations. | C | 07/10 07/28 | Working with AT line to have estimations
Status:
Business requirements: Approved.
Highlights:
Artifacts required for the next step like estimations and kick off is ready
Official kick off to happen on 06/30.
AT line occupied with Talend to python and focused on the same
Estimations provided by team.
Work started by AT line
Will be given a logical halt after Sep release
Next Steps:
Connecting with EDO team to use any of the AI agents
Kick off scheduled on July 10th.
Estimations provided were not suitable and looking at options to leverage AI agents to reduce the estimations.
Session with EDO team done and insights shared
Team provided the estimations and in process of preparing plan.
Project Manager : Chalam Buddha

## Slide 34: Completed Projects

## Slide 35: Pet Paperless eDelivery – Status
Status Key | C | Completed |  | On-Schedule |  | Major Issues |  | Some Issues | NS | Not Started
Status Date: | 8/21/2026
2026 Budget | YTD Actuals | Remaining 2026 Forecast | Total Actuals +Fcst | Total Budget
$990,000 | $933,321 | $52,920 | $986,242 | $990,000
Overall | Scope | Schedule | Financials
Target Delivery: | MMP1: 1/26 MMP2: 6/17
Milestone | Status | Due Date | Notes
MMP1 Release | C | 1/26 | 
Publish Approved MMP2 Project/Release Schedule | C | 2/25 | 
MMP2 DDIT Complete | C | 5/8 | 
MMP2 E2E Sign off | C | 6/9 | 
MMP2 UAT/Business Sign Off Complete | C | 6/9 | 
Staging Deployment and Validation | C | 6/16 | 
Go/No-Go Meeting | C | 6/17 | 
MMP2 Release | C | 6/17 | 
One time data load | C | 7/31 | Completed
MMP2 Warranty Support | C | 7/31 | Completed
Critical Risks/Issues | Status | Target Date | Resolution / Mitigation
Overall Project Status: Green
ECIF team has reprocessed 21 errored records, and one time data load is concluded. MMP2 Warranty Support is completed and Build to Run transition is concluded.
Highlights:
MMP1:
Final dashboard refinements remain in progress, with completion of the eDelivery dashboard updates targeted for 8/28.
Following dashboard finalization and approval, adoption metrics will be distributed more broadly to stakeholders.
MMP2:
  One time data load is now complete.
  MMP2 Warranty Support is completed.
  Build to Run transition has been concluded.
Next Steps:
Fix by ECIF and Titans for issue - Applicant is unable to submit a new application within three minutes of a previous submission.
  Capacity and delivery hours have been approved by ECIF, and the work is expected to begin in late August with a target completion of early October.
eDelivery Dashboard updates and review.
Project Manager : Shilpa K
OpEx Business Lead: Kelly Heitmann

## Slide 36: Non-Insurance Bundle v1 (Portfolio ID: 1024485) Providing our VB partners with additional non-insurance options
Status Key | C | Completed |  | On-Schedule |  | Major Issues |  | Some Issues | NS | Not Started
Status Date: | 8/10/2026
2026 Budget | YTD Actuals | Remaining 2026 Forecast | Current YE Forecast | Total Budget
$273K | $164,899 | $108K | $273K | $273K
Overall | Scope | Schedule | Financials
Target Delivery: | 7/15/26
Milestone | Status | Due Date | Notes
Received HLA/Architecture assessment | C | 1/23 | Document complete
Alignment of scope/requirements (HLA) with BDE/BL | C | 2/26 | Leslie approved on 2/26/26
Detailed Requirements/Epics creation | C | 3/13 3/27 | Surekha (TA) to deliver; Nidia is meeting with Surekha on 2/11 to support Epics creation.
SOW/Vendor sign-off | C | 2/13 3/13 | Contract is with procurement as of 3/13 and finalizing signatures
Solution Approach (Tech) | C | 2/27 | 
Master Test Strategy (MTS) | C | 2/223/27 | Draft version is ready based on the new requirement change
Line Estimate based on the requirements change of replacing PRC Bot | C | 4/3 | 
Development (DDIT) | C | 5/27 6/24 | Team is prioritizing the DDIT to complete. However, this does not affect the schedule timeline. Updated schedule
E2E testing | C | 6/25- 7/8 | E2E completed for EW line. Received file from Firstvet and AT line is proceeding on the test validation
UAT testing | C | 7/8 | EW line received UAT sign Off and AT line working with Business
Deploy and staging | C | 7/9-7/14 | EW line will start the staging process for code deployment
Production Release | C | 7/15 | 
Critical Risks/Issues | Status | Target Date | Resolution / Mitigation
Risk: If consumers choose not to share data, they will be unable to complete the purchase; from the NW side we will only see a lead sent and will have no visibility into why the funnel dropped on the FV side. | C | TBD | Unless FV sends additional fields, our systems cannot capture this reason—creating a risk that reporting deliverables (David Lee’s team) are based on data that does not exist.
Due to the current security event to secure MPIQEC activity the resources from EW are being pulled in to support it. | C | 6/24 | EW is planning to complete the DDIT as scheduled on time for 6/24.
Status: Overall Status GREEN
Line Estimates received; budget approval in progress.
  Original effort was estimated at $140K and new estimates are at $273K
    Scope has not changed; test automation 332 hours
    HLA has not been modified and has been broken down into detailed requirements
Critical‑path milestones:.
  Reporting development is in progress and will be completed by August 12| Owner: David Lee
Highlights:
Project went live in production successfully. Test files received from First Vet was validated successfully..
Reporting will be completed after July 15th as it does not affect the product development.
Next Steps:
Reporting team to confirm dashboard and complete development.
Project Manager : Rekha Kothandaraman
OpEx Business Lead: Nidia Gudino

## Slide 37: Data Center Production Migration
Status Key | C | Completed |  | On-Schedule |  | Major Issues |  | Some Issues | NS | Not Started
Status Date: | 08/21/2026
2026 Budget | YTD Actuals | Remaining 2026 Forecast | Current YE Forecast | Total Budget
 |  |  |  | N/A
Overall | Scope | Schedule | Financials
Target Delivery: | 7/24/2026 (Cutover) 8/17/2026 (Retirement)
Milestone | Status | Due Date | Notes
Production Cutover | C | 7/24 | 
Warranty Completed | C | 8/7 | 4 outstanding defects remaining.
Dallas Retirement Completed | C | 8/13 | 
Irvine Retirement Completed | C | 8/17 | 
Project Retrospective | C | 8/21 | 
Critical Risks/Issues | Status | Target Date | Resolution / Mitigation
Status Update
Overall Status: Green
The DCM Migration cutover has implemented on 7/24 successfully. Physical Server Retirement scheduled to complete on 8/17. On Schedule
Highlights:
Data Center Physical Retirement
  Dallas: 8/10 – 8/13 (Completed)
  Irvine: 8/13 – 8/17
Four Warranty defects remain outstanding and are being actively addressed.
Next Steps:
Project Retrospective
Project Manager : Kinney Barbour
OpEx Business : Melissa Morris

## Slide 38: NW Pet - Update Legacy Portal Interface to UAV3 - CHG0033774 - Deployed
Status Key | C | Completed |  | On-Schedule |  | Major Issues |  | Some Issues | NS | Not Started
Status Date: | 08/10/26
2026 Budget | YTD Actuals | Remaining 2026 Forecast | Current YE Forecast | Total Budget
$67,200 | $34,673 | $20K | $20K | $67K
Overall | Scope | Schedule | Financials
Target Delivery: | May 14 2026 May 20 2026 Aug 5
Milestone | Status | Due Date | Notes
Scope and Kick off | C |  | 
Design Doc | C |  | Incorporated BDE feedback
Detailed Plan | C |  | Scott (TA) to deliver; Nidia met with Scott on 1/30 to support Epic creations.
Dev & Test | C |  | Josh shared with IT teams on 2/23
UNAM Regression testing | C |  | Line estimates are being received
E2E | C |  | 
UAT | NA |  | 
Stage Validation | C |  | This failed after all the testing is complete
Critical Risks/Issues | Status | Target Date | Resolution / Mitigation
During final testing in staging, the connectivity failed and didn’t pass testing as the APIs failed to connect in the back end | C | 6/30 | API issues, Payment issues were resolved
There is one open issue where NW Mobile app not able to use SSO for login | C | 7/24 | Portal team is looking into the issue and expected the fix. This issue has been resolved and got sign off
UNAM issue reported where Email is not enrolled with policy | C | 7/28 | UNUM data issue reported functional wise its good
Status:
RED status is as the delivery date was moved multiple times due to change in firewall Keys and testing not passed in staging.
Go to Green: Confirmed the change for 5th Aug all testing passed and got Go decision.
The project aims to upgrade from EUA V2 to EUA V3 for portal authentication. This upgrade is intended to remove dependencies on legacy systems, specifically Legacy CAM and Legacy IM.
Scope:
Scope has been identified and locked
Planning:
Will work with TB team to confirm the plan once the technical document is published
Current state:
Development in progress. Planned completion 03/31 Complete
Testing - 4/16 Complete
Inter E2E testing c. Complete
UNAM testing by 04/24 Complete
Team has completed E2E testing and ready for UNAM regression testing requested.
API related issues were resolved by MIM team
This has been deployed and validated, Warranty period ends Sep 5
Target Q1/Q2 2026
Target delivery date was 5/13.l Went on hold as testing did not pass.
Next target date not confirmed; tentative date July 17th
Go No Go scheduled on July 13th to take a call
Next Steps:
Separate working session planned to fix the technical glitch.
UNAM testing has been initiated and issue reports
Testing has been completed and no issues reported In relates to login and log off.
Portal team to come up with resolution and schedule.
Sign off received from QA and staging
Project Manager : Chalam Buddha

## Slide 39
NW Pet - GW Cloud Platform Migration - Complete GWCP Migration - March |  |  |  |  | 
Executive Sponsor | IT Delivery Executive | Business Delivery Executive | Solution Architect | Tech Lead | QE Lead
Braden Love | Charles Hopper | Sastry Samavedam | Kiran Guniganti | Anuja Salgar | Lisa Blank
Budget
Status: Green Budget allocated: $350,000 Team working on : Business team, MIM Resources allocated: Future resource requirement: Test lead + 3
Overall Status
Overall Status: Green Scope: Green Schedule: Green Budget: Green
Overview
This project is aims to migrate the current Guidewire classic platform to Guidewire cloud infrastructure, which is a secure, reliable, and scalable environment where you can build, deploy, and manage insurance software in the cloud. Scope: Initial NW dev support to GWCP lift and shift and E2E testing Scope is defined Scope refinement and finalization in progress and targeted on 01/22 - Complete Planning: In Progress ETA 1/27 Cross application dependencies needs to be factored in Kickoff call completed on 02/18 Current state Initial NW dev support to GWCP lift and shift - Complete Environment setup on QA and PERF – Complete Technical session with the lines – 3/4 - Complete 3/20 SS team to hand over the environments to other lines for testing 4/05 – Complete e2e testing by all lines - Complete UAT completed and sign off – Complete Target Q2 2026 - Go/no GO scheduled on 05/29 Production deployment targeted on 06/12
Accomplishments/Risks
Risk: Classic lower environments platform will be decommissioned after June 12th, this has ben communicated to all the lines Mitigation: Build and align on the overall strategy for environment utilization and deployment governance Maintain close communication with GWCP team to ensure the environments are always available for testing Making sure teams continue use Cloud environments.
Dependencies/Assumptions
Environment Strategy for Upcoming Releases The team are leveraging GWCP lower‑tier environments for the next three months of releases. This approach will: Enable continuous end‑to‑end testing across all teams Reduce disruptions by eliminating frequent environment path changes Improve predictability and stability in the overall release cycle
Notes: Chuck for latest status

## Slide 40: Talend to Python Migration
Status Key | C | Completed |  | On-Schedule |  | Major Issues |  | Some Issues | NS | Not Started
Status Date: | 7/20/2026
2026 Budget | YTD Actuals | Remaining 2026 Forecast | Current YE Forecast | Total Budget
Overall | Scope | Schedule | Financials
Target Delivery: | 7/7
Milestone | Status | Due Date | Notes
ANT Files Dev and Testing | C | 2/25 | 
ANT Prod Deployment | C | 4/15 | 
DOG and CAT E2E testing and UAT | C | 5/1 | 
DOG and CAT Prod Deployment | C | 5/26 | 
PIG, Remittance Testing | C | 5/29 | 
PIG, Remittance Production | C | 6/4 | 
EDI Files, OP Reports E2E and UAT | C | 6/9 | 
EDI Files, OP Reports Production | C | 6/11 | 
Phase 3 Production | C | 6/30 | 
Phase 2 Production | C | 7/7 7/14 | REN, Medone, Concourse – Live in Production ECIF, S3 – Development and Testing Ongoing
Critical Risks/Issues | Status | Target Date | Resolution / Mitigation
There is no scheduled warranty by when the Talend jobs will stop running | C | 7/7 | GIN component was migrated to Python on 6/30 and Planning to move the remaning jobs on 7/7
Status:
Overall Status Yellow
Highlights:
ANT, DOG, CAT, RAT, PIG, BAA, EDI & OP reports : Live in Production
Phase 3 GIN components – Live in Production
Phase 2 – Medone and Concurse Deployed and live in production
Phase 2 – S3 and ECIF Live in production
Project Manager : Rekha Kothandaraman
OpEx Business Lead: Victor

## Slide 41: Planning Funnel

## Slide 42: Business Backlog
Description | OpEX Priority | Budgetary Estimate (Hours) | IT Rec’d | IT Triage Scheduled | Estimate complete Date | Funding Approved Date | Comment
Flagship Claims AI - TaiLWIND Phase 2 |  |  |  |  | NA |  | Initial Phase 2 business Case planning meeting scheduled for 6/24. Will work on target completion dates following that meeting.
Workday Integration (Ideation) | Reserve |  | TBD |  | TBD |  | Escalated - to Leadership regarding delay in releasing work to IT and it's impact to the Portfolio if not received by end of June ($500K remaining)
ABC Landing Page Enhancement |  |  | 4/7/2026 | 4/14/2026 |  |  | 4/14/26 Intake Triage- Align business, UX, product, and data stakeholders before estimating. Sarah Andrews is working with Dillion and team on the requirements actively.
Adding REN data to powerbi report SA4136 |  |  | 7/6/26 | 7/21/26 |  |  | New request
VB search page experience |  |  | 7/6/26 | 7/21/26 |  |  | New request
Pet & Finance Data Lifecycle alignment |  |  | 7/6/26 | 7/21/26 |  |  | New request
MA MPPC Dec Page Update |  |  | 7/6/26 | 7/21/26 |  |  | New request
Of the 7 items currently in Business Backlog, 2 have been received through IT Intake but returned to OpEx pending further business input. See Items in Yellow pending further follow-up and 4 are scheduled for Triage review on 7/21

## Slide 43: Plan Backlog
Description | Planning Team | OpEX Priority | Budgetary Estimate (Hours) | IT Rec’d | Estimate complete Date | Funding Approved Date | Comment

## Slide 44: HLA Backlog
Description | OpEX Priority | Budgetary Estimate (Hours) | Team Impacts | IT Triaged | Estimate complete Date | Funding Approved Date | Comment
DNS & Registration Updates from Precision to CSCGlobal | na | TBD | EW or TB | 6/9/2026 | 7/21/26 (t) | Pending | Triaged - 6/9/26, HLA tentatively scheduled to start 6/23 ; for further business input before HLA can start Pending decision and estimate whether 7 sites (2 with SSO) need rebuilt internally by Pet IT first then migrated to CSCglobal - unclear of size of this effort or interaction yet. Current CSCGlobal estimate for registration migration cost is $308, but could grow if needed to be done as a standalone separate the Moniker transfer.
Tshirt est for MPPC Refresh – Medium/Low | H-1 | TBD | SS, AT | NA | 6/30/2026 | Pending | 6/22/26 – Medium and Low Scope items reduced from 9 items to 3. Completion targeted no later than the end of the month.
Unum Insurance Commission Reporting | Angie - TIA Sathya -Arch | NA | TBD | 6/23/26 | 8/3/26(t) | Pending | Assigned to Angie and Sathya to begin 7/6/26 Target – as capacity becomes available
Enable PED Override for MPPC Payroll | H3 | XS ($50-$100K) | TBD | 2/17/2026 | 7/17/26 | Pending | 7/13/26 – Received notice from Gary that no further work on business process alignment is needed. Validating original estimate with Architecture before submitting for funding,
NW PET: MA Junk Fee Regulation | na |  | 11/18/2025 | 11/25/2025 | NA | Pending | Gary is still working on the requirements with Jennifer. Eta: 4 weeks from 5/19/26
MPI Age Eligibility Changes | na | TBD | Pending | 7/7/26 | Pending | Pending | 7/13/26- HLA Assigned to Chris and Josh. Intake Triaged 7/7/26, Intake received 6/24/26
4 items currently in assessment / estimation process. 1 remains blocked pending cross-functional resolution and workflow agreement.
Notes: Discovery Effort:
DL – 40 hrs
TA - 40
TL -40
Arch - 40
QE - 40
TIA – 40 (NB)
Total = 200 hours

## Slide 45: Pending Funding Backlog -
Description | OpEX Priority | Budgetary Estimate (Hours) | Team Impacts | IT Rec'd | Estimate complete Date | Funding Approved Date | Comment
NW Pet: Sales Conversion by Channel Reporting Data | H-2 | 3XS $90 - $10K / 1 - 111 Hrs | AT | 3/3/2026 | 6/2/26 | Pending | 06/02/26 – HLA Completed by Ken and Charysse, open questions will be addressed during Plan to Build stage, following funding approval and prioritization.
NW Pet Perks page in Portal | H -6 | 2XS $10K - $50K / 111 - 556 Hrs | TB | 3/17/2026 | 6/5/2026 | Pending | 6/4/2026- Charysse Completed XS Budgetary Estimate. If approved, planning team will complete documentation needed to move to build.
Phone Quote email (BPG2) Enhancement | H-4 | Small $100K-$300K | PR | 4/14/2026 | 6/4/2026 | Pending | 6/4/26- Completed Small HLA Estimate by Charysse and Josh. 4/14/26- Intake Triage, Waiting priority from OpEx . In plan backlog
AR Report vs. GL inconsistencies | H-2 | Pet Teams AT&SS: 2XS $10K - $50K / 111 - 556 Hrs FinTech – Pending | AT, SS , Fintech | 4/14/2026 | 6/5/2026 | Pending | 6/22/26 FinTech engaged on 6/11, awaiting estimate by 7/2, The architect updates to HLA were due 6/19 - missed, Angie will fwp with Sathya on 6/22 for new date. During the 6/11 meeting a request to workshop data flow to identify where inconsistencies are happening. Meeting scheduled for 6/26.
GIN BPG8 Task Update | H-8 | 2XS $10K - $50K / 111 - 556 Hrs | SS | 4/14/2026 | 6/5/2026 | Pending | 6/4/26- 2XS estimate based on initial discussion and solutioning with Architect. Pending updated HLA documentation if needed. If approved, planning team will complete documentation needed to move to build.
Direct Bill Validation during GIN Bulk Cancellation | H-7 | XS ($50-$100K) | SS, PP | 4/24/2026 | 5/21/2026 | Pending | Estimated as part of the 2027 Payroll Experience roadmap (GIN Bulk Payment Reversals - XS
Enable Policy Search in EID in GIN | H-3 | XS ($50-$100K) (preliminary) | SS, PP | 4/24/2026 | 6/5/2026 | Pending | 5/26/26 - Preliminary budgetary estimate in conversation with Kiran EIN/EID search in GIN: appears to be a new search-field capability using data already in GIN. If approved, planning team will complete documentation needed to move to build.
Tshirt est for MPPC Refresh – High Priority | H-1 | Variable – emailed to stakeholders | SS, AT, EW, PR | NA | 6/5/2026 | Pending | 6/5/26 - Provided budgetary estimate for High Priority MPPC Product refresh scenarios to OpEX and Product requestors.
Tshirt est for MPPC Refresh – Medium/Low | H-1 | Variable – emailed to stakeholders | SS, AT | NA | 7/2/26 | Pending | 6/22/26 – Medium and Low Scope items reduced from 9 items to 3. Completion targeted no later than the end of the month.
DNS & Registration Updates from Moniker to CSCGlobal | (blank) | 2XS $10K - $50K / 111 - 556 Hrs | No Pet IT | 6/5/2026 | 6/5/2026 | Pending | 6/5/26 - No IT Involvement - CSCGlobal provided estimate (Non Pet Labor) is $50,220. Once budget center approved, CSCGlobal contact and Digital Marketing can begin coordinating migration. Need an OpEx decision as to funding source and whether this will be funded from Portfolio or Marketing Business Dept Code.
Create an agent to manage data quality issue submission from business | 6 | 2XS $10K - $50K / 111 - 556 Hrs | AT | 6/2/26 | 6/23/202 | Pending | 6/23/26 – Estimated as an iterative build using a resource to design, build, test and iterate on agent capabilities to meet scope, including creating an operational B2R approach
17 total items pending funding and prioritization pending major build project estimate submittal

## Slide 46: Pending Funding Backlog
Description | OpEX Priority | Budgetary Estimate (Hours) | Team Impacts | IT Rec'd | Estimate complete Date | Funding Approved Date | Comment
Chase Bank Commerce Platform / Retire Paymentech | H-3 | 2XL$1.5M - $3.M: Mid: $2.3M | EW, SS, PR, GOP, MIM, TB, AT | 12/11/2025 | 3/27/2026 U/D: 7/6/2026 | (blank) | 7/6/26 – Architect reviewed and updated Estimate for submittal 6/22/26 - No final decisions have been made yet on the vendor, but the business case is planned for submittal by 6/30. Naming of the vendor is not a blocker to submission. Enterprise plans to start in 1Q27 and roll-out iteratively through 2028. Flexibility remains in how and when to migrate Pet. We can work with them on the implementation approach and scheduling. Enterprise Funding Pending – Assuming funding received, target a Plan to Build exercise by August 2026 to refine and prep for 2027/ 2028 readiness
Pet Analytics Model Outputs S3 Bucket | H-3 | 3XS $1-$10K upto 111 hrs | AT | 1/6/2026 | 5/20/2026 | Pending | 5/26/26 HLA - 3XS completed by Chris 5/20/26.
Claims History Reports for GIN | (blank) | M $300-500K / 3333 -5556 hrs | AT, MIM, SS , TB | 4/28/2026 | 4/28/2026 | Pending | Implementation complexity is driven primarily by GIN reporting gaps, data architecture setup, and governance considerations.
Callback Widget for VB QEC | (blank) | 2XS $10K - $50K / 111 - 556 Hrs | EW | 4/28/2026 | 4/28/2026 | Pending | Provide same capability on PET as currently articulated on MPI – potential for the MPI D2C Refresh to solve, if goal state is moving MPI to PET – this would be a feature that would be duplicated then.
Cobranding Capabilities for PET to support Unum | (blank) | XS $50K-$100K 556-1,111 hrs | Ew, Mktg | 5/26/2026 | 5/26/2026 | Pending | 5/26/26- Intake Triage completed, T-shirt estimate of XS submitted to OpEx.
Remove Utilization Level Capping in PA | (blank) | 2XS $10K - $50K / 111 - 556 Hrs | SS | 5/26/2026 | 5/26/2026 | Pending | 5/26/26- Intake Triaged, T-shirt estimate 2XS submitted to OpEx for funding/priority
DNS & Registration Updates from Moniker to CSCGlobal | (blank) | 2XS $10K - $50K / 111 - 556 Hrs | No Pet IT | 6/5/2026 | 6/5/2026 | Pending | 6/5/26 - No IT Involvement - CSCGlobal provided estimate (Non Pet Labor) is $50,220. Once budget center approved, CSCGlobal contact and Digital Marketing can begin coordinating migration. Need an OpEx decision as to funding source and whether this will be funded from Portfolio or Marketing Business Dept Code.
Create an agent to manage data quality issue submission from business | 6 | 2XS $10K - $50K / 111 - 556 Hrs | AT | 6/2/26 | 6/23/202 | Pending | 6/23/26 – Estimated as an iterative build using a resource to design, build, test and iterate on agent capabilities to meet scope, including creating an operational B2R approach
Enable PED Override for MPPC Payroll | H3 | Small $100K-$300K | TBD | 2/17/2026 | 7/13/26 | Pending | 7/13/26 – Received notice from Gary that no further work on business process alignment is needed. Removed block and validated Solution and estimate.,
17 total items pending funding and prioritization pending major build project estimate submittal

## Slide 47: Closed / On Hold in Last Month
Description | OpEX Priority | Budgetary Estimate (Hours) | Team Impacts | IT Triaged | Estimate complete Date | Funding Approved Date | Comment
GL vs Pet PIF/DWP Data Definition/Differences | (blank) | 20 hours, $1,800 | GOP, SS, FIN | 4/16/2026 | 5/29/2026 | Denied - Closed | 7/7/26 – Closed out as a new intake and moved to PO and operations team to address. 6/2/26 - Andromeda is not inclined to support funding this via Build as it is an existing system problem with GL Data definition / calculation from REN and GIN.
Pet Reference Data Standardization - Closed IT Intake | NA | NA | NA | 6/9/26 | NA | NA | 6/18/26- Per Focused Architecture & Strategy Meeting 6/18/26- Closed Intake as it represents a business-led enterprise data governance effort currently in strategy and remediation planning. Detailed scoping, governance definition, and prioritization must be completed prior to IT estimation or build engagement. Next Steps have been communicated with Business (Andrea and OpEx)
Data accuracy reporting for Partners from Snowflake | (blank) | 2XS $10K - $50K / 111 - 556 Hrs | AT | 5/26/2026 | 5/26/2026 | Pending | 6/23/26- per Karthik's email analysis is being treated as RUN (defect/data quality issue). Put on Hold if needs Build funding for new enhancement/requirement or if a production issue can be closed
Items that were denied funding, de-prioritized, or closed for other reasons in the last month

## Slide 48: Plan to Build Start
Description | OpEX Priority | Budgetary Estimate (Hours) | Team Impacts | IT Rec'd | Estimate complete Date | Funding Approved Date | Target Handoff | Target Delivery Qtr | Comment
Aggregator Quote Capability Enablement | H-1 | TBD | EW | 5/28/2026 | 8/17/2026 (t) |  |  | 2027 | . Note; that if it is decided to move forward, it will need to complete a Plan to Build /project delivery phase before a refined estimate will be available. Unclear whether it is expected to start this year or next.
TCPA "Consent to Contact" For Outbound Phone Call |  |  | EW, GOP, ITC, PR, SS, TB | 12/11/2025; resubmitted 6/9/26 | 7/22/26 (t) |  |  | 4th Qtr | Successor to 2027 Edelivery – project, complete a quick pass for initial sizing and to determine if room in 4th Qtr to start and carry over
Currently 7 items in Plan to Build / Ready for Hand-off. 1 (Cookie Banner) will remain on hold pending new tool readiness recently funded and added to Plan 2 build. 4 ready to hand-off next week with 2 having dependency on contract signage prior to moving to build backlog, and 2 entering into P2B

## Slide 49: Plan to Build /Ready for Hand-off
Description | OpEX Priority | Budgetary Estimate (Hours) | Team Impacts | IT Rec'd | Estimate complete Date | Funding Approved Date | Target Handoff | Target Delivery Qtr | Comment
Cookie Banner and Footer Links | (blank) | 2XS $10K - $50K / 111 - 556 Hrs | EW | 3/31/2026 | 5/11/2026 | 5/12/2026 | 6/3/2026 Jul-26 | 4th Quarter | 6/3/26- Handoff meeting to SEPM Mark. According to Erica, Moving tools so a decision to Hold cookie banner work in planning until the OneTrust transition path is clear enough to avoid immediate rework.
Remove Exit Warning on Confirmation Page | (blank) | 3XS $1-$10K upto 111 hrs | EW | 4/10/2026 | 5/8/2026 | 5/20/2026 | 7/10/2026 | 4th Quarter | 5/26/26 Kevin approved external funding (Partnership Integrations -non tech)- 5/20. Assigned to Angie for S2L activities 6/1. 6/26 Angie delivered light IPED on 6/16 to Alexis and Charysse in response to email request.
GIN Policy Numbers for DOM Events | (blank) | 3XS $1-$10K upto 111 hrs | EW | 4/10/2026 | 5/8/2026 | 5/20/2026 | 7/10/2026 | 4th Quarter | 5/26/26 Kevin approved external funding (Partnership Integrations -non tech)- 5/20. Assigned to Angie for S2L activities 6/1. 6/26 Angie delivered light IPED on 6/16 to Alexis and Charysse in response to email request.
Partner P.E.T. Migration/Adoption - Aptia 365 Pet Migration | H-5 | $23 -$25K within 2XS $10K - $50K / 111 - 556 Hrs | EW | 3/17/2026 | 5/11/2026 | 5/20/2026 | 7/10/2026 | 4th Quarter | 5/26/26 Kevin approved external funding (Partnership Integrations -non tech)- 5/20. Assigned to Angie for S2L activities 6/1. 6/16/26 - Angie delivered her review of HLA with recommendations.
Partner P.E.T. Migration/Adoption - bswift PET Migration | (blank) | $23 -$25K within 2XS $10K - $50K / 111 - 556 Hrs | EW | 4/24/2026 | 5/11/2026 | 5/20/2026 | 7/10/2026 | 4th Quarter | 5/26/26 Kevin approved external funding (Partnership Integrations -non tech)- 5/20. Assigned to Angie for S2L activities 6/1. 6/16/26 - Angie delivered her review of HLA with recommendations.
Currently 5 items in Plan to Build / Ready for Hand-off. 1 (Cookie Banner) will remain on hold pending new tool readiness recently funded and added to Plan 2 build. 4 ready to hand-off next week with 2 having dependency on contract signage prior to moving to build backlog

## Slide 50: Build Backlog
Description | OpEX Priority | Budgetary Estimate (Hours) | Team Impacts | IT Rec'd | Estimate complete Date | Funding Approved Date | Target Handoff | Handoff Type | Target Delivery Qtr | Comment
NW Pet: Enhancement for Commission Reporting - Internal Batch Process Enhancements for Sales Commission reporting |  | PV Budget: $57,575.04 | AT | NA | NA | 1/1/2026 | Sastry has teams and hours | S2L | 3rd Qtr | This is part of the 2026 IT Risk Operations Annual Portfolio. They are being prioritized and managed by Chalam in coordination with IT leadership
PEC Product & Underwriting Enhancements | P-1 | S - $100K-$300K; 1111-3333 | SS, Doc Sol, AT | 8/19/2025 | 12/3/2025 | 3/11/2026 | 5/15/2026 | Project | 4th Qtr | P2B transition completed 5/14/26 – Assume 4th quarter as Project team coming together now
Hard coded Tags Clean up | (blank) | 3XS $1-10K, 1-111 hrs | TB, EW , Mktg | 5/26/2026 | 5/26/2026 | 5/26/2026 | 6/5/2026 | S2L | 3rd Quarter | Handed off to line for immediate support of Adobe Insight to GTM to avoid business impacts with the shut down of Ensighten
WA MPI 5% Affinity Discount Removal (OpEx #69) | (blank) | 2XS $10-$50K ; 111-500 hr | EW,PR,SS | 3/30/2026 | 3/30/2026 | 4/2/2026 | 7/1/ 2026 | S2L | 4th Quarter | 6/10/26- Originally on-hold pending legal input, received duplicate Intake that this effort is approved to move forward as part of Compliance funding. Need Business confirmation that there are no changes to previous IPE then can schedule STL handoff.
Six items recently funded and added to Plan 2 build. Two items are security oriented and were included in QPP for 3rd Quarter delivery. Remaining 4 are funded directly from Business code and target 4th qtr delivery. 2 have a dependency on contract signage prior to execution

## Slide 51: Run Handoff
Description | OpEX Priority | Budgetary Estimate (Hours) | IT Rec'd | Estimate complete Date | Funding Approved Date | Target Handoff | Handoff Type | Target Delivery Qtr | Comment
AWS KMS to CMK Migration | NA | NA | 6/1/26 | NA | NA | 6/8/26 | Moved to Run |  | Completed Triage – SEPMs understood assignment and will ensure cards built for impacted groups., IT request moved to run and closed.
One item discussed and turned over to SEPMs for Run Mgmt

## Slide 52: Appendix

## Slide 53: 2026 Release Status – Work in Process

## Slide 54
2026 Release Calendar Status
Target Release Date | Project Name | Delivery Leader | Op Ex Business Lead | Status | Value Add | Note (reason for release date push)
9/9/2026 | Add a Pet | Rekha K | Nidia Gudino | On Schedule |  | 
9/9/2026 | MVP3 UW Question Reduction (Find a Vet) | Kinney B | Sara Andrews | On Schedule |  | 
9/16/2026 | Pet Model Law Reboot(Forms) | V Dinesh | Gary Wilson | On Schedule |  | 
9/16/2026 | Pricing Segmentation - (R9) NV, AK, ND | Kinney B | Alex Suarez | On Schedule |  | 
9/16/2026 | MVP3 UW Question Reduction (Find a Vet) - Warranty | Kinney B | Sara Andrews | TBD |  | 
10/14/2026 | Pricing Segmentation - (R10) | Kinney B | Alex Suarez | TBD |  | 
10/14/2026 | UW Optimization MVP1 | Lalitha K | Sarah Andrews | TBD |  | 
11/11/2026 | Pricing Segmentation - (R11) | Kinney B | Alex Suarez | TBD |  | 
11/11/2026 | UW Optimization MVP2 | Lalitha K | Sarah Andrews | TBD |  | 
11/11/2026 | Tailwind Phase 1 (Go-Live) | Shilpa | Dan Clausing | TBD |  | 
11/11/2026 | Employer Portal (Go-Live) | Ali D |  | TBD |  | 
11/11/2026 | Sales Commission Reporting | Chalam | Ellis Ryan | TBD |  | 
11/11/2026 | GIN 2026 Update | Chalam | NA (risk project) | TBD |  | 
11/11/2026 | MMPC - Multiple Denial Code Handling Enhancement | Kinney B | Alex Suarez | TBD |  | 
11/11/2026 | PEC Product & UW Enhancements | Kinney B | Gary Wilson | TBD |  | 
12/9/2026 | MPPC to MPI | Lalitha K | Gary Wilson | TBD |  | 
On Hold | Informatica to Python | Chalam | NA (risk project) |  |  | 
12/9/2026 | Employer Portal (Post Prod-Support) | Ali D |  | TBD |  | 

## Slide 55
Nationwide Financial Portfolio Project Detail: Pet (8/26) | Personal Lines $2M+ Project Detail |  | SLT Sponsor: Joel Carnes / Misty Kuamoo |  |  | Execution Owner: Andromeda Thompson / Braden Love |  | 
Y | Pet Portfolio (Pet Platform Transformation) incl. Payroll Experience & Partner Portal | Capabilities: Modernizing policy administration, billing and claims system | Scope: G | Schedule: Y | Budget: G |  | Actual / Forecast: G | Biz Case On-Track: Yes
Business Case Outcome: Platform Modernization - Pricing sophistication, integration capabilities, & technology risk mitigation | Business Case Outcome: |  | X |  |  |  | X | 
Prior Key Milestones Delivered: <30-60-90> |  | Next Key Milestones Planned: <30-60-90> |  |  |  |  |  | 
Program status: Yellow. Program remains on an executable path; however, Employer Portal schedule contingency has been fully consumed, requiring active risk mitigation to maintain target delivery dates. Employer Portal: Bundle 4 completed, and the first production dark launch was successfully executed. Bundle 5 and 6 schedule at risk due to scope change. Payroll Billing Defects: Trending Green. Wave 2 was deployed to production on 8/19, one day ahead of plan. Wave 1 was previously deployed. Policy Migration: PA and MD releases deployed; validation is underway Manual Migration discovery has begun. The SOW is currently in development Major Medical: Development is in progress. Resource capacity constraints may impact the schedule NY/Unapproved State Product Build: SOW development underway with Cognizant MM-to-MM : SOW development underway with ITS Conversions progress (as of 8/19) excludes Major Medical, legacy products and DOI-unapproved states : | Key Business Outcome Metric (KPI): | Employer Portal – Key Milestones • Bundle 5 Testing: 9/29; Bundle 6 Testing: 10/2 • IAM Dark Launch: 10/8 • Portal Dark Launch: 10/21 • Finance Dark Launch: 10/23 • Production Go-Live: 11/11 • Warranty Release: 12/9 Payroll Billing Defects: Wave 3 deployment scheduled for 9/17 Wave 4 analysis underway Policy Migration: Manual Migration SOW approved; Discovery phase completed. MM-to-MM Migration: SOW approved; discover completed. Major Medical Product Build: Resource gap addressed; development is progressing as planned. New York Product Build : SOW finalized. Core team staffed; discovery phase is beginning. Key Risks: Employer Portal Schedule: Risk: The approved rebaseline has no remaining schedule contingency. Bundle 6 testing, scope decisions, and defect remediation activities could impact October dark launch milestones and the 11/11 go-live. Mitigation: Daily defect and backlog triage is in place; non-MVP scope has been deferred to future releases to protect critical milestones. 2027 Funding: Risk: Preliminary forecasts indicate an additional funding requirement of approximately $2M for 2027. Mitigation: Pet Portfolio and Finance teams are evaluating funding options and accelerating eligible work into 2026 to reduce 2027 demand. |  |  |  |  |  | 
Benefits: | Key Business Outcome Metric (KPI): | Key Performance Indicators: |  |  |  |  |  | 
Platform Modernization: Pricing sophistication Integration capabilities Technology risk mitigation |  | Faster product launches and channel growth More agile product administration and lifecycle management Quicker time to market for new products and changes Better customer and partner experience through self-service Lower cost and risk through modernization and legacy retirement |  |  |  |  |  | 
Product | States Deployed | Policies Migrated | Original Premium Migrated | % Complete
MM to MPI | CA | 66,550 | $58.6M​ | 99.7%​
MPP to MPPC | 49 | 531,739 | $424.3M​ | 86.5%​
WP to MPI | 25 | 37,946 | $81.1M​ | 79.9%​
Total |  | 635,984 | $564 M​ | 86.6%​