## Slide 1
September 2026
Pet Build Portfolio
Delivery Review
Nationwide Pet | Monthly Delivery Review
Reporting month: September 2026 Snapshot date: 10/9/2026 (10/12 weekly)

## Slide 2
September go-lives landed on schedule, and Red projects fell from four to two.
RAG MIX: SEPTEMBER VS. CURRENT (10/9)
Chart: 
| Green | Yellow | Red | Compl. | Not Assd.
September Planview (48) | 18 | 3 | 4 | 5 | 18
Current 10/9 (48) | 9 | 7 | 2 | 9 | 21
Same 48 Planview items. Current status from the 10/12 weekly; pipeline, closed and overhead items shown as Not Assd.
KEY DELIVERY RISKS
Employer Portal (Red): UAT is 46% complete with 289 scenarios left, and Finance has 10 high defects open ahead of the 10/21 dark launch and 11/11 go-live.
GIN / Batch Stabilization (Red): ECIF data-integrity work is paused until a revised estimate is approved; part of the work moves to early 2027.
Underwriting Optimization (Yellow): MVP1 was paused over loss-ratio concerns; MVP1 and MVP2 now release together on 1/13/2027.
Major Medical on GIN (Yellow): line capacity across three delivery teams puts the 2/10/2027 release at risk.
TaiLWIND Claims AI (Yellow): dependent-team timing could compress testing before the 11/11 go-live.
SEPTEMBER AND EARLY OCTOBER ACHIEVEMENTS
Add-A-Pet Improvements went live 9/16.
FirstVet Consultation File delivered to ImageRight 9/16; project complete.
Underwriting Questions MVP3 (Find a Vet) went live 9/16, with warranty release 9/23.
Pricing Segmentation R9 (NV, AK, ND) and Pet Model Law Reboot forms went live 9/16.
TaiLWIND email ingestion went live 10/7, replacing the legacy ImageRight email process.
UPCOMING GO-LIVES / MILESTONES
10/14: Pricing Segmentation R10 (RI, DC, CT); GIN scalability Phase 1.
10/21: Employer Portal dark launch.
11/11: Employer Portal, TaiLWIND Phase 1, PEC, Multi Denial Code, 2026 GIN Update, Pricing R11, GIN API Claims.
12/9: MPPC to MPI dark launch; GIN API Members and Accounts.
1/13/2027: Underwriting Optimization MVP1 and MVP2.
Current status from the 10/12 weekly (status dates 9/25 to 10/9/2026); September Planview shown for comparison.
KEY PROJECT UPDATES
Employer Portal: IAM is green for the 10/15 release. Year-end spend is forecast at $3.7M, $0.4M under budget, and the underspend returns to the portfolio.
Policy migration: 650,790 policies (86.6%, $599M original premium) are now on GIN; manual migration goes live 2/10/2027.
Windows server refresh complete: all 71 servers upgraded by 9/29, ahead of Open Enrollment.
FINANCIALS
Placeholder: Cindy to provide the PPT and spend summary.

## Slide 3
Delivered in September: eight releases reached production.
Project | Work ID | Go-Live Date | Confirmation | Value Statement | Delivery Leader
NW Pet: Add-A-Pet Improvements | 1029314 | 9/16/2026 | Implemented | Draft: Streamlines the add-a-pet quote flow to boost conversion by showing the right products and eliminating redundant data entry. PM to confirm. | Kothandaraman, Rekha
NW Pet: FirstVet Consultation File API (ImageRight change) | 1031012 | 9/16/2026 | Implemented | Draft: Delivers FirstVet telemedicine consultation files into ImageRight for claims use, supporting the September telemedicine launch. PM to confirm. | Kothandaraman, Rekha
NW Pet: PET Enhancement - MPPC UW Questions MVP3 (Find a Vet) | 1030950 | 9/16/2026 (warranty 9/23) | Implemented | PM to provide value statement. | Barbour, Kinney
NW Pet: Pricing Segmentation Sophistication (R9: NV, AK, ND) | 1024050 | 9/16/2026 | Implemented | PM to provide value statement. | Barbour, Kinney
NW Pet: Pet Model Law Reboot (REN form updates) | 1029817 | 9/16/2026 | Deployed; closed for 2026 | Not in the September Planview list. PM to provide value statement. | Dinesh, Venkata
NW Pet: Portal Stability Work (reliability releases) | 1029256 | 9/16, 9/23, 9/29 | Completed | Draft: Fixes Member Portal login, payment and claim-submission reliability issues and removes redundant API calls. PM to confirm. | Dinesh
NW Pet: Payroll Billing Defect Fixes, Wave 3 | PM to provide | 9/8 and 9/17 | Completed | Draft: Wave 3 planned 31 payroll billing defect fixes for production. PM to confirm count and value. | Kothandaraman, Rekha
NW Pet: Refresh the Windows 2016 Server | 1029977 | 9/29/2026 | Completed | Draft: All 71 servers upgraded ahead of Open Enrollment. PM to confirm. | Buddha, Chalam
Go-live status from the 10/12 weekly and its release calendar. Draft value statements come from PM descriptions; orange italic marks items for PM input.

## Slide 4
2026 and 2027 Pet portfolio roadmap.
ROADMAP
Placeholder: Cindy to add the roadmap (from Sandy).

## Slide 5
PPT program and portfolio spend.
PPT AND SPEND
Placeholder: Cindy to add the PPT and spend slide.

## Slide 6
Two Red and seven Yellow projects need attention as of 10/9; Red fell from four to two.
Red
Yellow
Green
Completed
Not Assessed
Project | Work ID | Sept RAG | Current (10/9) | Key Driver | Target Delivery
NW Pet: PPT Payroll Billing Employer Experience | 1029802 | Red | Red | UAT 46% complete (250 of 539 scenarios); 10 high Finance defects open; IAM green for 10/15 | Dark launch 10/21; go-live 11/11/2026
NW Pet: Portal and GIN Stability (GIN / Batch Stabilization) | 1031470 | Green | Red | ECIF data-integrity work on hold pending revised estimate approval; Kafka releases move to 2027 | 12/9/2026; Kafka 2/10 and 3/18/2027
NW Pet: Underwriting Question Optimization for MPI | 1030240 | Red | Yellow | MVP1 October release paused for loss-ratio review; MVP1 and MVP2 combined; holiday testing risk | MVP1/MVP2 1/13/2027; MVP3 3/10/2027
NW Pet: MPPC to MPI Conversion at Notice of Cancel | 1031134 | Green | Yellow | Holiday testing coverage; Steering Committee approved release plan 10/1 | Dark launch 12/9/2026; go-live 2/10/2027
NW Pet: Portal Stability Work (Portal Stabilization) | 1029256 | Green | Yellow | September scope delivered; Q4 scope awaiting funding decision | 12/9/2026
NW Pet: GIN Cap/Scalability to 1.5-2M policies | 1032177 | Not Assessed | Yellow | Phase 1 built; performance and regression testing delayed by a resource gap | Phase 1 10/14/2026; Phase 2 11/11/2026
NW Pet: Unapproved States Product Build | 1030587 | Completed | Yellow | PM and TA roles pending; SOW leadership review 10/16; possible 2026 underspend | TBD (Cognizant kickoff 10/30)
NW Pet – PPT – Major Medical – New Business on GIN | 1014368 | Green | Yellow | DDIT completion risk across EW, MiM and AT lines | 2/10/2027
NW Pet: TaiLWIND Phase 1 (Claims AI) | 1029859 | Yellow | Yellow | Dependent-team timing; processing service about two weeks behind; phased testing | Go-live 11/11/2026
Sept RAG = September Planview. Current = 10/12 weekly status (status dates 9/25 to 10/9/2026).

## Slide 7
Nine projects are on track, and PEC recovered from Yellow to Green.
Red
Yellow
Green
Completed
Not Assessed
Project | Work ID | Sept RAG | Current (10/9) | Key Driver | Target Delivery
NW Pet - PPT - REN2GIN Policy migration-B2C | 1014865 | Green | Green | Manual migration SOW final 9/11; 650,790 policies (86.6%) migrated | Manual migration go-live 2/10/2027
NW Pet: MM to MM Non CA Migration Capability | 1030589 | Completed | Green | ITS discovery complete 10/6; development through 11/13 | 3/10/2027
NW Pet: GIN API v5 Upgrades | 1029979 | Green | Green | Claims APIs in QA/E2E; Members and Accounts APIs in DDIT | Claims 11/11/2026; Members/Accounts 12/9/2026
NW Pet: PEC Product and Underwriting Enhancements | 1029313 | Yellow | Green | QA validation complete 10/6; dark launch 10/9; E2E on track | 11/11/2026
NW Pet: PET Enhancement - MPPC UW Questions MVP3 | 1030950 | Green | Green | MVP3 live 9/16, warranty 9/23; MVP3.5 in development | MVP3.5 2/10/2027
NW Pet: Enhance Multi Denial Code Claims Z160/Z151 | 1029586 | Green | Green | Development and E2E testing complete 10/7; UAT by 10/30 | 11/11/2026
NW Pet: Pricing Segmentation Sophistication | 1024050 | Green | Green | R9 live 9/16; R10 (RI, DC, CT) 10/14; R11 (AL) 11/11; other states to 2027 | R10 10/14/2026; R11 11/11/2026
NW Pet: Enhancement for Commission Reporting | 1029608 | Completed | Green | Kickoff 8/26; E2E design due 10/23; line capacity moved target to January | 1/22/2027
NW Pet: 2026 GIN Upgrades | 1029587 | Green | Green | Development complete 10/10; single deployment scheduled | 11/11/2026
Sept RAG = September Planview. Current = 10/12 weekly status (status dates 9/25 to 10/9/2026).

## Slide 8
Nine projects are complete, including three that finished in September.
Red
Yellow
Green
Completed
Not Assessed
Project | Work ID | Sept RAG | Current (10/9) | Key Driver | Target Delivery
NW Pet: FirstVet Consultation File API | 1031012 | Red | Completed | Live 8/19; ImageRight file transfer live 9/16; minor fixes 10/14 | Completed 9/16/2026
NW Pet: Add-A-Pet Improvements | 1029314 | Green | Completed | Production release 9/16 | Completed 9/16/2026
NW Pet: Refresh the Windows 2016 Server | 1029977 | Green | Completed | All 71 servers upgraded by 9/29, ahead of Open Enrollment | Completed 9/29/2026
NW Pet: Non-Insurance Pet Protection Bundle | 1024485 | Green | Completed | Production release 7/15 | Completed 7/15/2026
NW Pet: Paperless E-Delivery | 1026960 | Green | Completed | MMP2 warranty and one-time data load complete 7/31 | Completed 7/31/2026
Pet Data Center Transition | 1022011 | Green | Completed | Production cutover 7/24 | Completed 7/24/2026
NW Pet: 2026 Product Rate Refresh | 1029254 | Green | Completed | Not in 10/12 weekly; September source reported DDIT, UAT and production complete | PM to confirm date
NW Pet: QEC A/B Testing & Tool Enhancements | 1028060 | Green | Completed | Not in 10/12 weekly; treated as complete | PM to confirm date
NW Pet: NJ MPPC New Product and Rate Capping | 1029148 | Yellow | Completed | Not in 10/12 weekly; treated as complete | PM to confirm date
Sept RAG = September Planview. Current = 10/12 weekly status (status dates 9/25 to 10/9/2026). Items not in the 10/12 weekly are treated as complete pending PM confirmation.

## Slide 9
Overhead, on-hold, carryover, closed and reserve items are kept separate from delivery health.
Red
Yellow
Green
Completed
Not Assessed
Project | Work ID | Sept RAG | Current (10/9) | Key Driver | Target Delivery
NW Pet – PPT Program (Program Overhead) | 1014117 | Red | Overhead | Program overhead work item; Employer Portal status reported under 1029802 | N/A
NW Pet: Move Informatica Powercenter, SQL & Windows | 1029588 | Green | On Hold | Logical halt after September release; estimates under review | Was 12/15/2026
NW Pet: Callback Widget for PET Tool | 1032259 | Completed | Carryover | Deferred to 2027 to avoid Open Enrollment operational risk | 2027 (TBD)
Pet Small Projects allocation for MM | 1015021 | Completed | Closed | Funding allocation bucket, not a delivery item | N/A
NW Pet: Data Quality Submission Chatbot | 1032487 | Not Assessed | Closed | Not in 10/12 weekly; treated as closed | PM to confirm
NW Pet: DNS & Regi Updates Moniker to CSCglobal | 1031784 | Not Assessed | Closed | Not in 10/12 weekly; treated as closed | PM to confirm
NW Pet: Perks Page + uplift in Portal | 1031021 | Not Assessed | Closed | Not in 10/12 weekly; treated as closed | PM to confirm
NW Pet: IT Operational Risk Reserve | 1032179 | Not Assessed | Reserve | Reserve bucket, not a delivery item; not in 10/12 weekly | N/A
NW Pet: Portfolio Readiness OTL Reserve | 1032181 | Not Assessed | Reserve | Reserve bucket, not a delivery item; not in 10/12 weekly | N/A
Sept RAG = September Planview. Current = 10/12 weekly status (status dates 9/25 to 10/9/2026). Items not in the 10/12 weekly are treated as closed pending PM confirmation.

## Slide 10
Six funded pipeline items are in Plan to Build.
Red
Yellow
Green
Completed
Not Assessed
Project | Work ID | Sept RAG | Current (10/9) | Key Driver | Target Delivery
NW Pet: AR Report vs. GL inconsistencies | 1031458 | Not Assessed | Plan to Build | Funding approved 7/28; FinTech engaged | Plan to Build target 10/23/2026
NW Pet: Claims History Report for GIN | 1032289 | Not Assessed | Plan to Build | Funding approved 7/28; GIN reporting complexity | TBD
NW Pet: Enable PED Override for MPPC Payroll | 1030826 | Not Assessed | Plan to Build | Funding approved 7/28 | TBD
NW Pet: Phone Quote Email (BPG2) Enhancements | 1031457 | Not Assessed | Plan to Build | Funding approved 7/28 | TBD
NW Pet: MA Junk Fee Regulation | 1029723 | Not Assessed | Plan to Build | Funding approved 7/28 from the Compliance bucket | Plan to Build target 10/2/2026
NW Pet: Unum Cobranding Capabilities for PET | 1032297 | Not Assessed | Plan to Build | Funding approved 7/28 | Plan to Build target 10/9/2026
Sept RAG = September Planview. Current = 10/12 weekly status (status dates 9/25 to 10/9/2026). Pipeline stage from the 10/12 weekly backlog pages; no delivery RAG until build starts.

## Slide 11
Six pipeline items are ready for hand-off to delivery teams.
Red
Yellow
Green
Completed
Not Assessed
Project | Work ID | Sept RAG | Current (10/9) | Key Driver | Target Delivery
NW Pet: Sales Conversion by Channel Reporting Data | 1030930 | Not Assessed | Ready for Hand-off | Depends on Commission Reporting (1029608); likely carryover | Plan to Build target 8/21/2026
NW Pet: Pet Analytics Model Outputs S3 Bucket | 1030239 | Not Assessed | Ready for Hand-off | Funding approved 7/28 | Plan to Build target 8/21/2026
NW Pet: Enable Policy Search in EID in GIN | 1032258 | Not Assessed | Ready for Hand-off | Funding approved 7/28 | Plan to Build target 8/24/2026
NW Pet: GIN BPG8 Task Update | 1031455 | Not Assessed | Ready for Hand-off | Hand-off to delivery scheduled 9/11 | Plan to Build target 8/24/2026
NW Pet: MA MPPC Dec Page Update | 1032274 | Not Assessed | Ready for Hand-off | Funding approved 7/28 | Not supplied
NW Pet: Remove MPPC Utilization Level Capping PA | 1032273 | Not Assessed | Ready for Hand-off | Funding approved 7/28 | Plan to Build target 8/24/2026
Sept RAG = September Planview. Current = 10/12 weekly status (status dates 9/25 to 10/9/2026). Pipeline stage from the 10/12 weekly backlog pages; no delivery RAG until build starts.

## Slide 12
Health improved: Red fell from four to two, and nine projects are now complete.
48
Total
9
Green
7
Yellow
2
Red
9
Completed
21
Pipeline / Other
RAG DISTRIBUTION
Chart: 
| Green | Yellow | Red | Completed | Pipeline / Other
RAG | 9 | 7 | 2 | 9 | 21
MOVEMENT: SEPTEMBER TO 10/9
Improved: 4 Declined: 4 Completed: 7 Unchanged: 8
Reclassified or not RAG-tracked: 25
Compares September Planview with the 10/12 weekly for the same 48 items. Reclassified covers items Planview marked Completed that are still active, pipeline items, overhead, reserves, on-hold and closed items.
EMERGING RISKS
GIN / Batch Stabilization: Green to Red (ECIF data integrity on hold).
Portal Stability: Green to Yellow (Q4 scope decision).
MPPC to MPI and Major Medical on GIN: Green to Yellow (testing and line capacity).
RED ITEMS
Employer Portal (PPT Payroll Billing Employer Experience)
GIN / Batch Stabilization (Portal and GIN Stability)
TOP YELLOW DELIVERY RISKS
Underwriting Optimization: MVP1 and MVP2 combined for 1/13/2027.
Major Medical on GIN: line capacity for 2/10/2027.
TaiLWIND: dependent-team timing for 11/11.
RECENT SUCCESSES
Add-A-Pet, FirstVet and MVP3 live 9/16.
Pricing R9 and Pet Model Law forms live 9/16.
TaiLWIND email ingestion live 10/7.
PEC dark launch 10/9; back to Green.
LEADERSHIP WATCHLIST
Employer Portal dark launch 10/21 and Finance production 10/23.
11/11 release wave: seven projects scheduled.
Holiday testing coverage for Q1 2027 releases.
FINANCIALS IN FOCUS
Placeholder: Cindy to provide the PPT and spend summary.

## Slide 13
NW Pet: PPT Payroll Billing Employer Experience
Work ID 1029802
OVERALL RAG · MONTH OVER MONTH
SEPTEMBER
CURRENT (10/9)
Red
Red
DESCRIPTION
Self-service administration for payroll employer groups, with payroll billing integrated into Finance (AR posting, GL posting and reconciliation).
RAG ASSESSMENT
Red. UAT is about two weeks behind plan. UAT is 46% complete (250 of 539 scenarios), with 68 defects closed in the past week. Finance testing improved to 50 passed, 0 failed and 10 pending, with 10 high defects open. IAM is green for the 10/15 release.
CHANGES / RISKS / ISSUES
UAT and Finance testing must finish ahead of the 10/21 portal dark launch and 10/23 Finance production deployment.
IAM, Finance and QE dependencies could delay testing further.
Should-have features moved to 6/30/2027 to protect the MVP.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Date
Planning | Completed | 
DDIT | Completed | 9/18/2026
E2E | In Progress | 10/16/2026
Business UAT | In Progress | 10/16/2026
Implementation Plan Review | Upcoming | 
Go/No-Go | Upcoming | 
Stage | Upcoming | 10/21/2026
Implementation | Upcoming | 11/11/2026
FINANCIALS (10/12 WEEKLY, AS REPORTED)
2026 Revised Budget | $4,111,000
YTD Actuals | $2,526,060
Remaining 2026 Forecast | $1,162,654
Total Actuals + Forecast | $3,688,714
Reported as supplied in the 10/12 weekly; financials are not recalculated.
BUSINESS VALUE / BENEFIT
Seamless self-service administration for payroll employer groups.
ACCOMPLISHMENTS (10/12 WEEKLY)
Bundles 2 to 4, Finance development and Bundle 5 and 6 DDIT complete (9/18).
IAM testing and sign-offs complete for the 10/15 release.
Year-end spend forecast $3.7M, $0.4M under budget; underspend returns to the portfolio.
LEADERSHIP CONTACTS
Delivery Leader Dadgar, Ali Business Lead Nas, Victor (as of 10/9)
TARGET / DELIVERY & % COMPLETE
Target delivery Go-live 11/11/2026
49%

## Slide 14
NW Pet: Portal and GIN Stability (GIN / Batch Stabilization)
Work ID 1031470
OVERALL RAG · MONTH OVER MONTH
SEPTEMBER
CURRENT (10/9)
Green
Red
DESCRIPTION
Stabilize GIN batch processing and ECIF data integrity, including moving agreement and party notifications from MQ to Kafka event streams.
RAG ASSESSMENT
Red. The Portal Stability and GIN batch hardening scope was completed by 9/30, and the budget overage was approved 9/25. The ECIF data-integrity effort is on hold until leadership approves a revised estimate. Data extract and ECN collapse work moves to 2027.
CHANGES / RISKS / ISSUES
ECIF analysis delays hold up Kafka topic mapping, onboarding and development.
Kafka production releases move to 2/10/2027 and 3/18/2027.
Revised ECIF estimate awaiting leadership approval (target 10/15).
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Date
Planning | Completed | 
DDIT | In Progress | 11/11/2026
E2E | Upcoming | 2027
Business UAT | Upcoming | 
Implementation Plan Review | Upcoming | 
Go/No-Go | Upcoming | 
Stage | Upcoming | 
Implementation | Upcoming | 12/9/2026
FINANCIALS (10/12 WEEKLY, AS REPORTED)
2026 Budget | $595,000
YTD Actuals | $485,212
Remaining 2026 Forecast | $134,110
Total Budget | $670,000
Reported as supplied in the 10/12 weekly; financials are not recalculated.
BUSINESS VALUE / BENEFIT
Platform stability and data integrity across GIN batch processing and ECIF.
ACCOMPLISHMENTS (10/12 WEEKLY)
Portal Stability and GIN batch hardening scope completed 9/30.
Budget overage approved 9/25.
ECIF confirmed the MQ-to-Kafka requirements phase can finish in 2026.
LEADERSHIP CONTACTS
Delivery Leader Dinesh Business Lead Wilson, Gary (as of 10/9)
TARGET / DELIVERY & % COMPLETE
Target delivery 12/9/2026 (Kafka work into 2027)
N/A

## Slide 15
NW Pet: Underwriting Question Optimization for MPI
Work ID 1030240
OVERALL RAG · MONTH OVER MONTH
SEPTEMBER
CURRENT (10/9)
Red
Yellow
DESCRIPTION
Increase new business writings by simplifying point-of-sale underwriting and accelerating rule-based decisions.
RAG ASSESSMENT
Yellow. The business paused the MVP1 October release over loss-ratio concerns, then kept the original requirements and addressed the concern through business rules. MVP1 and MVP2 are now one release targeting production 1/13/2027; MVP3 targets 3/10/2027.
CHANGES / RISKS / ISSUES
Holiday UAT and testing overlap Thanksgiving through New Year.
Dependency on the ESS team for Enterprise Authentication V3.
Funding for remaining testing and release activities to be confirmed.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Date
Planning | Completed | 
DDIT | In Progress | 11/26/2026
E2E | Upcoming | 12/9/2026
Business UAT | Upcoming | 1/1/2027
Implementation Plan Review | Upcoming | 11/26/2026
Go/No-Go | Upcoming | 1/6/2027
Stage | Upcoming | 1/6/2027
Implementation | Upcoming | 1/13/2027
FINANCIALS (10/12 WEEKLY, AS REPORTED)
2026 Budget | $1,090,000
YTD Actuals | $529,525
Remaining 2026 Forecast | $557,589
Current YE Forecast | $1,087,115
Reported as supplied in the 10/12 weekly; financials are not recalculated.
BUSINESS VALUE / BENEFIT
More new business through simpler point-of-sale underwriting and faster rule-based decisions.
ACCOMPLISHMENTS (10/12 WEEKLY)
Business confirmed requirements unchanged; no scope change.
MVP1 and MVP2 consolidated with the GIN Provider Information change for Claims.
MVP3 development progressing toward March 2027.
LEADERSHIP CONTACTS
Delivery Leader Kumar, Lalitha Business Lead Andrews, Sarah (as of 10/9)
TARGET / DELIVERY & % COMPLETE
Target delivery 1/13/2027 (MVP1/MVP2); 3/10/2027 (MVP3)
57%

## Slide 16
NW Pet: MPPC to MPI Conversion at Notice of Cancel
Work ID 1031134
OVERALL RAG · MONTH OVER MONTH
SEPTEMBER
CURRENT (10/9)
Green
Yellow
DESCRIPTION
Offer cancelled MPPC policyholders conversion to MPI when their employer relationship ends.
RAG ASSESSMENT
Yellow. The team is working toward the 12/9/2026 dark launch and the 2/10/2027 production go-live. The Steering Committee approved the change requests, release plan and funding on 10/1. Holiday testing coverage and finalizing 2027 funding are the open risks.
CHANGES / RISKS / ISSUES
Holiday testing overlaps and shared business and technology testers.
Enterprise Authentication V3 needed for the UW Rules Engine API (not a release blocker).
2027 funding beyond the approved amount still under evaluation.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Date
Planning | Completed | 
DDIT | In Progress | 10/28/2026
E2E | In Progress | 11/27/2026
Business UAT | Upcoming | 1/29/2027
Implementation Plan Review | Upcoming | 
Go/No-Go | Upcoming | 1/29/2027
Stage | Upcoming | 12/9/2026
Implementation | Upcoming | 2/10/2027
FINANCIALS (10/12 WEEKLY, AS REPORTED)
2026 Budget | $880,000
YTD Actuals | $441,003
Remaining 2026 Forecast | $438,957
Current YE Forecast | $879,960
Reported as supplied in the 10/12 weekly; financials are not recalculated.
BUSINESS VALUE / BENEFIT
Keeps customers covered by offering MPI when MPPC coverage ends with an employer.
ACCOMPLISHMENTS (10/12 WEEKLY)
Steering Committee approved change requests, release plan and funding (10/1).
Dark launch on track for 12/9/2026.
Holiday resource mitigation plan in progress.
LEADERSHIP CONTACTS
Delivery Leader Kumar, Lalitha Business Lead Wilson, Gary (as of 10/9)
TARGET / DELIVERY & % COMPLETE
Target delivery Go-live 2/10/2027
N/A

## Slide 17
NW Pet: Portal Stability Work (Portal Stabilization)
Work ID 1029256
OVERALL RAG · MONTH OVER MONTH
SEPTEMBER
CURRENT (10/9)
Green
Yellow
DESCRIPTION
Improve Member Portal reliability: login, payments, claim submission, performance and code quality.
RAG ASSESSMENT
Yellow. All work identified for the current $75K budget was delivered by 9/30. Q4 scope (Portal on-premises database decommission) is defined but needs a funding decision, or a decision not to pursue Q4 work.
CHANGES / RISKS / ISSUES
No Q4 resources until scope and funding are decided.
Decision needed to plan resources for Q4.
Current resources allocated only through September.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Date
Planning | Completed | 
DDIT | Completed | 
E2E | Completed | 
Business UAT | Completed | 
Implementation Plan Review | Completed | 
Go/No-Go | Completed | 
Stage | Completed | 
Implementation | Completed | 9/29/2026
FINANCIALS (10/12 WEEKLY, AS REPORTED)
2026 Budget | $75,000
YTD Actuals | $74,653
Remaining 2026 Forecast | $347
Total Budget | $75,000
Reported as supplied in the 10/12 weekly; financials are not recalculated.
BUSINESS VALUE / BENEFIT
More reliable Member Portal login, payments and claim submission.
ACCOMPLISHMENTS (10/12 WEEKLY)
Angular upgrade deployed 9/16.
Login, payment and claim-submission reliability fixes deployed 9/16.
Redundant API calls removed 9/23; code cleanup and memory-leak fixes 9/29.
LEADERSHIP CONTACTS
Delivery Leader Dinesh Business Lead Gudino, Nidia (as of 10/9)
TARGET / DELIVERY & % COMPLETE
Target delivery 12/9/2026
N/A

## Slide 18
NW Pet: GIN Cap/Scalability to 1.5-2M policies
Work ID 1032177
OVERALL RAG · MONTH OVER MONTH
SEPTEMBER
CURRENT (10/9)
Not Assessed
Yellow
DESCRIPTION
Scale GIN to support 1 to 2 million policies.
RAG ASSESSMENT
Yellow. Phase 1 development is complete. Performance and regression testing slipped because of an emergency offshore resource absence; an alternate team is helping finish by 10/12. Phase 2 long-term solutions target 11/11.
CHANGES / RISKS / ISSUES
Performance and regression testing completion (10/12).
Phase 2 claim-transaction work pending business confirmation.
Schedule impact analysis in progress.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Date
Planning | Completed | 8/31/2026
DDIT | In Progress | 11/11/2026
E2E | In Progress | 10/12/2026
Business UAT | Upcoming | 
Implementation Plan Review | Upcoming | 
Go/No-Go | Upcoming | 
Stage | Upcoming | 
Implementation | Upcoming | 10/14/2026
FINANCIALS (10/12 WEEKLY, AS REPORTED)
2026 Budget | $463,000
YTD Actuals | $172,318
Remaining 2026 Forecast | $315,537
Current YE Forecast | $463,000
Reported as supplied in the 10/12 weekly; financials are not recalculated.
BUSINESS VALUE / BENEFIT
Supports growth to 1 to 2 million policies on GIN.
ACCOMPLISHMENTS (10/12 WEEKLY)
Discovery, project plan and solution approach complete.
Snowflake infrastructure upgrade and RS2SNF architecture complete.
QE lead identified (9/4).
LEADERSHIP CONTACTS
Delivery Leader Dinesh Business Lead Wilson, Gary (as of 10/9)
TARGET / DELIVERY & % COMPLETE
Target delivery Phase 1 10/14/2026; 12/9/2026
N/A

## Slide 19
NW Pet: Unapproved States Product Build
Work ID 1030587
OVERALL RAG · MONTH OVER MONTH
SEPTEMBER
CURRENT (10/9)
Completed
Yellow
DESCRIPTION
Build NY, unapproved migration states and legacy products in GIN.
RAG ASSESSMENT
Yellow. Staffing and the Cognizant start are delayed. An architect is assigned; PM and TA roles are pending. The SOW goes to leadership review 10/16, with the final SOW targeted 10/30. Part of this year's budget may return to the portfolio if work starts late.
CHANGES / RISKS / ISSUES
Potential 2026 underspend of the $267K budget.
PM and TA roles not yet staffed.
Cognizant kickoff (10/30) depends on SOW approval.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Date
Planning | In Progress | 10/30/2026
DDIT | Upcoming | 
E2E | Upcoming | 
Business UAT | Upcoming | 
Implementation Plan Review | Upcoming | 
Go/No-Go | Upcoming | 
Stage | Upcoming | 
Implementation | Upcoming | TBD
FINANCIALS (10/12 WEEKLY, AS REPORTED)
2026 Budget | $267,000
YTD Actuals | $2,056
Remaining 2026 Forecast | $216,571
Total Actuals + Forecast | $218,627
Reported as supplied in the 10/12 weekly; financials are not recalculated.
BUSINESS VALUE / BENEFIT
Moves remaining states and legacy products onto GIN.
ACCOMPLISHMENTS (10/12 WEEKLY)
Procurement intake complete (8/10).
Draft SOW complete (9/11).
Architect assigned.
LEADERSHIP CONTACTS
Delivery Leader Dadgar, Ali (Interim) Business Lead Wilson, Gary (as of 10/9)
TARGET / DELIVERY & % COMPLETE
Target delivery TBD
N/A

## Slide 20
NW Pet – PPT – Major Medical – New Business on GIN
Work ID 1014368
OVERALL RAG · MONTH OVER MONTH
SEPTEMBER
CURRENT (10/9)
Green
Yellow
DESCRIPTION
Build Major Medical new business on GIN.
RAG ASSESSMENT
Yellow. DDIT completion across the EW, MiM and AT lines is at risk for the 2/10/2027 release. MiM committed based on a second developer. Delivery timing for change request Z-160 and reporting work is not yet final.
CHANGES / RISKS / ISSUES
AT line capacity for the February 2027 timeline.
MiM capacity and commitment to the February release.
EW prioritization.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Date
Planning | Completed | 
DDIT | In Progress | 12/23/2026
E2E | Upcoming | 1/6/2027
Business UAT | Upcoming | 1/29/2027
Implementation Plan Review | Upcoming | 
Go/No-Go | Upcoming | 
Stage | Upcoming | 2/9/2027
Implementation | Upcoming | 2/10/2027
FINANCIALS (10/12 WEEKLY, AS REPORTED)
2026 Budget | $840,000
YTD Actuals | $306,913
Remaining 2026 Forecast | $502,717
Total Actuals + Forecast | $809,631
Reported as supplied in the 10/12 weekly; financials are not recalculated.
BUSINESS VALUE / BENEFIT
Moves Major Medical new business onto the modern GIN platform.
ACCOMPLISHMENTS (10/12 WEEKLY)
MiM commitment received for the Partnership API workstream.
Test strategy prepared and being finalized.
Z-160 requirements being finalized.
LEADERSHIP CONTACTS
Delivery Leader Kulkarni, Shilpa Sachin Business Lead Wilson, Gary (as of 10/9)
TARGET / DELIVERY & % COMPLETE
Target delivery 2/10/2027
N/A

## Slide 21
NW Pet: TaiLWIND Phase 1 (Claims AI)
Work ID 1029859
OVERALL RAG · MONTH OVER MONTH
SEPTEMBER
CURRENT (10/9)
Yellow
Yellow
DESCRIPTION
AI-enabled claims intake and document transformation across Pet claims workflows.
RAG ASSESSMENT
Yellow. Development continues with the REN, GIN, MiM, DMX and Portal teams. Dependent-team timing remains the risk: the GOP line committed to 10/15 and the processing service is trending about two weeks behind, so testing is phased.
CHANGES / RISKS / ISSUES
Dependent-team timelines (SS, AT, GOP, DMX, MiM) to be agreed by 10/15.
Operational metrics for leadership, model and operations to be defined by 10/30.
Cross-team access provisioning friction.
STANDARD MILESTONE TRACK (8 STAGES)
Stage | Status | Date
Planning | Completed | 
DDIT | In Progress | 10/15/2026
E2E | In Progress | 10/15/2026
Business UAT | Upcoming | 
Implementation Plan Review | Upcoming | 
Go/No-Go | Upcoming | 
Stage | Upcoming | 
Implementation | Upcoming | 11/11/2026
FINANCIALS (10/12 WEEKLY, AS REPORTED)
2026 Budget | $1,500,000
YTD Actuals | $1,034,379
Remaining 2026 Forecast | $480,305
Total Actuals + Forecast | $1,519,832
Reported as supplied in the 10/12 weekly; financials are not recalculated.
BUSINESS VALUE / BENEFIT
Reduces manual claims intake and builds a path to scalable claims automation.
ACCOMPLISHMENTS (10/12 WEEKLY)
Email ingestion live 10/7, replacing the legacy ImageRight email process.
Document Transformation Service third production dark launch (10/8).
Portal ingestion deployed (10/8); claim notification service 85% complete.
LEADERSHIP CONTACTS
Delivery Leader Kulkarni, Shilpa Sachin Business Lead Clausing, Dan (as of 10/9)
TARGET / DELIVERY & % COMPLETE
Target delivery Go-live 11/11/2026
51%

## Slide 22
Source hierarchy and reporting conventions keep the September view factual and auditable.
SOURCE REFERENCES
September Planview source (September comparison values)
https://nationwide-be.glean.com/api/v1/downloadchatfile/4a6d42aa59af4cfb915a23d20ee9a127
August monthly deck (structure and August reference)
https://nationwide-be.glean.com/api/v1/downloadchatfile/7de8e6a82b7645d991dd40b812ae04bd
October 12 weekly update (authoritative current status)
https://nationwide-be.glean.com/api/v1/downloadchatfile/bd397ec5813a4a798ef2bf594df7ff54
Nationwide branding template
https://nationwide-be.glean.com/api/v1/downloadchatfile/6e51c3eb3505444c8de9c5104855bfdc
Pet Build rocket logo
https://nationwide-be.glean.com/api/v1/downloadchatfile/85e0dcfcf8c34d26855c580f0365b378
REPORTING ASSUMPTIONS
September 2026 reporting month; current status from the 10/12 weekly (status dates 9/25 to 10/9/2026).
Sept RAG = September Planview; Current = 10/12 weekly status.
Items not in the 10/12 weekly are shown as closed or completed and marked for PM confirmation.
Pipeline items show their 10/12 backlog stage (Plan to Build, Ready for Hand-off, Carryover).
PPT Program (1014117) classified as program overhead per the 2027 annual planning workbook.
Business leads from the 10/12 weekly. Orange italic text marks placeholders.
RAG DEFINITIONS
Green — On track. Major milestones progressing as planned.
Yellow — At risk. Key dependency, schedule, funding, or resource concerns require monitoring.
Red — Critical risk impacting delivery. Immediate mitigation and leadership support required.
Completed — Delivery completed successfully.
Not Assessed — Status unavailable, planning-only, or data insufficient (supported source reasons only).
MILESTONE LEGEND & DATA QUALITY
Milestone statuses: Completed, In Progress, Upcoming. Dates appear only when supplied; none invented.
48 Planview items represented; nine current Red/Yellow projects have detail slides.
Detail-slide financials are as reported in the 10/12 weekly; not recalculated.
Delivered in September also lists weekly-tracked releases not in the September Planview list.
% complete from September Planview where available; N/A where not supplied.
This report covers September 2026 with current status from the 10/12 weekly (status dates through 10/9/2026). Source fields are reported as supplied. Financial calculations are not modified or recalculated. · Nationwide internal use only.