## Slide 1
One cadence releases 7,484 recurring attendee-hours a year
9,480
hours
Current layered recurring attendee-hours
1,996
hours
Future recurring attendee-hours (one cadence)
7,484
hours released
78.9% reduction in recurring attendee-hours
$748,400 annual capacity value released, valued at $100 per attendee-hour.
Recurring run-rate only, using the tiered proposal's method (30-minute meetings, $100 per attendee-hour). Event-based checkpoints are excluded in both models.
Notes: Same method as the tiered proposal. Future hours: 22 projects x 3 required attendees x 0.5 hr x 52 weeks = 1,716; weekly Portfolio Pulse 8 x 0.5 x 52 = 208; monthly Portfolio Review 6 x 1 x 12 = 72. Total 1,996.

## Slide 2
Meetings are fragmented across 52 types and 22 projects
52
distinct meeting types
22
projects
31
recurring meeting types
1.41
recurring types per project (avg)
Where the recurring hours sit today
Share of 9,246 current project recurring attendee-hours
Medium / Large
8,544 hours (92%)
Small / Straight to the Lines
702 hours (8%)
Key message The problem is duplicated coordination, not project size.
Notes: All figures on this slide come from the original Meetings Proposal. Only 8% of recurring hours sit in Small and Straight to the Lines work, so separate size tiers for them save little.

## Slide 3
Sizing by cost alone adds rules without adding control
The tiered proposal: three rule sets for one team
Medium / Large
Core forum
Weekly, 6 attendees
Meeting types
9 lifecycle + 8 event-based types
Small
Core forum
Every other week, 6 attendees
Meeting types
3 standard + 2 kickoff types
Straight to the Lines
Core forum
Monthly, 4 attendees
Meeting types
1 Finance & Risk Review
Each project must first be classified, and re-classified when its budget changes. The proposal's own Phase 3 still has to classify two projects and separate Medium from Large.
Why one cadence is simpler
Cost does not predict coordination need. Risk, dependencies and the number of teams do.
The largest projects are about $5M, so "large" says little about complexity.
Small and Straight to the Lines work holds only 8% of recurring hours.
One rule is easier to teach, follow and audit than three.
Key message Let the work's risk add checkpoints, not its budget add meetings.
Notes: Tier details are taken from the original proposal (slide 5). The $5M figure reflects the current sizing bands as described by the delivery team.

## Slide 4
Three recurring meetings, plus checkpoints when needed
Portfolio Review
Monthly, 60 minutes. Budget versus forecast, capacity, benefits and trends across the portfolio. Reprioritize and fund.
Monthly, 6 people
Portfolio Pulse
Weekly, 30 minutes. Leadership reviews the dashboard for all 22 projects and works only red, amber and pending decisions.
Weekly, 5 people
Project Sync
Weekly, 30 minutes, every project in the same format: risks, blockers, dependencies and next decisions.
Weekly, 3 people
Checkpoints
Requirements, design, estimate approval, Go / No-Go and closeout, held only when the phase calls for them.
Event-based
Weekly Update
One standard written update per project, due Friday at noon. It feeds the dashboard, so status never needs a meeting.
No meeting
Key message Every project runs the same rhythm. Leadership sees all of it every week.
Notes: Projects follow one cadence with no size tiers. Leadership visibility comes from the standard weekly update and dashboard, discussed by exception in the weekly Portfolio Pulse, with money and trends in the monthly Portfolio Review.

## Slide 5
How leadership keeps a weekly pulse on every project
Tuesday to Thursday
Project Syncs
30 minutes each. Teams work risks, blockers and next decisions.
Friday by noon
Weekly Updates
Each TPM posts the standard update. The dashboard refreshes for all 22 projects.
Monday
Portfolio Pulse
30 minutes. Leadership works only red, amber and decisions needed.
First Monday of each month, after the Pulse
Portfolio Review, 60 minutes
Budget versus forecast, capacity, benefits and trends. Reprioritize and fund.
What leadership sees every week
Status for all 22 projects: schedule, cost, scope and risk, each red, amber or green
Next milestone and its date
Top risks and open blockers
Decisions needed, and by when
What changed since last week
Key message Leadership sees every project every week, without sitting in every project meeting.
Notes: The pulse comes from information, not attendance. Every project posts the same update every week, so the dashboard is complete before the Monday Pulse.

## Slide 6
Bare-minimum attendance: deciders attend, others on call
Meeting | Must attend | Joins only when needed | Gets the written update
Project Sync weekly, 30 min | TPM (runs it) Product Owner or Business Lead Tech Lead | Agile Lead, Architect, QE, Release, SRE, SMEs, for their agenda item only | Agile Leads, sponsors, stakeholders
Portfolio Pulse weekly, 30 min | Director or AVP (chair) Portfolio lead (runs it) Strategy business owners (up to 3) | TPMs of red or amber projects, for their slot only | All TPMs and the Planning team
Portfolio Review monthly, 60 min | Director or AVP (chair) Portfolio lead (runs it) Finance partner Strategy business owners (up to 3) | TPMs if asked; architects for capacity trade-offs | All TPMs and sponsors
Checkpoints as needed | The decision owner and the people doing the work | Example, Go / No-Go: TPM, Release Management, QE lead, Product Owner | Core project team
Key message Attendance follows decision rights, not awareness.
Notes: Required attendees are the minimum needed to make the decision each meeting exists for. The Pulse estimate assumes 3 TPMs join on average each week.

## Slide 7
Early-warning triggers surface slips before they grow
Signal | Amber | Red | Where it goes
Schedule | Milestone missed, or forecast finish up to 2 weeks late | More than 2 weeks late, or a gate date at risk | Portfolio Pulse
Cost | Forecast more than 5% over budget | Forecast more than 10% over budget | Pulse; Review for funding
Blockers | Open more than 5 business days | Open more than 10 business days, or blocking a gate | Portfolio Pulse
Scope | Change request pending | Change affects the date or budget | Pulse for a decision
Resources | Key role at risk, or a shared-resource conflict | Key role unfilled for 2 weeks or more | Portfolio Pulse
Missing update | No update by Friday noon: automatically amber | Two missed updates in a row | Portfolio lead follows up
Proposed starting thresholds. Calibrate them with leadership during the first 90 days.
Key message Slips are caught by rule every week, not by chance in a meeting.
Notes: Thresholds are suggestions to start the conversation, not current policy.

## Slide 8
One cadence cuts recurring hours by 79%, versus 65% tiered
Chart: 
| Today | Tiered proposal | One cadence
Recurring attendee-hours per year | 9480 | 3300 | 1996
9,480 → 1,996
total recurring attendee-hours
7,484 hours
released annually
$748,400 at $100 / hour
How 1,996 is built
Project Syncs 22 x 3 x 30 min x 52 = 1,716
Portfolio Pulse 8 x 30 min x 52 = 208
Portfolio Review 6 x 60 min x 12 = 72
Pulse: 5 required plus 3 TPMs on average
Key message One cadence releases 1,304 more hours a year than the tiered proposal ($130,400).
Notes: Tiered proposal figure is its three-strategy case (3,300 hours). Today = 9,480 hours from the original proposal. If 6 TPMs join the Pulse each week instead of 3, the total is 2,074 hours, still a 78% reduction.

## Slide 9
Side by side: the tiered proposal versus one cadence
 | Tiered proposal | One cadence
Project size tiers | 3 (by cost) | None
Project forum | Weekly, every other week or monthly; 6 or 4 attendees | Weekly for all; 3 required
Leadership forums | Weekly per strategy (8) plus portfolio every other week (6) | Weekly Pulse (5) plus monthly Review (6)
Leadership visibility | Projects discussed within strategy forums | All 22 projects on one dashboard every week
Early-warning triggers | None stated | Amber and red thresholds for 6 signals
Recurring attendee-hours | 3,300 | 1,996
Reduction from 9,480 | 65.2% | 78.9%
Capacity value | $618,000 | $748,400
Model: Future recurring attendee-hours = (projects x 78) + 280. 22 projects = 1,996.
Key message Conservative: one cadence counts all 22 projects; the tiered model counted 20.
Notes: 78 = 3 attendees x 0.5 hr x 52 weeks per project. 280 = Portfolio Pulse 208 plus Portfolio Review 72.

## Slide 10
Five rules keep meetings useful and cost effective
Update first, meet second
The standard update is due Friday at noon. No update means the project shows amber.
Exceptions get the airtime
Green projects are read, not discussed. Meetings cover red, amber and decisions.
No decision, no project meeting
Nothing to decide or unblock? Cancel the sync. The written update is still required.
Specialists by invitation
Architects, QE, Release and SRE join for their agenda item, then leave.
Escalate one level, log once
Project Sync to Pulse to Review. Decisions and risks are recorded once, in the RAID log.
Key message The Pulse never skips. Project syncs skip only when there is nothing to decide.
Notes: Savings from cancelled project syncs are not counted in the 1,996-hour estimate.

## Slide 11
Roll out in three phases
Phase 1
Standardize
Publish the cadence charter, the standard weekly update, the dashboard and the early-warning triggers. Name required attendees.
Phase 2
Launch
Move every project to the weekly Project Sync. Start the weekly Pulse and monthly Review. Retire size tiers and duplicate forums.
Phase 3
Measure
Track hours, decisions and slips monthly. At 90 days, ask leadership whether their pulse is strong enough, and adjust.
Track success through
Recurring meeting hours Decisions made Overdue actions Slips flagged amber before red Leadership confidence rating
Notes: The leadership confidence rating answers the key concern directly: is the pulse strong enough? If not, adjust at 90 days.

## Slide 12
Decision requested: adopt one cadence for every project
✓
Adopt one meeting cadence for all projects in place of cost-based size tiers.
✓
Approve the weekly Project Sync, weekly Portfolio Pulse and monthly Portfolio Review, with their required attendees.
✓
Approve the standard weekly update, dashboard and early-warning triggers as the portfolio's pulse.
✓
Accept 1,996 recurring attendee-hours ($748,400 released) as directional, and review at 90 days.
Weekly pulse. Fewest people. Decisions where they belong.