## Slide 1
PET IT DELIVERY | ROLE GUIDE
Delivery Coordinator: First Line of Portfolio Governance
The role keeps Planview Portfolio accurate and executive-ready, so project managers and scrum masters can focus on delivery and leaders see data that reflects reality.
Planview Portfolio
Schedules and Releases
Allocations
Financials
Weekly, Fridays 10 AM
WHAT THE ROLE DOES
Runs the weekly RAG status report
Confirms every Yellow or Red has a clear explanation
Flags Green projects with overdue milestones or open changes
Flags status changes with no supporting comments
Checks the executive narrative is present and current
CATEGORY 1
Status and RAG Integrity
WHY IT MATTERS
Status tells the truth before leaders see it. No surprises in reviews.
WHAT THE ROLE DOES
Runs Milestone Schedule, Release and Change reports
Finds past-due milestones still marked Open
Finds delivered releases not yet marked Complete
Asks if each open change request should stay open
Asks if an open change should move status to at least Yellow
CATEGORY 2
Milestones, Releases and Changes
WHY IT MATTERS
Schedules match reality, and scope changes are visible in project health.
WHAT THE ROLE DOES
Sets up a shared past-due task report anyone can bookmark
Runs it every Friday by 10 AM
Emails each task owner with past-due items
Follows up until updated or reforecast
Escalates repeat exceptions to the delivery lead
CATEGORY 3
Schedule Compliance
WHY IT MATTERS
One shared view keeps everyone accountable, and schedules stay current weekly.
WHAT THE ROLE DOES
Reviews allocation reports for each resource
Confirms allocations total 8 hours per day
Corrects clear allocation gaps or overages
Asks the project manager when the right project is unclear
Reports capacity exceptions
CATEGORY 4
Capacity and Allocations
WHY IT MATTERS
Hours land on the right work, so cost and capacity data can be trusted.
WHAT THE ROLE DOES
Updates and validates Planview financials
Prepares financials for the Monday leadership review
Reports financial variance
Sends timesheet reminders
Tracks timesheet compliance
CATEGORY 5
Financials and Timesheets
WHY IT MATTERS
Leaders review accurate spend and forecasts, and actuals stay complete.
Weekly governance rhythm
FRIDAY BY 10 AM
Run the reports
RAG, milestones, releases, changes, tasks, allocations
FRIDAY
Notify owners
One clear note per exception to the responsible owner
BY EOD MONDAY
Owners update
Status, completion or a revised forecast
MONDAY
Leadership review
Clean financials and status data
Sample note: Milestone “UAT Complete” was due 10/10 and remains Open in Planview. Please update the status or provide a revised forecast by EOD Monday.
Where the line is
THE ROLE DOES
Identifies issues
Notifies owners
Recommends corrections
Follows up to closure
Produces governance reports
OWNERS DECIDE
Final RAG status
Forecast dates
Scope and change approval
Delivery priorities
Quality checker, not decision maker.
Benefits to team and portfolio
Project managers and scrum masters focus on delivery
Planview stays the trusted system of record
Issues surface early, before leadership reviews
Consistent standards across every project
Better return on the Planview investment
Accurate data. Clear status. Ready for leaders every Monday.
Pet IT Delivery internal role guide. Proposed Delivery Coordinator responsibilities for discussion.